## Tasks_Corrected
ID | WBS | Name | Duration_Original | Duration_MPXJ_Hours | Duration_Corrected | Duration_Corrected_Hours | Duration_Source | Start | Finish | Percent Complete | Predecessors | Resource Names | Cost | Work | Critical | Milestone | Summary | Notes | Outline Level
0 | 0 | Programa FCC II 2025 Rev 5 19-6 FALTA AFINAR PEM Y DETALLES | 33.93680555555556d | 814.4833 | 33.93680555555556d | 814.4833 | MPXJ | 2025-07-14T00:00 | 2025-08-16T23:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 0
1 | 1 | CRACKING CATALITICO II | 33.93680555555556d | 814.4833 | 232.0h | 231.9667 | Nativo (factor 0.3x) | 2025-07-14T00:00 | 2025-08-16T23:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 1
2 | 1.1 | PARO DE UNIDAD | 3.747916666666667d | 89.95 | 814.5h | 814.4833 | Nativo (factor 9.1x) | 2025-07-14T00:00 | 2025-07-17T18:00 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 2
3 | 1.1.1 | INICIO DEL PARO DE UNIDAD | 1.0eh | 1 | 90.0h | 89.95 | Nativo (factor 90.0x) | 2025-07-14T00:00 | 2025-07-14T01:00 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 3
4 | 1.1.2 | BAJADA DE CARGA | 5.0eh | 5 | 24.0h | 24 | Nativo (factor 4.8x) | 2025-07-14T01:00 | 2025-07-14T06:00 | 0 | 3FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 3
5 | 1.1.3 | COLOCAR BC LB | 89.0eh | 89 | 120.0h | 120 | Nativo (factor 1.3x) | 2025-07-14T00:00 | 2025-07-17T17:00 | 0 | 3SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 3
6 | 1.1.4 | ENTREGA DE EQUIP.GRAL. | 1.0eh | 1 | 2136.0h | 2136 | Nativo (factor 2136.0x) | 2025-07-17T17:00 | 2025-07-17T18:00 | 0 | 5FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 3
7 | 1.2 | MANTENIMIENTO | 28.690277777777776d | 688.5667 | 24.0h | 24 | Nativo (factor 0.0x) | 2025-07-15T06:00 | 2025-08-12T23:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 2
8 | 1.2.1 | ZONA DE REACCION | 28.690277777777776d | 688.5667 | 28.690277777777776d | 688.5667 | MPXJ (validado) | 2025-07-15T06:00 | 2025-08-12T23:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 3
9 | 1.2.1.1 | BC 48" | 12.0eh | 12 | 688.6h | 688.5667 | Nativo (factor 57.4x) | 2025-07-15T06:00 | 2025-07-15T18:00 | 0 | 4FS+24eh |  | 0 | 0.0h | TRUE | TRUE | FALSE |  | 4
10 | 1.2.1.2 | COLOCAR BC RX RG | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-15T06:00 | 2025-07-16T18:00 | 0 | 9SS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 4
11 | 1.2.1.3 | D-672 REGENERADOR | 24.483333333333334d | 587.6 | 864.0h | 864 | Nativo (factor 1.5x) | 2025-07-15T06:00 | 2025-08-08T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
12 | 1.2.1.3.1 | RETIRAR ESPARRAGO POR MEDIO PH PLENUM | 6.0eh | 6 | 587.6h | 587.6 | Nativo (factor 97.9x) | 2025-07-15T06:00 | 2025-07-15T12:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
13 | 1.2.1.3.2 | RETIRAR ESPARRAGO POR MEDIO PH CICLONES Y STRIPPER | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-15T06:00 | 2025-07-15T12:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
14 | 5 | RETIRAR 4x1 ESPARRAGOS PH 96" | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-15T06:00 | 2025-07-15T18:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
15 | 1.2.1.3.4 | RETIRAR ESPARRAGO POR MEDIO PH BAJO GRILLA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-15T06:00 | 2025-07-15T18:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
16 | 1.2.1.3.5 | PLENUM | 19.65277777777778d | 471.6667 | 288.0h | 288 | Nativo (factor 0.6x) | 2025-07-16T18:00 | 2025-08-05T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
17 | 1.2.1.3.5.1 | APERTURA DE PH | 4.0eh | 4 | 471.7h | 471.6667 | Nativo (factor 117.9x) | 2025-07-16T18:00 | 2025-07-16T22:00 | 0 | 12FS; 110FS; 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
18 | 1.2.1.3.5.2 | ROTURA DE TAPONES DE PH | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-16T22:00 | 2025-07-17T04:00 | 0 | 17FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
19 | 1.2.1.3.5.3 | VENTILACION | 18.0eh | 18 | 144.0h | 144 | Nativo (factor 8.0x) | 2025-07-17T04:00 | 2025-07-17T22:00 | 0 | 18FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
20 | 1.2.1.3.5.4 | MONTAR ACCESO E ILUMINACIÓN | 4.0eh | 4 | 432.0h | 432 | Nativo (factor 108.0x) | 2025-07-17T22:00 | 2025-07-18T02:00 | 0 | 19FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
21 | 1.2.1.3.5.5 | MONTAR ACCESO A MANGA | 10.0eh | 10 | 96.0h | 96 | Nativo (factor 9.6x) | 2025-07-18T02:00 | 2025-07-18T12:00 | 0 | 20FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
22 | 1.2.1.3.5.6 | INSPECCION VEE/PROCESOS | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T12:00 | 2025-07-18T20:00 | 0 | 21FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
23 | 1.2.1.3.5.7 | REPARAR REFRACTARIO PLENUM | 17.570833333333333d | 421.7 | 192.0h | 192 | Nativo (factor 0.5x) | 2025-07-18T20:00 | 2025-08-05T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | REFRACTARIO PLENUM: PAREDES CON DOBLE CAPA Y TECHO CON 2125 CONTEMPLA REPARACIONES EN MANGA HACIA C-671/672 | 6
24 | 1.2.1.3.5.7.1 | ROTURA Y CORTE DE MALLA | 36.0eh | 36 | 421.7h | 421.7 | Nativo (factor 11.7x) | 2025-07-18T20:00 | 2025-07-20T08:00 | 0 | 22FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
25 | 1.2.1.3.5.7.2 | DEMOLER ANTIEROSIVO Y AISLANTE | 18.0eh | 18 | 864.0h | 864 | Nativo (factor 48.0x) | 2025-07-20T08:00 | 2025-07-21T02:00 | 0 | 24FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
26 | 1.2.1.3.5.7.3 | LIMPIEZA Y SOLDADURA DE ANCLAJES/STUD BOLT | 24.0eh | 24 | 432.0h | 432 | Nativo (factor 18.0x) | 2025-07-21T02:00 | 2025-07-22T02:00 | 0 | 25FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
27 | 1.2.1.3.5.7.4 | GUNITAR ANTIEROSIVO F 2125 | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-07-22T02:00 | 2025-07-22T08:00 | 0 | 26FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
28 | 1.2.1.3.5.7.5 | GUNITAR REFRACTARIO AISLANTE | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-22T08:00 | 2025-07-22T14:00 | 0 | 27FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
29 | 1.2.1.3.5.7.6 | PRESENTAR Y SOLDAR MALLA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-22T14:00 | 2025-07-23T14:00 | 0 | 28FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
30 | 1.2.1.3.5.7.7 | APLICAR ANTIEROSIVO F 12L | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-23T14:00 | 2025-07-24T08:00 | 0 | 29FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
31 | 1.2.1.3.5.7.8 | INSPECCIÓN VEE/CAUSEWAY | 4.0eh | 4 | 432.0h | 432 | Nativo (factor 108.0x) | 2025-07-24T08:00 | 2025-07-24T12:00 | 0 | 30FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
32 | 1.2.1.3.5.7.9 | LIMPIEZA | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-24T12:00 | 2025-07-24T18:00 | 0 | 31FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
33 | 1.2.1.3.5.7.10 | RECEPCIÓN OPERACIONES/PROCESOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-24T18:00 | 2025-07-25T00:00 | 0 | 32FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
34 | 1.2.1.3.5.7.11 | RETIRAR ACCESO | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-25T00:00 | 2025-07-25T06:00 | 0 | 33FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
35 | 1.2.1.3.5.7.12 | TAPAR PH | 16.0eh | 16 | 144.0h | 144 | Nativo (factor 9.0x) | 2025-08-04T18:00 | 2025-08-05T10:00 | 0 | 73FS; 34FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
36 | 1.2.1.3.5.8 | REPARAR CICLONES SECUNDARIOS 4 | 17.570833333333333d | 421.7 | 17.570833333333333d | 421.7 | MPXJ (validado) | 2025-07-18T20:00 | 2025-08-05T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | REPARACIONES EN CICLONES DESDE PLANUM | 6
37 | 1.2.1.3.5.8.1 | ROTURA Y CORTE DE MALLA | 36.0eh | 36 | 421.7h | 421.7 | Nativo (factor 11.7x) | 2025-07-18T20:00 | 2025-07-20T08:00 | 0 | 22FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
38 | 1.2.1.3.5.8.2 | LIMPIEZA DE SUPERFICIE | 48.0eh | 48 | 864.0h | 864 | Nativo (factor 18.0x) | 2025-07-20T08:00 | 2025-07-22T08:00 | 0 | 37FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
39 | 1.2.1.3.5.8.3 | PRESENTAR Y SOLDAR MALLA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-22T14:00 | 2025-07-23T14:00 | 0 | 28FS; 38FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
40 | 1.2.1.3.5.8.4 | APLICAR ANTIEROSIVO F 12L | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-23T14:00 | 2025-07-24T08:00 | 0 | 39FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
41 | 1.2.1.3.5.8.5 | INSPECCIÓN VEE/CAUSEWAY | 4.0eh | 4 | 432.0h | 432 | Nativo (factor 108.0x) | 2025-07-24T08:00 | 2025-07-24T12:00 | 0 | 40FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
42 | 1.2.1.3.5.8.6 | LIMPIEZA | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-24T12:00 | 2025-07-24T18:00 | 0 | 41FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
43 | 1.2.1.3.5.8.7 | RECEPCIÓN OPERACIONES/PROCESOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-24T18:00 | 2025-07-25T00:00 | 0 | 42FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
44 | 1.2.1.3.5.8.8 | RETIRAR ACCESO | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-25T00:00 | 2025-07-25T06:00 | 0 | 43FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
45 | 1.2.1.3.5.8.9 | TAPAR PH | 16.0eh | 16 | 144.0h | 144 | Nativo (factor 9.0x) | 2025-08-04T18:00 | 2025-08-05T10:00 | 0 | 44FS; 73FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
46 | 1.2.1.3.6 | ENVOLVENTE RG (96") | 22.98402777777778d | 551.6167 | 384.0h | 384 | Nativo (factor 0.7x) | 2025-07-16T18:00 | 2025-08-08T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
47 | 1.2.1.3.6.1 | APERTURA PHs 96" y 24" | 12.0eh | 12 | 551.6h | 551.6167 | Nativo (factor 46.0x) | 2025-07-16T18:00 | 2025-07-17T06:00 | 0 | 14FS; 13FS; 111FS; 112FS; 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
48 | 1.2.1.3.6.2 | VENTILACION | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-17T06:00 | 2025-07-18T06:00 | 0 | 47FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
49 | 1.2.1.3.6.3 | MONTAR ACCESO PH96 | 10.0eh | 10 | 576.0h | 576 | Nativo (factor 57.6x) | 2025-07-18T06:00 | 2025-07-18T16:00 | 0 | 48FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
50 | 1.2.1.3.6.4 | RETIRAR CATALIZADOR GRILLA | 26.0eh | 26 | 240.0h | 240 | Nativo (factor 9.2x) | 2025-07-18T16:00 | 2025-07-19T18:00 | 0 | 49FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
51 | 1.2.1.3.6.5 | PRIMERA INSPECCIÓN PROCESOS/INSPECCIÓN | 4.0eh | 4 | 624.0h | 624 | Nativo (factor 156.0x) | 2025-07-18T16:00 | 2025-07-18T20:00 | 0 | 49FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
52 | 1.2.1.3.6.6 | TAPAR GRILLA SELLO HACIA ABAJO GRILLA | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-18T20:00 | 2025-07-19T02:00 | 0 | 51FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
53 | 1.2.1.3.6.7 | MONTAR ANDAMIO COMPLETO E ILUMINACIÓN | 30.0eh | 30 | 144.0h | 144 | Nativo (factor 4.8x) | 2025-07-19T18:00 | 2025-07-21T00:00 | 0 | 50FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | Andamio completo en envolvente para inspeccion | 6
54 | 1.2.1.3.6.8 | INSPECCION DE REFRACTARIO | 12.0eh | 12 | 720.0h | 720 | Nativo (factor 60.0x) | 2025-07-21T00:00 | 2025-07-21T12:00 | 0 | 53FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
55 | 1.2.1.3.6.9 | MODIFICAR ANDAMIO Y COLOCAR "SELLO" | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-21T12:00 | 2025-07-21T20:00 | 0 | 54FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
56 | 1.2.1.3.6.10 | DEMOLER DEFRACTARIO (20m2) | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-21T20:00 | 2025-07-23T08:00 | 0 | 55FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | estimacion 10m2 por cada frente de demolicion | 6
57 | 1.2.1.3.6.11 | SOLDAR ANCLAJES | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-23T08:00 | 2025-07-24T08:00 | 0 | 56FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
58 | 1.2.1.3.6.12 | GUNITAR REFRACTARIO AISLANTE | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-24T08:00 | 2025-07-25T20:00 | 0 | 57FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | se estima por frente colocar 14 m2. en 2010 se realizo virolar de 1,3mts de alturax 22mts de perimetro, en 15 hs inclutendo la limpieza, con dos maquinas. | 6
59 | 1.2.1.3.6.13 | CAMBIO DE SPARGER | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-25T20:00 | 2025-07-26T20:00 | 0 | 58FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
60 | 1.2.1.3.6.14 | CAMBIO DE COMPUERTAS (8) | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-25T20:00 | 2025-07-27T20:00 | 0 | 58FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
61 | 1.2.1.3.6.15 | ENVOLVENTE SUPERIOR/CICLONES PRIMARIOS 4 | 16.072222222222223d | 385.7333 | 1152.0h | 1152 | Nativo (factor 3.0x) | 2025-07-21T00:00 | 2025-08-06T02:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
62 | 1.2.1.3.6.15.1 | ARMAR ANDAMIO EN CICLONES PRIMARIOS | 24.0eh | 24 | 385.7h | 385.7333 | Nativo (factor 16.1x) | 2025-07-21T00:00 | 2025-07-22T00:00 | 0 | 53FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
63 | 1.2.1.3.6.15.2 | INSPECCION CICLONES INTERNO/EXTERNO | 38.0eh | 38 | 576.0h | 576 | Nativo (factor 15.2x) | 2025-07-22T00:00 | 2025-07-23T14:00 | 0 | 62FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
64 | 1.2.1.3.6.15.3 | DESMONTAJE DE BOCINAS (4) | 30.0eh | 30 | 912.0h | 912 | Nativo (factor 30.4x) | 2025-07-23T14:00 | 2025-07-24T20:00 | 0 | 63FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
65 | 1.2.1.3.6.15.4 | DESMONTAR ESCUDOS (8) | 36.0eh | 36 | 720.0h | 720 | Nativo (corregido) | 2025-07-21T00:00 | 2025-07-22T12:00 | 0 | 53FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
66 | 1.2.1.3.6.15.5 | MONTAR BOCINAS-SOLD.-REFRACTA | 70.0eh | 70 | 864.0h | 864 | Nativo (factor 12.3x) | 2025-07-24T20:00 | 2025-07-27T18:00 | 0 | 64FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
67 | 1.2.1.3.6.15.6 | MONTAR ESCUDOS | 48.0eh | 48 | 1680.0h | 1680 | Nativo (factor 35.0x) | 2025-07-25T20:00 | 2025-07-27T20:00 | 0 | 66SS+24eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
68 | 1.2.1.3.6.15.7 | CEPILLAR COSTURAS DE SOPORTERIA | 70.0eh | 70 | 1152.0h | 1152 | Nativo (factor 16.5x) | 2025-07-21T00:00 | 2025-07-23T22:00 | 0 | 53FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
69 | 1.2.1.3.6.15.8 | REPARACION DE SOPORTERIA | 60.0eh | 60 | 1680.0h | 1680 | Nativo (corregido) | 2025-07-23T22:00 | 2025-07-26T10:00 | 0 | 68FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
70 | 1.2.1.3.6.15.9 | DEMOLER DEFRACTARIO (20m2) | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-21T20:00 | 2025-07-23T08:00 | 0 | 55FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | SE ESTIMAN 7 M2 POR TURNO | 7
71 | 1.2.1.3.6.15.10 | SOLDAR ANCLAJES | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-23T08:00 | 2025-07-24T08:00 | 0 | 70FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
72 | 1.2.1.3.6.15.11 | GUNITAR REFRACTARIO AISLANTE | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-24T08:00 | 2025-07-25T20:00 | 0 | 71FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
73 | 1.2.1.3.6.15.12 | REPARACION INTERNA DE CICLONES | 192.0eh | 192 | 864.0h | 864 | Nativo (factor 4.5x) | 2025-07-27T18:00 | 2025-08-04T18:00 | 0 | 66FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
74 | 1.2.1.3.6.15.13 | INSPECCION VEE Y PROCESOS | 12.0eh | 12 | 4608.0h | 4608 | Nativo (factor 384.0x) | 2025-08-04T18:00 | 2025-08-05T06:00 | 0 | 73FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
75 | 1.2.1.3.6.15.14 | DESMONTAR ACCESOS A CICLONES | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-05T06:00 | 2025-08-05T14:00 | 0 | 74FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
76 | 1.2.1.3.6.15.15 | LIMPIEZA INSPECCION ENVOLVENTE Y SOPORTERÍA | 18.0eh | 18 | 192.0h | 192 | Nativo (factor 10.7x) | 2025-07-25T20:00 | 2025-07-26T14:00 | 0 | 72FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
77 | 1.2.1.3.6.15.16 | DESMONTAR ANDAMIO Y SELLO HASTA STAND PIPE | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-08-05T14:00 | 2025-08-06T02:00 | 0 | 75FS; 76FS; 74FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
78 | 1.2.1.3.6.16 | RECEPCIÓN PROCESOS OPERACIONES STAND PIPE Y VÁLVULAS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-06T02:00 | 2025-08-06T06:00 | 0 | 77FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
79 | 1.2.1.3.6.17 | BAJAR ANDAMIO | 14.0eh | 14 | 96.0h | 96 | Nativo (factor 6.9x) | 2025-08-06T06:00 | 2025-08-06T20:00 | 0 | 78FS; 60FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
80 | 1.2.1.3.6.18 | CALAFATEAR CONTORNO DE GRILLA | 12.0eh | 12 | 336.0h | 336 | Nativo (corregido) | 2025-08-06T20:00 | 2025-08-07T08:00 | 0 | 79FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | SE DEBERÁ TENER CHAPA PARA CAJON | 6
81 | 1.2.1.3.6.19 | LIMPIEZA FINAL DE GRILLA RETIRO DE ACCESO | 14.0eh | 14 | 288.0h | 288 | Nativo (corregido) | 2025-08-07T08:00 | 2025-08-07T22:00 | 0 | 80FS; 79FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
82 | 1.2.1.3.6.20 | CERRAR PH 96" RG | 20.0eh | 20 | 336.0h | 336 | Nativo (factor 16.8x) | 2025-08-07T22:00 | 2025-08-08T18:00 | 0 | 81FS; 59FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
83 | 1.2.1.3.6.21 | BAJO GRILLA | 14.989583333333334d | 359.75 | 480.0h | 480 | Nativo (factor 1.3x) | 2025-07-16T18:00 | 2025-07-31T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
84 | 1.2.1.3.6.21.1 | ABRIR PH | 2.0d | 48 | 359.8h | 359.75 | Nativo (factor 7.5x) | 2025-07-16T18:00 | 2025-07-18T18:02 | 0 | 10FS; 15FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
85 | 1.2.1.3.6.21.2 | DESMONTAR QUEMADOR | 16.0eh | 16 | 48.0h | 48 | Nativo (factor 3.0x) | 2025-07-16T18:00 | 2025-07-17T10:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
86 | 1.2.1.3.6.21.3 | REALIZAR LIMPIEZA BAJO GRILLA | 36.0eh | 36 | 384.0h | 384 | Nativo (factor 10.7x) | 2025-07-19T18:00 | 2025-07-21T06:00 | 0 | 84FS; 50FS; 52FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
87 | 1.2.1.3.6.21.4 | INSPECCION | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-21T06:00 | 2025-07-21T18:00 | 0 | 86FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
88 | 1.2.1.3.6.21.5 | REPARAR QUEMADOR | 72.0eh | 72 | 288.0h | 288 | Nativo (factor 4.0x) | 2025-07-17T10:00 | 2025-07-20T10:00 | 0 | 85FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
89 | 1.2.1.3.6.21.6 | ROTURA DE REFRACTARIO | 60.0eh | 60 | 1728.0h | 1728 | Nativo (factor 28.8x) | 2025-07-21T18:00 | 2025-07-24T06:00 | 0 | 87FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
90 | 1.2.1.3.6.21.7 | CAMBIO DE LADRILLOS | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-24T06:00 | 2025-07-25T06:00 | 0 | 89FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
91 | 1.2.1.3.6.21.8 | SOLDADURA DE ANCLAJES | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-24T06:00 | 2025-07-25T18:00 | 0 | 89FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
92 | 1.2.1.3.6.21.9 | LIMPIEZA Y CEPILLADO DE COSTURAS | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-25T18:00 | 2025-07-26T18:00 | 0 | 91FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
93 | 1.2.1.3.6.21.10 | INSPECCION Y END | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-26T18:00 | 2025-07-27T06:00 | 0 | 92FS; 90FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
94 | 1.2.1.3.6.21.11 | REPARACION DE SOPORTES Y ESCUDO | 60.0eh | 60 | 288.0h | 288 | Nativo (factor 4.8x) | 2025-07-27T06:00 | 2025-07-29T18:00 | 0 | 93FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
95 | 1.2.1.3.6.21.12 | GUNITADO REFRACTARIO | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-29T18:00 | 2025-07-31T06:00 | 0 | 94FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
96 | 1.2.1.3.6.21.13 | INSPECCIÓN PROCESOS y VEE | 4.0eh | 4 | 864.0h | 864 | Nativo (factor 216.0x) | 2025-07-31T06:00 | 2025-07-31T10:00 | 0 | 94FS; 95FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
97 | 1.2.1.3.6.21.14 | MONTAR QUEMADOR | 8.0eh | 8 | 96.0h | 96 | Nativo (factor 12.0x) | 2025-07-31T10:00 | 2025-07-31T18:00 | 0 | 88FS; 96FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
98 | 1.2.1.3.6.21.15 | CERRAR PH | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-31T10:00 | 2025-07-31T18:00 | 0 | 96FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
99 | 1.2.1.3.6.22 | STAND PIPE | 6.579166666666667d | 157.9 | 192.0h | 192 | Nativo (factor 1.2x) | 2025-07-21T00:00 | 2025-07-27T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
100 | 1.2.1.3.6.22.1 | MONTAR AND. STAND PIPE | 12.0eh | 12 | 157.9h | 157.9 | Nativo (factor 13.2x) | 2025-07-21T00:00 | 2025-07-21T12:00 | 0 | 53FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
101 | 1.2.1.3.6.22.2 | INSPECCION | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-21T12:00 | 2025-07-21T16:00 | 0 | 100FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
102 | 1.2.1.3.6.22.3 | ROTURA REFRACTARIO | 40.0eh | 40 | 96.0h | 96 | Nativo (factor 2.4x) | 2025-07-21T16:00 | 2025-07-23T08:00 | 0 | 101FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
103 | 1.2.1.3.6.22.4 | REPELADO ANCLAJES | 30.0eh | 30 | 960.0h | 960 | Nativo (factor 32.0x) | 2025-07-23T08:00 | 2025-07-24T14:00 | 0 | 102FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
104 | 1.2.1.3.6.22.5 | SOLDADURA ANCLAJES | 24.0eh | 24 | 720.0h | 720 | Nativo (factor 30.0x) | 2025-07-24T14:00 | 2025-07-25T14:00 | 0 | 103FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
105 | 1.2.1.3.6.22.6 | HORMIGONADO | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-25T14:00 | 2025-07-26T14:00 | 0 | 104FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
106 | 1.2.1.3.6.22.7 | LIMPIEZA | 10.0eh | 10 | 576.0h | 576 | Nativo (factor 57.6x) | 2025-07-26T14:00 | 2025-07-27T00:00 | 0 | 105FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
107 | 1.2.1.3.6.22.8 | INSPECCION | 4.0eh | 4 | 240.0h | 240 | Nativo (factor 60.0x) | 2025-07-27T00:00 | 2025-07-27T04:00 | 0 | 106FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
108 | 1.2.1.3.6.22.9 | DESMONTAR ANDAMIO | 10.0eh | 10 | 96.0h | 96 | Nativo (factor 9.6x) | 2025-07-27T04:00 | 2025-07-27T14:00 | 0 | 107FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
109 | 1.2.1.4 | D-671 REACTOR | 26.774305555555557d | 642.5833 | 240.0h | 240 | Nativo (factor 0.4x) | 2025-07-15T06:00 | 2025-08-11T01:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 4
110 | 1.2.1.4.1 | RETIRAR ESPARRAGO POR MEDIO PH PLENUM | 6.0eh | 6 | 642.6h | 642.5833 | Nativo (factor 107.1x) | 2025-07-15T06:00 | 2025-07-15T12:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
111 | 1.2.1.4.2 | RETIRAR ESPARRAGO POR MEDIO PH CICLONES | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-15T06:00 | 2025-07-15T12:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
112 | 5 | RETIRAR 4x1 ESPARRAGOS PH 96" | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-15T06:00 | 2025-07-15T18:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
113 | 1.2.1.4.4 | ENVOLVENTE | 25.275d | 606.6 | 288.0h | 288 | Nativo (factor 0.5x) | 2025-07-16T18:00 | 2025-08-11T01:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 5
114 | 1.2.1.4.4.1 | ABRIR PH 96" | 12.0eh | 12 | 606.6h | 606.6 | Nativo (factor 50.6x) | 2025-07-16T18:00 | 2025-07-17T06:00 | 0 | 112FS; 9FS; 10FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
115 | 1.2.1.4.4.2 | ABRIR PH 24 | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-16T18:00 | 2025-07-17T00:00 | 0 | 111FS; 9FS; 10FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
116 | 1.2.1.4.4.3 | DEMOLER TAPÓN PH 24 | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-17T00:00 | 2025-07-17T06:00 | 0 | 115FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
117 | 1.2.1.4.4.4 | VENTILACION | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-17T06:00 | 2025-07-18T06:00 | 0 | 116FS; 114FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
118 | 1.2.1.4.4.5 | ARMAR ACCESO | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-18T06:00 | 2025-07-18T14:00 | 0 | 117FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
119 | 1.2.1.4.4.6 | INSPECCIÓN PROCESOS | 4.0eh | 4 | 192.0h | 192 | Nativo (factor 48.0x) | 2025-07-18T14:00 | 2025-07-18T18:00 | 0 | 118FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
120 | 1.2.1.4.4.7 | COLOCAR SELLO CONTRA STRIPPER | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-18T18:00 | 2025-07-19T00:00 | 0 | 119FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
121 | 1.2.1.4.4.8 | ARMAR ANDAMIO E ILUMINACIÓN | 30.0eh | 30 | 144.0h | 144 | Nativo (factor 4.8x) | 2025-07-19T00:00 | 2025-07-20T06:00 | 0 | 120FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
122 | 1.2.1.4.4.9 | RETIRO DE CARBON | 60.0eh | 60 | 720.0h | 720 | Nativo (factor 12.0x) | 2025-07-20T06:00 | 2025-07-22T18:00 | 0 | 121FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
123 | 1.2.1.4.4.10 | MODIFICAR ANDAMIO Y LIMPIEZA | 12.0eh | 12 | 1440.0h | 1440 | Nativo (factor 120.0x) | 2025-07-22T18:00 | 2025-07-23T06:00 | 0 | 122FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
124 | 1.2.1.4.4.11 | INSPECCION | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-23T06:00 | 2025-07-24T06:00 | 0 | 123FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
125 | 1.2.1.4.4.12 | DEMOLER REFRACTARIO (20M2) | 60.0eh | 60 | 576.0h | 576 | Nativo (factor 9.6x) | 2025-07-24T06:00 | 2025-07-26T18:00 | 0 | 124FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | se estiman retirar 6m2 de refractario x turno con 2 frentes | 6
126 | 1.2.1.4.4.13 | LIMPIEZA DE CHAPA ENVOLVENTE | 34.0eh | 34 | 1440.0h | 1440 | Nativo (factor 42.4x) | 2025-07-26T18:00 | 2025-07-28T04:00 | 0 | 125FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
127 | 1.2.1.4.4.14 | SOLDAR ANCLAJES | 24.0eh | 24 | 816.0h | 816 | Nativo (factor 34.0x) | 2025-07-28T04:00 | 2025-07-29T04:00 | 0 | 126FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
128 | 1.2.1.4.4.15 | PROYECTAR HORMIGON | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-08-01T04:00 | 2025-08-03T04:00 | 0 | 127FS; 131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
129 | 1.2.1.4.4.16 | REVISION Y DESTAPADO DE TOMAS Y CAMBIO DE VÁLVULAS | 90.0eh | 90 | 1152.0h | 1152 | Nativo (factor 12.8x) | 2025-07-28T04:00 | 2025-07-31T22:00 | 0 | 126FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
130 | 1.2.1.4.4.17 | CEPILLAR COSTURAS DE SOPORTERIA | 70.0eh | 70 | 2160.0h | 2160 | Nativo (factor 30.9x) | 2025-07-26T18:00 | 2025-07-29T16:00 | 0 | 125FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
131 | 1.2.1.4.4.18 | REPARACION DE SOPORTERIA | 60.0eh | 60 | 1680.0h | 1680 | Nativo (corregido) | 2025-07-29T16:00 | 2025-08-01T04:00 | 0 | 130FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
132 | 1.2.1.4.4.19 | INSPECCION | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-08-03T04:00 | 2025-08-04T16:00 | 0 | 128FS; 131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
133 | 1.2.1.4.4.20 | DESMONTAR ANDAMIO | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-08-06T05:02 | 2025-08-07T05:02 | 0 | 132FS; 171FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
134 | 1.2.1.4.4.21 | DESMONTAR SELLO | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-08-07T05:02 | 2025-08-07T11:02 | 0 | 133FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
135 | 1.2.1.4.4.22 | REPARACION DE REFRACTARIO ZONA DEL SELLO (CONO) | 60.0eh | 60 | 144.0h | 144 | Nativo (factor 2.4x) | 2025-08-07T11:02 | 2025-08-09T23:02 | 0 | 134FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
136 | 1.2.1.4.4.23 | INSPECCION FINAL | 6.0eh | 6 | 1440.0h | 1440 | Nativo (factor 240.0x) | 2025-08-09T23:02 | 2025-08-10T05:02 | 0 | 135FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
137 | 1.2.1.4.4.24 | CIERRE DE PH 96 | 20.0eh | 20 | 144.0h | 144 | Nativo (factor 7.2x) | 2025-08-10T05:02 | 2025-08-11T01:02 | 0 | 136FS; 152FS; 129FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
138 | 1.2.1.4.5 | STRIPPER D671 | 25.275d | 606.6 | 480.0h | 480 | Nativo (factor 0.8x) | 2025-07-16T18:00 | 2025-08-11T01:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 5
139 | 1.2.1.4.5.1 | ABRIR PHs (2) | 6.0eh | 6 | 606.6h | 606.6 | Nativo (factor 101.1x) | 2025-07-16T18:00 | 2025-07-17T00:00 | 0 | 13FS; 9FS; 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
140 | 1.2.1.4.5.2 | DEMOLER PHs (2) | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-17T00:00 | 2025-07-17T12:00 | 0 | 139FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
141 | 1.2.1.4.5.3 | INGRESO E INSPECCIÓN INICIAL | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-17T12:00 | 2025-07-17T20:00 | 0 | 140FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
142 | 1.2.1.4.5.4 | DESMONTAR FILTRO CORPIÑO | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-17T20:00 | 2025-07-18T04:00 | 0 | 141FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
143 | 1.2.1.4.5.5 | DESMONTAJE DE TEJAS (4) | 24.0eh | 24 | 192.0h | 192 | Nativo (factor 8.0x) | 2025-07-18T04:00 | 2025-07-19T04:00 | 0 | 142FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
144 | 1.2.1.4.5.6 | CEPILLADO PARA END DE SOPORTES | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-19T04:00 | 2025-07-20T04:00 | 0 | 143FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
145 | 1.2.1.4.5.7 | REPARACIÓN DE SOPORTES Y TRUÑON | 30.0eh | 30 | 576.0h | 576 | Nativo (factor 19.2x) | 2025-07-20T04:00 | 2025-07-21T10:00 | 0 | 144FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
146 | 1.2.1.4.5.8 | DEMOLER REFRACTARIO | 24.0eh | 24 | 720.0h | 720 | Nativo (factor 30.0x) | 2025-07-21T10:00 | 2025-07-22T10:00 | 0 | 145FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
147 | 1.2.1.4.5.9 | LIMPIEZA DE SUPERFICIE Y SOLDADURA DE ANCLAJES | 16.0eh | 16 | 576.0h | 576 | Nativo (factor 36.0x) | 2025-07-22T10:00 | 2025-07-23T02:00 | 0 | 146FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
148 | 1.2.1.4.5.10 | GUNITAR AISLANTE | 16.0eh | 16 | 384.0h | 384 | Nativo (corregido) | 2025-07-23T02:00 | 2025-07-23T18:00 | 0 | 147FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
149 | 1.2.1.4.5.11 | CAMBIO DE DISTRIBUIDORES DE VAPOR | 36.0eh | 36 | 384.0h | 384 | Nativo (factor 10.7x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 148FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
150 | 1.2.1.4.5.12 | MONTAJE DE TEJAS | 20.0eh | 20 | 864.0h | 864 | Nativo (factor 43.2x) | 2025-07-25T06:00 | 2025-07-26T02:00 | 0 | 149FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
151 | 1.2.1.4.5.13 | MONTAJE DE FILTRO | 10.0eh | 10 | 480.0h | 480 | Nativo (factor 48.0x) | 2025-07-26T02:00 | 2025-07-26T12:00 | 0 | 150FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
152 | 1.2.1.4.5.14 | LIMPIEZA E INSPECCIÓN FINAL | 12.0eh | 12 | 240.0h | 240 | Nativo (corregido) | 2025-07-26T12:00 | 2025-07-27T00:00 | 0 | 151FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
153 | 1.2.1.4.5.15 | PROYECTAR HORMIGON EN PHs | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-10T05:02 | 2025-08-10T13:02 | 0 | 152FS; 137SS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
154 | 1.2.1.4.5.16 | CERRRAR PHs (2) | 12.0eh | 12 | 192.0h | 192 | Nativo (factor 16.0x) | 2025-08-10T13:02 | 2025-08-11T01:02 | 0 | 153FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
155 | 1.2.1.4.6 | RISER EXTERNO - INTERNO | 21.111805555555556d | 506.6833 | 288.0h | 288 | Nativo (factor 0.6x) | 2025-07-16T18:00 | 2025-08-06T21:02 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
156 | 1.2.1.4.6.1 | ABRIR Y DEMOLER PHs (2) | 12.0eh | 12 | 506.7h | 506.6833 | Nativo (factor 42.2x) | 2025-07-16T18:00 | 2025-07-17T06:00 | 0 | 9FS; 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
157 | 1.2.1.4.6.2 | RETIRAR TAPA SUPERIOR | 12.0h | 0 | 288.0h | 288 | Nativo (MPXJ=0) | 2025-07-20T06:00 | 2025-07-20T18:00 | 0 | 156FS; 121FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
158 | 1.2.1.4.6.3 | VENTILACION | 6.0eh | 6 | 12.0h | 12 | Nativo (factor 2.0x) | 2025-07-20T18:00 | 2025-07-21T00:00 | 0 | 157FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
159 | 1.2.1.4.6.4 | ARMAR ACCESO | 48.0h | 0 | 144.0h | 144 | Nativo (MPXJ=0) | 2025-07-21T00:00 | 2025-07-23T00:02 | 0 | 158FS |  | 0 | 0.0h | TRUE | FALSE | FALSE | DESDE TOBERAS DE CARGA HASTA CAP RISER | 6
160 | 1.2.1.4.6.5 | LIMPIEZA | 24.0eh | 24 | 48.0h | 48 | Nativo (factor 2.0x) | 2025-07-23T00:02 | 2025-07-24T00:02 | 0 | 159FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
161 | 1.2.1.4.6.6 | DETAPAR TOMAS | 80.0eh | 80 | 576.0h | 576 | Nativo (factor 7.2x) | 2025-07-21T00:00 | 2025-07-24T08:00 | 0 | 158FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
162 | 1.2.1.4.6.7 | INSPECCION | 18.0eh | 18 | 1920.0h | 1920 | Nativo (factor 106.7x) | 2025-07-24T00:02 | 2025-07-24T18:02 | 0 | 160FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
163 | 1.2.1.4.6.8 | RAPARACIÓN DE MALLA EXTERNA | 36.0eh | 36 | 432.0h | 432 | Nativo (factor 12.0x) | 2025-07-24T18:02 | 2025-07-26T06:02 | 0 | 162FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
164 | 1.2.1.4.6.9 | RAPARACIÓN DE MALLA INTERNA | 35.0eh | 35 | 864.0h | 864 | Nativo (corregido) | 2025-07-25T18:02 | 2025-07-27T05:02 | 0 | 163SS+24eh |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
165 | 1.2.1.4.6.10 | REPARACION DE REFRACTARIO | 90.0eh | 90 | 840.0h | 840 | Nativo (factor 9.3x) | 2025-07-27T05:02 | 2025-07-30T23:02 | 0 | 164FS; 163FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
166 | 1.2.1.4.6.11 | INSPECCION | 14.0eh | 14 | 2160.0h | 2160 | Nativo (factor 154.3x) | 2025-07-30T23:02 | 2025-07-31T13:02 | 0 | 161FS; 165FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
167 | 1.2.1.4.6.12 | DESMONTAR ACCESO | 36.0eh | 36 | 336.0h | 336 | Nativo (factor 9.3x) | 2025-07-31T13:02 | 2025-08-02T01:02 | 0 | 166FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
168 | 1.2.1.4.6.13 | REPARACION REFRACTARIO TOBERAS | 60.0eh | 60 | 864.0h | 864 | Nativo (factor 14.4x) | 2025-08-02T01:02 | 2025-08-04T13:02 | 0 | 167FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
169 | 1.2.1.4.6.14 | RECEPCIÓN PROCESOS/OPERACIONES | 4.0eh | 4 | 1440.0h | 1440 | Nativo (factor 360.0x) | 2025-08-04T13:02 | 2025-08-04T17:02 | 0 | 168FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
170 | 1.2.1.4.6.15 | PROYECTAR HORMIGON EN PHs | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-08-04T17:02 | 2025-08-05T17:02 | 0 | 169FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
171 | 1.2.1.4.6.16 | CERRAR TAPA SUPERIOR | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-08-05T17:02 | 2025-08-06T05:02 | 0 | 170FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 6
172 | 1.2.1.4.6.17 | CERRRAR PHs (2) | 16.0eh | 16 | 288.0h | 288 | Nativo (factor 18.0x) | 2025-08-06T05:02 | 2025-08-06T21:02 | 0 | 171FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
173 | 1.2.1.4.7 | PLENUM Y CICLONES | 18.070833333333333d | 433.7 | 18.070833333333333d | 433.7 | MPXJ (validado) | 2025-07-18T06:00 | 2025-08-05T08:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
174 | 1.2.1.4.7.1 | COLOCAR ACCESO | 8.0eh | 8 | 433.7h | 433.7 | Nativo (factor 54.2x) | 2025-07-18T06:00 | 2025-07-18T14:00 | 0 | 117FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
175 | 1.2.1.4.7.2 | REALIZAR LIMPIEZA | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-18T14:00 | 2025-07-20T02:00 | 0 | 174FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
176 | 1.2.1.4.7.3 | INSPECCION | 10.0eh | 10 | 864.0h | 864 | Nativo (factor 86.4x) | 2025-07-20T02:00 | 2025-07-20T12:00 | 0 | 175FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
177 | 1.2.1.4.7.4 | REPARACION DE REFRACTARIO | 90.0eh | 90 | 240.0h | 240 | Nativo (factor 2.7x) | 2025-07-20T12:00 | 2025-07-24T06:00 | 0 | 176FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
178 | 1.2.1.4.7.5 | LIMPIEZA E INSPECCION | 24.0eh | 24 | 2160.0h | 2160 | Nativo (factor 90.0x) | 2025-08-02T10:00 | 2025-08-03T10:00 | 0 | 177FS; 190FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
179 | 1.2.1.4.7.6 | RETIRO DE ACCESO | 10.0eh | 10 | 576.0h | 576 | Nativo (factor 57.6x) | 2025-08-03T10:00 | 2025-08-03T20:00 | 0 | 178FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
180 | 1.2.1.4.7.7 | TAPAR PH | 36.0eh | 36 | 240.0h | 240 | Nativo (factor 6.7x) | 2025-08-03T20:00 | 2025-08-05T08:00 | 0 | 179FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
181 | 1.2.1.4.7.8 | CICLONES PRIMARIOS | 13.324305555555556d | 319.7833 | 864.0h | 864 | Nativo (factor 2.7x) | 2025-07-20T02:00 | 2025-08-02T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
182 | 1.2.1.4.7.8.1 | RETIRO DE TAPAS SOLDADAS | 12.0eh | 12 | 319.8h | 319.7833 | Nativo (corregido) | 2025-07-20T02:00 | 2025-07-20T14:00 | 0 | 175FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
183 | 1.2.1.4.7.8.2 | ARMAR ACCESOS | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-20T14:00 | 2025-07-21T14:00 | 0 | 182FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
184 | 1.2.1.4.7.8.3 | LIMPIEZA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-21T14:00 | 2025-07-22T14:00 | 0 | 183FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
185 | 1.2.1.4.7.8.4 | INSPECCION | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T14:00 | 2025-07-23T14:00 | 0 | 184FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
186 | 1.2.1.4.7.8.5 | REPARACIONES | 100.0eh | 100 | 576.0h | 576 | Nativo (factor 5.8x) | 2025-07-23T14:00 | 2025-07-27T18:00 | 0 | 185FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
187 | 1.2.1.4.7.8.6 | INSPECCION | 6.0eh | 6 | 2400.0h | 2400 | Nativo (factor 400.0x) | 2025-07-27T18:00 | 2025-07-28T00:00 | 0 | 186FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
188 | 1.2.1.4.7.8.7 | PROBAR PASAJE | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-28T00:00 | 2025-07-29T00:00 | 0 | 187FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
189 | 1.2.1.4.7.8.8 | RETIRO DE ACCESOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-29T22:00 | 2025-07-30T22:00 | 0 | 188FS; 198FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
190 | 1.2.1.4.7.8.9 | COLOCAR TAPAS Y SOLDAR | 60.0eh | 60 | 576.0h | 576 | Nativo (factor 9.6x) | 2025-07-30T22:00 | 2025-08-02T10:00 | 0 | 189FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
191 | 1.2.1.4.7.9 | CICLONES SECUNDARIOS | 8.327777777777778d | 199.8667 | 1440.0h | 1440 | Nativo (factor 7.2x) | 2025-07-21T14:00 | 2025-07-29T22:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
192 | 1.2.1.4.7.9.1 | ARMAR ACCESOS | 24.0eh | 24 | 199.9h | 199.8667 | Nativo (factor 8.3x) | 2025-07-21T14:00 | 2025-07-22T14:00 | 0 | 183FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
193 | 1.2.1.4.7.9.2 | LIMPIEZA | 16.0eh | 16 | 576.0h | 576 | Nativo (factor 36.0x) | 2025-07-22T14:00 | 2025-07-23T06:00 | 0 | 192FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
194 | 1.2.1.4.7.9.3 | INSPECCION | 12.0eh | 12 | 384.0h | 384 | Nativo (factor 32.0x) | 2025-07-23T06:00 | 2025-07-23T18:00 | 0 | 193FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
195 | 1.2.1.4.7.9.4 | REPARACIONES | 100.0eh | 100 | 288.0h | 288 | Nativo (factor 2.9x) | 2025-07-23T18:00 | 2025-07-27T22:00 | 0 | 194FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
196 | 1.2.1.4.7.9.5 | INSPECCION | 12.0eh | 12 | 2400.0h | 2400 | Nativo (factor 200.0x) | 2025-07-27T22:00 | 2025-07-28T10:00 | 0 | 195FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
197 | 1.2.1.4.7.9.6 | PROBAR PASAJE | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-28T10:00 | 2025-07-29T10:00 | 0 | 196FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
198 | 1.2.1.4.7.9.7 | RETIRO DE ACCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-29T10:00 | 2025-07-29T22:00 | 0 | 197FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
199 | 1.2.1.4.8 | HICV606 | 16.488194444444446d | 395.7167 | 288.0h | 288 | Nativo (factor 0.7x) | 2025-07-16T18:00 | 2025-08-02T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
200 | 1.2.1.4.8.1 | DESMONTAR MECANISMO | 8.0eh | 8 | 395.7h | 395.7167 | Nativo (factor 49.5x) | 2025-07-16T18:00 | 2025-07-17T02:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
201 | 1.2.1.4.8.2 | DESMONTAR BONETE | 30.0eh | 30 | 192.0h | 192 | Nativo (factor 6.4x) | 2025-07-17T02:00 | 2025-07-18T08:00 | 0 | 200FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | CORTAR FLEJE SOLDADO | 6
202 | 1.2.1.4.8.3 | INSPECCION | 6.0eh | 6 | 720.0h | 720 | Nativo (factor 120.0x) | 2025-07-21T16:00 | 2025-07-21T22:00 | 0 | 101FS; 201FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
203 | 1.2.1.4.8.4 | CAMBIO DE FLEJES CUERPO | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-26T22:00 | 2025-07-28T22:00 | 0 | 202FS; 207FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
204 | 1.2.1.4.8.5 | REACONDICIONAR BONETE | 144.0eh | 144 | 1152.0h | 1152 | Nativo (factor 8.0x) | 2025-07-18T08:00 | 2025-07-24T08:00 | 0 | 201FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | DESMONTAJE,RECUPERACION DE BASE Y SOLDAR NUEVO | 6
205 | 1.2.1.4.8.6 | ROMPER REFRACTARIO | 24.0eh | 24 | 3456.0h | 3456 | Nativo (factor 144.0x) | 2025-07-21T22:00 | 2025-07-22T22:00 | 0 | 202FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
206 | 1.2.1.4.8.7 | CAMBIO DE INYECCIONES | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-22T22:00 | 2025-07-24T10:00 | 0 | 205FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
207 | 1.2.1.4.8.8 | REPARAR REFRACTARIO | 60.0eh | 60 | 864.0h | 864 | Nativo (factor 14.4x) | 2025-07-24T10:00 | 2025-07-26T22:00 | 0 | 206FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
208 | 1.2.1.4.8.9 | MONTAR BONETE | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-28T22:00 | 2025-07-29T22:00 | 0 | 108FS; 203FS; 204FS; 207FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
209 | 1.2.1.4.8.10 | SOLDAR DIAFRAGMA | 30.0eh | 30 | 576.0h | 576 | Nativo (factor 19.2x) | 2025-07-29T22:00 | 2025-07-31T04:00 | 0 | 208FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
210 | 1.2.1.4.8.11 | MONTAR MECANISMOS | 12.0eh | 12 | 720.0h | 720 | Nativo (factor 60.0x) | 2025-07-31T04:00 | 2025-07-31T16:00 | 0 | 209FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
211 | 1.2.1.4.8.12 | CALIBRAR | 30.0eh | 30 | 288.0h | 288 | Nativo (factor 9.6x) | 2025-07-31T16:00 | 2025-08-01T22:00 | 0 | 210FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
212 | 1.2.1.4.8.13 | ACCIONAR | 8.0eh | 8 | 720.0h | 720 | Nativo (factor 90.0x) | 2025-08-01T22:00 | 2025-08-02T06:00 | 0 | 211FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
213 | 1.2.1.4.9 | LINEA "J" | 18.4875d | 443.7 | 192.0h | 192 | Nativo (factor 0.4x) | 2025-07-15T06:00 | 2025-08-02T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
214 | 1.2.1.4.9.1 | DESTAPAR P.H. | 24.0eh | 24 | 443.7h | 443.7 | Nativo (factor 18.5x) | 2025-07-15T06:00 | 2025-07-16T06:00 | 0 | 10SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
215 | 1.2.1.4.9.2 | VENTILACION | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-16T06:00 | 2025-07-17T06:00 | 0 | 214FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
216 | 1.2.1.4.9.3 | LIMPIEZA | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-17T06:00 | 2025-07-18T18:00 | 0 | 215FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
217 | 1.2.1.4.9.4 | INSPECCION | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-18T18:00 | 2025-07-19T18:00 | 0 | 216FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
218 | 1.2.1.4.9.5 | ROMPER REFRACTARIO | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-26T22:00 | 2025-07-28T22:00 | 0 | 207FS; 217FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
219 | 1.2.1.4.9.6 | REPONER ANCLAJES | 40.0eh | 40 | 1152.0h | 1152 | Nativo (factor 28.8x) | 2025-07-28T22:00 | 2025-07-30T14:00 | 0 | 218FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
220 | 1.2.1.4.9.7 | REPARAR FEFRACTARIO | 48.0eh | 48 | 960.0h | 960 | Nativo (corregido) | 2025-07-30T14:00 | 2025-08-01T14:00 | 0 | 219FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
221 | 1.2.1.4.9.8 | LIMPIEZA / INSP./REC.HICV606 | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-08-01T14:00 | 2025-08-02T02:00 | 0 | 208FS; 220FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
222 | 1.2.1.4.9.9 | TAPAR PH | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-02T06:00 | 2025-08-02T18:00 | 0 | 212FS; 221FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
223 | 1.2.1.5 | HCV-605 | 14.65625d | 351.75 | 14.65625d | 351.75 | MPXJ (validado) | 2025-07-16T18:00 | 2025-07-31T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
224 | 1.2.1.5.1 | DESCONECTAR | 12.0eh | 12 | 351.8h | 351.75 | Nativo (factor 29.3x) | 2025-07-16T18:00 | 2025-07-17T06:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
225 | 1.2.1.5.2 | DESMONTAR BONETES | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-17T06:00 | 2025-07-18T06:00 | 0 | 224FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
226 | 1.2.1.5.3 | DESMONTAJE DE INTERNOS | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-18T06:00 | 2025-07-19T00:00 | 0 | 225FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
227 | 1.2.1.5.4 | DESBRIDAR Y GIRAR CUERPO | 48.0eh | 48 | 432.0h | 432 | Nativo (factor 9.0x) | 2025-07-19T00:00 | 2025-07-21T00:00 | 0 | 226FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
228 | 1.2.1.5.5 | REPARACION | 90.0eh | 90 | 1152.0h | 1152 | Nativo (factor 12.8x) | 2025-07-21T00:00 | 2025-07-24T18:00 | 0 | 227FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
229 | 1.2.1.5.6 | MONTAJE DE INTERNOS | 22.0eh | 22 | 2160.0h | 2160 | Nativo (factor 98.2x) | 2025-07-27T00:00 | 2025-07-27T22:00 | 0 | 152FS; 228FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
230 | 1.2.1.5.7 | MONTAJE BONETE | 24.0eh | 24 | 528.0h | 528 | Nativo (corregido) | 2025-07-27T22:00 | 2025-07-28T22:00 | 0 | 229FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
231 | 1.2.1.5.8 | SOLDAR DIAFRAGMA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-28T22:00 | 2025-07-29T22:00 | 0 | 230FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
232 | 1.2.1.5.9 | CONECTAR INSTRUMENTAL | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-29T22:00 | 2025-07-31T10:00 | 0 | 231FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
233 | 1.2.1.6 | HCV-607 | 15.364583333333334d | 368.75 | 864.0h | 864 | Nativo (factor 2.3x) | 2025-07-17T06:00 | 2025-08-01T15:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
234 | 1.2.1.6.1 | DESCONECTAR | 12.0eh | 12 | 368.8h | 368.75 | Nativo (factor 30.7x) | 2025-07-17T06:00 | 2025-07-17T18:00 | 0 | 224FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
235 | 1.2.1.6.2 | DESMONTAR BONETE | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 234FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
236 | 1.2.1.6.3 | DESARME DE INTERNOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-18T18:00 | 2025-07-19T06:00 | 0 | 235FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
237 | 1.2.1.6.4 | REPARACION | 90.0eh | 90 | 288.0h | 288 | Nativo (factor 3.2x) | 2025-07-19T06:00 | 2025-07-23T00:00 | 0 | 236FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
238 | 1.2.1.6.5 | MONTAJE DE INTERNOS | 24.0eh | 24 | 2160.0h | 2160 | Nativo (factor 90.0x) | 2025-07-27T22:00 | 2025-07-28T22:00 | 0 | 229FS; 237FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
239 | 1.2.1.6.6 | MONTAJE DE BONETE | 17.0eh | 17 | 576.0h | 576 | Nativo (factor 33.9x) | 2025-07-28T22:00 | 2025-07-29T15:00 | 0 | 238FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
240 | 1.2.1.6.7 | CONECTAR INSTRUMENTAL | 36.0eh | 36 | 408.0h | 408 | Nativo (factor 11.3x) | 2025-07-29T15:00 | 2025-07-31T03:00 | 0 | 239FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
241 | 1.2.1.6.8 | PRUEBA DE NUEVA CENTRALINA | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-31T03:00 | 2025-08-01T15:00 | 0 | 240FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
242 | 1.2.1.7 | F-673 (CICLONES TERCIARIO) | 16.072222222222223d | 385.7333 | 864.0h | 864 | Nativo (factor 2.2x) | 2025-07-15T18:00 | 2025-07-31T20:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
243 | 1.2.1.7.1 | COLOCAR BC | 12.0eh | 12 | 385.7h | 385.7333 | Nativo (factor 32.1x) | 2025-07-15T18:00 | 2025-07-16T06:00 | 0 | 15FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
244 | 1.2.1.7.2 | DESTAPAR PHs | 18.0eh | 18 | 288.0h | 288 | Nativo (factor 16.0x) | 2025-07-16T06:00 | 2025-07-17T00:00 | 0 | 243FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
245 | 1.2.1.7.3 | RETIRAR CATALIZADOR | 72.0eh | 72 | 432.0h | 432 | Nativo (factor 6.0x) | 2025-07-17T00:00 | 2025-07-20T00:00 | 0 | 244FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
246 | 1.2.1.7.4 | MONTAR ANDAMIO INTERIOR | 12.0eh | 12 | 1728.0h | 1728 | Nativo (factor 144.0x) | 2025-07-20T00:00 | 2025-07-20T12:00 | 0 | 245FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
247 | 1.2.1.7.5 | REALIZAR LPZA CICLONES | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-20T12:00 | 2025-07-21T12:00 | 0 | 246FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
248 | 1.2.1.7.6 | REALIZAR LPZA ENVOLV. | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-21T12:00 | 2025-07-23T12:00 | 0 | 247FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
249 | 1.2.1.7.7 | INSPECCION | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-23T12:00 | 2025-07-24T12:00 | 0 | 248FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
250 | 1.2.1.7.8 | REPARACIONES MET. | 72.0eh | 72 | 576.0h | 576 | Nativo (factor 8.0x) | 2025-07-24T12:00 | 2025-07-27T12:00 | 0 | 249FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
251 | 1.2.1.7.9 | RECEPCIÓN DE LIMPIEZA CICLONES PROCESOS/OPERACIONES | 6.0eh | 6 | 1728.0h | 1728 | Nativo (factor 288.0x) | 2025-07-27T12:00 | 2025-07-27T18:00 | 0 | 250FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
252 | 1.2.1.7.10 | DESMONTAR ANDAMIOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-27T18:00 | 2025-07-28T00:00 | 0 | 251FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
253 | 1.2.1.7.11 | REPARAR REFRACTARIO CONO | 36.0eh | 36 | 144.0h | 144 | Nativo (factor 4.0x) | 2025-07-28T00:00 | 2025-07-29T12:00 | 0 | 252FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
254 | 1.2.1.7.12 | LIMPIEZA FINA | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-29T12:00 | 2025-07-30T00:00 | 0 | 253FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
255 | 1.2.1.7.13 | DESMONTAR ACCESO | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-30T00:00 | 2025-07-31T00:00 | 0 | 254FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
256 | 1.2.1.7.14 | TAPAR PHs | 20.0eh | 20 | 576.0h | 576 | Nativo (factor 28.8x) | 2025-07-31T00:00 | 2025-07-31T20:00 | 0 | 255FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
257 | 1.2.1.8 | CHIMENEA Y VALV. DESLIZANTES | 13.948611111111111d | 334.7667 | 480.0h | 480 | Nativo (factor 1.4x) | 2025-07-16T18:00 | 2025-07-30T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 1-CONSTRUIR BALANCIN PARA DESMONTAR 2-VERIFICAR ESTADO DE LA CHAPA 3-MONTAR ANDAMO PARA DESBRIDAR Y CORTAR 4-REALIZAR RELEVAMIENTO DE ZONA A CORTAR. 5-GRUA 6-MONTAR SOPORTES PROVISORIOS | 4
258 | 1.2.1.8.1 | G-614 CHIMENEA | 13.074305555555556d | 313.7833 | 13.074305555555556d | 313.7833 | MPXJ (validado) | 2025-07-16T18:00 | 2025-07-29T20:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
259 | 1.2.1.8.1.1 | DESTAPAR PH (3) | 24.0eh | 24 | 313.8h | 313.7833 | Nativo (factor 13.1x) | 2025-07-16T18:00 | 2025-07-17T18:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
260 | 1.2.1.8.1.2 | MONTAR ANDAMIOS INTERIOR | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 259FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
261 | 1.2.1.8.1.3 | LIMPIEZA INTERNA COMPLETA | 80.0eh | 80 | 1152.0h | 1152 | Nativo (factor 14.4x) | 2025-07-19T18:00 | 2025-07-23T02:00 | 0 | 260FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
262 | 1.2.1.8.1.4 | INSPECCION | 24.0eh | 24 | 1920.0h | 1920 | Nativo (factor 80.0x) | 2025-07-23T02:00 | 2025-07-24T02:00 | 0 | 261FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
263 | 1.2.1.8.1.5 | REPARACIONES | 90.0eh | 90 | 576.0h | 576 | Nativo (factor 6.4x) | 2025-07-24T02:00 | 2025-07-27T20:00 | 0 | 262FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
264 | 1.2.1.8.1.6 | DESARME DE ANDAMIO | 24.0eh | 24 | 2160.0h | 2160 | Nativo (factor 90.0x) | 2025-07-27T20:00 | 2025-07-28T20:00 | 0 | 263FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
265 | 1.2.1.8.1.7 | CIERRE DE PH | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-28T20:00 | 2025-07-29T20:00 | 0 | 264FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
266 | 1.2.1.8.2 | VALVULAS DESLIZANTES | 12.949305555555556d | 310.7833 | 576.0h | 576 | Nativo (factor 1.9x) | 2025-07-17T18:00 | 2025-07-30T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
267 | 1.2.1.8.2.1 | HCV 621/622 | 8.785416666666666d | 210.85 | 310.8h | 310.7833 | Nativo (factor 1.5x) | 2025-07-17T18:00 | 2025-07-26T13:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
268 | 1.2.1.8.2.1.1 | DESMONTAR BONETES | 24.0eh | 24 | 210.8h | 210.85 | Nativo (factor 8.8x) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 259FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
269 | 1.2.1.8.2.1.2 | INSPECCIÓN | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-07-18T18:00 | 2025-07-19T00:00 | 0 | 268FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
270 | 1.2.1.8.2.1.3 | REPARACION DE REFRACTARIO | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-20T09:00 | 2025-07-21T09:00 | 0 | 269FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
271 | 1.2.1.8.2.1.4 | ENSAYOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-21T09:00 | 2025-07-22T09:00 | 0 | 270FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
272 | 1.2.1.8.2.1.5 | ARMADO Y CONEXIÓN DE SISTEMA CENTRALINA | 100.0eh | 100 | 576.0h | 576 | Nativo (factor 5.8x) | 2025-07-22T09:00 | 2025-07-26T13:00 | 0 | 271FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
273 | 1.2.1.8.2.2 | HCV 623/624 | 11.700694444444444d | 280.8167 | 2400.0h | 2400 | Nativo (factor 8.5x) | 2025-07-19T00:00 | 2025-07-30T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 6
274 | 1.2.1.8.2.2.1 | DESMONTAR BONETES | 24.0eh | 24 | 280.8h | 280.8167 | Nativo (factor 11.7x) | 2025-07-19T00:00 | 2025-07-20T00:00 | 0 | 269FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
275 | 1.2.1.8.2.2.2 | REEMPLAZO DE CUERPO | 96.0eh | 96 | 576.0h | 576 | Nativo (factor 6.0x) | 2025-07-20T00:00 | 2025-07-24T00:00 | 0 | 274FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
276 | 1.2.1.8.2.2.3 | ENSAYOS | 24.0eh | 24 | 2304.0h | 2304 | Nativo (factor 96.0x) | 2025-07-24T00:00 | 2025-07-25T00:00 | 0 | 271FS; 275FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
277 | 1.2.1.8.2.2.4 | ARMADO Y CONEXIÓN DE SISTEMA CENTRALINA | 100.0eh | 100 | 576.0h | 576 | Nativo (factor 5.8x) | 2025-07-26T13:00 | 2025-07-30T17:00 | 0 | 272FS; 276FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 7
278 | 1.2.1.9 | LINEA TRANSFERENCIA | 17.904166666666665d | 429.7 | 2400.0h | 2400 | Nativo (factor 5.6x) | 2025-07-16T18:00 | 2025-08-03T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 1-RELIZAR RELEVAMIENTO 2-MONTAR ANDAMIOS NECESARIOS 3-MONTAR SOPORTES PROVISORIOS 4-MONTAR CANCAMOS 5-SON 6 TRAMOS | 4
279 | 1.2.1.9.1 | ABRIR 2 PH | 36.0eh | 36 | 429.7h | 429.7 | Nativo (factor 11.9x) | 2025-07-16T18:00 | 2025-07-18T06:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | SE DEBERÁ SOLDAAR P.P. | 5
280 | 1.2.1.9.2 | VENTILACION | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-18T06:00 | 2025-07-19T06:00 | 0 | 279FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
281 | 1.2.1.9.3 | MONTAR ACCESO | 72.0eh | 72 | 576.0h | 576 | Nativo (factor 8.0x) | 2025-07-19T06:00 | 2025-07-22T06:00 | 0 | 280FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
282 | 1.2.1.9.4 | LIMPIEZA | 60.0eh | 60 | 1728.0h | 1728 | Nativo (factor 28.8x) | 2025-07-22T06:00 | 2025-07-24T18:00 | 0 | 279FS; 281FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | REALIZAR CORTE EN FRIO (HILO) 2 CORTES | 5
283 | 1.2.1.9.5 | INSPECCION | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-24T18:00 | 2025-07-25T18:00 | 0 | 282FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
284 | 1.2.1.9.6 | REPARACIONES DE REFRACTARIO | 70.0eh | 70 | 576.0h | 576 | Nativo (factor 8.2x) | 2025-07-25T18:00 | 2025-07-28T16:00 | 0 | 283FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
285 | 1.2.1.9.7 | INSPECCION | 24.0eh | 24 | 1680.0h | 1680 | Nativo (factor 70.0x) | 2025-07-28T16:00 | 2025-07-29T16:00 | 0 | 284FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
286 | 1.2.1.9.8 | DESARME DE ACCESO | 72.0eh | 72 | 576.0h | 576 | Nativo (factor 8.0x) | 2025-07-29T16:00 | 2025-08-01T16:00 | 0 | 285FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
287 | 1.2.1.9.9 | CIERRE DE TAPONES | 24.0eh | 24 | 1728.0h | 1728 | Nativo (factor 72.0x) | 2025-08-01T16:00 | 2025-08-02T16:00 | 0 | 286FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
288 | 1.2.1.9.10 | CERRA PH (2) | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-08-02T16:00 | 2025-08-03T16:00 | 0 | 287FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
289 | 1.2.1.10 | C671 FLUE GAS COOLER ALTA | 18.486805555555556d | 443.6833 | 576.0h | 576 | Nativo (factor 1.3x) | 2025-07-16T18:00 | 2025-08-04T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
290 | 1.2.1.10.1 | ABRIR PH | 24.0eh | 24 | 443.7h | 443.6833 | Nativo (factor 18.5x) | 2025-07-16T18:00 | 2025-07-17T18:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
291 | 1.2.1.10.2 | COLOCAR BC | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 290FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
292 | 1.2.1.10.3 | VENTILACION | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-18T18:00 | 2025-07-19T18:00 | 0 | 291FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
293 | 1.2.1.10.4 | MONTAR ACCESO | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-19T18:00 | 2025-07-20T02:00 | 0 | 292FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
294 | 1.2.1.10.5 | RETIRO DE FERRULES | 60.0eh | 60 | 192.0h | 192 | Nativo (factor 3.2x) | 2025-07-20T02:00 | 2025-07-22T14:00 | 0 | 293FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
295 | 1.2.1.10.6 | RETIRO DE REFRACTARIO | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-22T14:00 | 2025-07-25T02:00 | 0 | 294FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
296 | 1.2.1.10.7 | LIMPIEZA DE PLACA Y COSTURAS | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-25T02:00 | 2025-07-26T14:00 | 0 | 295FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
297 | 1.2.1.10.8 | INSPECCION | 20.0eh | 20 | 864.0h | 864 | Nativo (factor 43.2x) | 2025-07-26T14:00 | 2025-07-27T10:00 | 0 | 296FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
298 | 1.2.1.10.9 | PRUEBA HIDRAULICA | 36.0eh | 36 | 480.0h | 480 | Nativo (factor 13.3x) | 2025-07-27T10:00 | 2025-07-28T22:00 | 0 | 291FS; 297FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
299 | 1.2.1.10.10 | COLOCAR FERRULES Y HORMIGON | 72.0eh | 72 | 864.0h | 864 | Nativo (factor 12.0x) | 2025-07-28T22:00 | 2025-07-31T22:00 | 0 | 298FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
300 | 1.2.1.10.11 | INSPECCION | 12.0eh | 12 | 1728.0h | 1728 | Nativo (factor 144.0x) | 2025-07-31T22:00 | 2025-08-01T10:00 | 0 | 299FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
301 | 1.2.1.10.12 | RETIRO DE ACCESO | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-08-01T10:00 | 2025-08-02T10:00 | 0 | 300FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
302 | 1.2.1.10.13 | CERRAR PH | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-08-02T10:00 | 2025-08-03T22:00 | 0 | 301FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
303 | 1.2.1.10.14 | RETIRO DE BC | 8.0eh | 8 | 864.0h | 864 | Nativo (factor 108.0x) | 2025-08-03T22:00 | 2025-08-04T06:00 | 0 | 302FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
304 | 1.2.1.11 | C672 FLUE GAS COOLER BAJA | 5.4125d | 129.9 | 192.0h | 192 | Nativo (factor 1.5x) | 2025-07-16T18:00 | 2025-07-22T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
305 | 1.2.1.11.1 | ABRIR PH | 12.0eh | 12 | 129.9h | 129.9 | Nativo (factor 10.8x) | 2025-07-16T18:00 | 2025-07-17T06:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
306 | 1.2.1.11.2 | COLOCAR BC | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-17T06:00 | 2025-07-18T06:00 | 0 | 305FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
307 | 1.2.1.11.3 | MONTAR ACCESO | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-18T06:00 | 2025-07-18T18:00 | 0 | 306FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
308 | 1.2.1.11.4 | PRUEBA HIDRAULICA | 30.0eh | 30 | 288.0h | 288 | Nativo (factor 9.6x) | 2025-07-18T18:00 | 2025-07-20T00:00 | 0 | 307FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
309 | 1.2.1.11.5 | INSPECCION | 12.0eh | 12 | 720.0h | 720 | Nativo (factor 60.0x) | 2025-07-20T00:00 | 2025-07-20T12:00 | 0 | 308FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
310 | 1.2.1.11.6 | RETIRO DE ACCESO | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-20T12:00 | 2025-07-20T20:00 | 0 | 309FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
311 | 1.2.1.11.7 | CERRAR PH | 24.0eh | 24 | 192.0h | 192 | Nativo (factor 8.0x) | 2025-07-20T20:00 | 2025-07-21T20:00 | 0 | 310FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
312 | 1.2.1.11.8 | RETIRO DE BC | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-21T20:00 | 2025-07-22T04:00 | 0 | 311FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
313 | 1.2.1.12 | RETIRO BC RG RX | 46.0eh | 46 | 192.0h | 192 | Nativo (factor 4.2x) | 2025-08-11T01:02 | 2025-08-12T23:02 | 0 | 35FS; 82FS; 137FS; 154FS; 172FS; 180FS; 222FS; 256FS; 288FS; 1123FS; 1124FS; 45FS; 98FS; 209FS; 231FS; 241FS; 265FS; 272FS; 275FS; 97FS; 232FS; 277FS; 312FS; 303FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 4
314 | 1.2.2 | TORRES (8) | 25.981944444444444d | 623.5667 | 1104.0h | 1104 | Nativo (factor 1.8x) | 2025-07-17T18:00 | 2025-08-12T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
315 | 1.2.2.1 | E-601 | 25.981944444444444d | 623.5667 | 25.981944444444444d | 623.5667 | MPXJ (validado) | 2025-07-17T18:00 | 2025-08-12T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 32 PLATOS , P1 , P2, BAFLES 6, DIA. 5650 mm (25 m2) | 4
316 | 1.2.2.1.1 | CEGADO | 36.0eh | 36 | 623.6h | 623.5667 | Nativo (factor 17.3x) | 2025-07-17T18:00 | 2025-07-19T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
317 | 1.2.2.1.2 | RETIRO ESPARRAGO POR MEDIO DE PHs | 6.0eh | 6 | 864.0h | 864 | Nativo (factor 144.0x) | 2025-07-17T18:00 | 2025-07-18T00:00 | 0 | 316SS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
318 | 1.2.2.1.3 | APERTURA DE PH | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-07-19T06:00 | 2025-07-19T14:00 | 0 | 316FS; 317FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
319 | 1.2.2.1.4 | VENTILACIÓN | 12.0eh | 12 | 192.0h | 192 | Nativo (factor 16.0x) | 2025-07-19T14:00 | 2025-07-20T02:00 | 0 | 318FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
320 | 1.2.2.1.5 | INSPECCIÓN PROCESOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-20T02:00 | 2025-07-20T06:00 | 0 | 319FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
321 | 1.2.2.1.6 | APERTURA DE PASAJES | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-07-20T06:00 | 2025-07-21T06:00 | 0 | 319FS; 320FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
322 | 1.2.2.1.7 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-21T06:00 | 2025-07-21T18:00 | 0 | 321FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
323 | 1.2.2.1.8 | LIMPIEZA GRUESA | 72.0eh | 72 | 288.0h | 288 | Nativo (factor 4.0x) | 2025-07-21T18:00 | 2025-07-24T18:00 | 0 | 322FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
324 | 1.2.2.1.9 | CEPILLADO UNIÓN POLLERA-ENVOLVENTE Y SALIDA DE FONDO | 12.0eh | 12 | 1728.0h | 1728 | Nativo (factor 144.0x) | 2025-07-19T06:00 | 2025-07-19T18:00 | 0 | 316FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
325 | 1.2.2.1.10 | END EXTERIORES | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-19T18:00 | 2025-07-20T00:00 | 0 | 324FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
326 | 1.2.2.1.11 | PLATOS 32 AL 19 | 17.7375d | 425.7 | 144.0h | 144 | Nativo (factor 0.3x) | 2025-07-24T18:00 | 2025-08-11T12:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
327 | 1.2.2.1.11.1 | MONTAJE DE SELLO | 4.0eh | 4 | 425.7h | 425.7 | Nativo (factor 106.4x) | 2025-07-24T18:00 | 2025-07-24T22:00 | 0 | 323FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
328 | 1.2.2.1.11.2 | LIMPIEZA FINA | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-07-24T22:00 | 2025-07-25T22:00 | 0 | 327FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
329 | 1.2.2.1.11.3 | CEPILLADO SEGÚN ANEXO I | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-26T00:00 | 2025-07-27T12:00 | 0 | 328FS; 344FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
330 | 1.2.2.1.11.4 | INSPECCIÓN Y END | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-27T12:00 | 2025-07-28T00:00 | 0 | 329FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
331 | 1.2.2.1.11.5 | DESMONTAJE DE PLATOS 28-32 | 54.0eh | 54 | 288.0h | 288 | Nativo (factor 5.3x) | 2025-07-28T00:00 | 2025-07-30T06:00 | 0 | 330FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
332 | 1.2.2.1.11.6 | MONTAJE DE PLATOS 28-32 | 90.0eh | 90 | 1296.0h | 1296 | Nativo (factor 14.4x) | 2025-07-30T06:00 | 2025-08-03T00:00 | 0 | 331FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
333 | 1.2.2.1.11.7 | REPOSICIÓN CLAPETAS Y BULONERÍA (PLATOS 19-27) | 12.0eh | 12 | 2160.0h | 2160 | Nativo (factor 180.0x) | 2025-08-03T00:00 | 2025-08-03T12:00 | 0 | 332FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
334 | 1.2.2.1.11.8 | LIMPIEZA FINA | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-08-03T12:00 | 2025-08-05T00:00 | 0 | 333FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
335 | 1.2.2.1.11.9 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-08-05T00:00 | 2025-08-05T12:00 | 0 | 334FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
336 | 1.2.2.1.11.10 | REPARACIONES METALURGICAS Y AJUSTE DE PLATOS | 96.0eh | 96 | 288.0h | 288 | Nativo (factor 3.0x) | 2025-08-05T12:00 | 2025-08-09T12:00 | 0 | 335FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
337 | 1.2.2.1.11.11 | DESTAPADO TOMA DE INSTRUMENTOS | 12.0eh | 12 | 2304.0h | 2304 | Nativo (factor 192.0x) | 2025-08-03T12:00 | 2025-08-04T00:00 | 0 | 333FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
338 | 1.2.2.1.11.12 | RECEPCIÓN TOMA DE INSTRUMENTOS | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-04T00:00 | 2025-08-04T08:00 | 0 | 337FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
339 | 1.2.2.1.11.13 | RECEPCIÓN FINAL IEE Y PROCESOS | 18.0eh | 18 | 192.0h | 192 | Nativo (factor 10.7x) | 2025-08-09T12:00 | 2025-08-10T06:00 | 0 | 337FS; 336FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
340 | 1.2.2.1.11.14 | CIERRE DE PASAJES | 18.0eh | 18 | 432.0h | 432 | Nativo (corregido) | 2025-08-10T06:00 | 2025-08-11T00:00 | 0 | 339FS; 337FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
341 | 1.2.2.1.11.15 | CIERRE Y TORQUEO DE PH (M1) | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-08-11T00:00 | 2025-08-11T12:00 | 0 | 340FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
342 | 1.2.2.1.12 | PLATOS 18 AL 7 | 15.738888888888889d | 377.7333 | 288.0h | 288 | Nativo (factor 0.8x) | 2025-07-24T18:00 | 2025-08-09T12:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
343 | 1.2.2.1.12.1 | MONTAJE DE SELLO | 6.0eh | 6 | 377.7h | 377.7333 | Nativo (factor 63.0x) | 2025-07-24T18:00 | 2025-07-25T00:00 | 0 | 323FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
344 | 1.2.2.1.12.2 | LIMPIEZA FINA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-25T00:00 | 2025-07-26T00:00 | 0 | 343FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
345 | 1.2.2.1.12.3 | CEPILLADO SEGÚN ANEXO I | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-26T00:00 | 2025-07-27T12:00 | 0 | 344FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
346 | 1.2.2.1.12.4 | INSPECCIÓN Y END | 18.0eh | 18 | 864.0h | 864 | Nativo (factor 48.0x) | 2025-07-27T12:00 | 2025-07-28T06:00 | 0 | 345FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
347 | 1.2.2.1.12.5 | DESMONTAJE DE PLATOS | 72.0eh | 72 | 432.0h | 432 | Nativo (factor 6.0x) | 2025-07-28T06:00 | 2025-07-31T06:00 | 0 | 346FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
348 | 1.2.2.1.12.6 | MONTAJE DE PLATOS | 108.0eh | 108 | 1728.0h | 1728 | Nativo (factor 16.0x) | 2025-07-31T06:00 | 2025-08-04T18:00 | 0 | 347FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
349 | 1.2.2.1.12.7 | LIMPIEZA FINA | 24.0eh | 24 | 2592.0h | 2592 | Nativo (factor 108.0x) | 2025-08-04T18:00 | 2025-08-05T18:00 | 0 | 348FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
350 | 1.2.2.1.12.8 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-08-04T18:00 | 2025-08-05T06:00 | 0 | 348FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
351 | 1.2.2.1.12.9 | REPARACIONES METALURGICAS Y AJUSTE DE PLATOS | 60.0eh | 60 | 288.0h | 288 | Nativo (factor 4.8x) | 2025-08-05T06:00 | 2025-08-07T18:00 | 0 | 350FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
352 | 1.2.2.1.12.10 | DESTAPADO Y RECEPCIÓN TOMA DE INSTRUMENTOS | 4.0eh | 4 | 1440.0h | 1440 | Nativo (factor 360.0x) | 2025-08-07T18:00 | 2025-08-07T22:00 | 0 | 351FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
353 | 1.2.2.1.12.11 | RECEPCIÓN FINAL IEE Y PROCESOS | 18.0eh | 18 | 96.0h | 96 | Nativo (factor 5.3x) | 2025-08-07T22:00 | 2025-08-08T16:00 | 0 | 352FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
354 | 1.2.2.1.12.12 | CIERRE DE PASAJES | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-08-08T16:00 | 2025-08-09T04:00 | 0 | 353FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
355 | 1.2.2.1.12.13 | CIERRE Y TORQUEO DE PH (M2) | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-09T04:00 | 2025-08-09T12:00 | 0 | 354FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
356 | 1.2.2.1.13 | PLATOS 6 AL P2 | 17.404166666666665d | 417.7 | 192.0h | 192 | Nativo (factor 0.5x) | 2025-07-24T18:00 | 2025-08-11T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
357 | 1.2.2.1.13.1 | CEPILLADO SEGÚN ANEXO I | 24.0eh | 24 | 417.7h | 417.7 | Nativo (factor 17.4x) | 2025-07-24T18:00 | 2025-07-25T18:00 | 0 | 323FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
358 | 1.2.2.1.13.2 | INSPECCIÓN Y END | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-28T06:00 | 2025-07-29T00:00 | 0 | 330FS; 346FS; 357FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
359 | 1.2.2.1.13.3 | REPARACION DE CLADING ENVOLVENTE PLATO 4 | 220.0eh | 220 | 432.0h | 432 | Nativo (factor 2.0x) | 2025-07-29T00:00 | 2025-08-07T04:00 | 0 | 358FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
360 | 1.2.2.1.13.4 | REPOSICIÓN DE CLAPETAS Y BULONERÍA | 12.0eh | 12 | 5280.0h | 5280 | Nativo (factor 440.0x) | 2025-08-06T16:00 | 2025-08-07T04:00 | 0 | 359FF |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
361 | 1.2.2.1.13.5 | INSPECCIÓN PROCESOS | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-08-07T04:00 | 2025-08-08T04:00 | 0 | 360FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
362 | 1.2.2.1.13.6 | AJUSTE DE PLATOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-08-08T04:00 | 2025-08-09T04:00 | 0 | 361FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
363 | 1.2.2.1.13.7 | DESTAPADO Y RECEPCIÓN TOMA DE INSTRUMENTOS | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-08-09T04:00 | 2025-08-09T08:00 | 0 | 362FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
364 | 1.2.2.1.13.8 | RECEPCIÓN FINAL IEE Y PROCESOS | 18.0eh | 18 | 96.0h | 96 | Nativo (factor 5.3x) | 2025-08-09T08:00 | 2025-08-10T02:00 | 0 | 363FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
365 | 1.2.2.1.13.9 | PRUEBA DE ESTANQUEIDAD PLATO P2 | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-08-10T02:00 | 2025-08-10T08:00 | 0 | 364FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
366 | 1.2.2.1.13.10 | CIERRE DE PASAJES | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-08-10T08:00 | 2025-08-10T20:00 | 0 | 365FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
367 | 1.2.2.1.13.11 | CIERRE Y TORQUEO DE PH (M3 Y M4) | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-10T20:00 | 2025-08-11T04:00 | 0 | 366FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
368 | 1.2.2.1.14 | PLATOS 3 AL P1 | 14.489583333333334d | 347.75 | 192.0h | 192 | Nativo (factor 0.6x) | 2025-07-24T18:00 | 2025-08-08T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
369 | 1.2.2.1.14.1 | RETIRO DE CARBÓN PLATO P1 Y LIMPIEZA | 36.0eh | 36 | 347.8h | 347.75 | Nativo (factor 9.7x) | 2025-07-24T18:00 | 2025-07-26T06:00 | 0 | 323FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
370 | 1.2.2.1.14.2 | CEPILLADO SEGÚN ANEXO I | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-26T06:00 | 2025-07-27T06:00 | 0 | 369FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
371 | 1.2.2.1.14.3 | INSPECCIÓN Y END | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-27T06:00 | 2025-07-27T18:00 | 0 | 370FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
372 | 1.2.2.1.14.4 | DESMONTAJE DE PLATO 1 | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-27T18:00 | 2025-07-28T06:00 | 0 | 371FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
373 | 1.2.2.1.14.5 | CORTE Y DESMONTAJE DE PLATO P1 | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-28T06:00 | 2025-07-29T18:00 | 0 | 372FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
374 | 1.2.2.1.14.6 | PREPARACIÓN Y END EN ARO SOPORTE | 18.0eh | 18 | 864.0h | 864 | Nativo (factor 48.0x) | 2025-07-29T18:00 | 2025-07-30T12:00 | 0 | 373FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
375 | 1.2.2.1.14.7 | MONTAJE Y SOLDADURA DE PLATO P1 | 96.0eh | 96 | 432.0h | 432 | Nativo (factor 4.5x) | 2025-07-30T12:00 | 2025-08-03T12:00 | 0 | 374FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | 125 metros lineales de soldadura | 6
376 | 1.2.2.1.14.8 | MONTAJE DE PLATO 1 | 12.0eh | 12 | 2304.0h | 2304 | Nativo (factor 192.0x) | 2025-08-03T12:00 | 2025-08-04T00:00 | 0 | 375FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
377 | 1.2.2.1.14.9 | REPOSICIÓN DE CLAPETAS Y BULONERÍA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-04T00:00 | 2025-08-04T12:00 | 0 | 376FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
378 | 1.2.2.1.14.10 | LIMPIEZA FINA | 18.0eh | 18 | 288.0h | 288 | Nativo (factor 16.0x) | 2025-08-04T12:00 | 2025-08-05T06:00 | 0 | 377FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
379 | 1.2.2.1.14.11 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-08-05T06:00 | 2025-08-05T18:00 | 0 | 378FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
380 | 1.2.2.1.14.12 | AJUSTE DE PLATOS | 18.0eh | 18 | 288.0h | 288 | Nativo (factor 16.0x) | 2025-08-05T18:00 | 2025-08-06T12:00 | 0 | 379FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
381 | 1.2.2.1.14.13 | DESTAPADO Y RECEPCIÓN TOMA DE INSTRUMENTOS | 4.0eh | 4 | 432.0h | 432 | Nativo (factor 108.0x) | 2025-08-06T12:00 | 2025-08-06T16:00 | 0 | 380FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
382 | 1.2.2.1.14.14 | RECEPCIÓN FINAL IEE Y PROCESOS | 18.0eh | 18 | 96.0h | 96 | Nativo (factor 5.3x) | 2025-08-06T16:00 | 2025-08-07T10:00 | 0 | 381FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
383 | 1.2.2.1.14.15 | PRUEBA DE ESTANQUEIDAD PLATO P1 | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-08-07T10:00 | 2025-08-07T16:00 | 0 | 382FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
384 | 1.2.2.1.14.16 | CIERRE DE PASAJES | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-08-07T16:00 | 2025-08-07T22:00 | 0 | 383FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
385 | 1.2.2.1.14.17 | CIERRE Y TORQUEO DE PH (M5) | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-08-07T22:00 | 2025-08-08T06:00 | 0 | 384FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
386 | 1.2.2.1.15 | PLATOS S6-FONDO | 21.56875d | 517.65 | 192.0h | 192 | Nativo (factor 0.4x) | 2025-07-20T02:00 | 2025-08-10T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
387 | 1.2.2.1.15.1 | MONTAJE DE ANDAMIO DE FONDO | 12.0eh | 12 | 517.6h | 517.65 | Nativo (factor 43.1x) | 2025-07-20T02:00 | 2025-07-20T14:00 | 0 | 319FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
388 | 1.2.2.1.15.2 | RETIRO DE CARBÓN PLATOS S Y FONDO | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-26T06:00 | 2025-07-27T18:00 | 0 | 369FS; 387FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
389 | 1.2.2.1.15.3 | CEPILLADO SEGÚN ANEXO I | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-27T18:00 | 2025-07-28T18:00 | 0 | 388FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
390 | 1.2.2.1.15.4 | INSPECCIÓN Y END | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-28T18:00 | 2025-07-29T12:00 | 0 | 371FS; 389FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
391 | 1.2.2.1.15.5 | LIMPIEZA DE CANASTO Y SALIDA DE FONDO | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-07-29T12:00 | 2025-07-29T18:00 | 0 | 390FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
392 | 1.2.2.1.15.6 | REPARACIONES METALÚRGICAS (POSIBLE CAMBIO DE PLATOS S) | 36.0eh | 36 | 144.0h | 144 | Nativo (factor 4.0x) | 2025-08-03T12:00 | 2025-08-05T00:00 | 0 | 375FS; 391FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
393 | 1.2.2.1.15.7 | REMPLAZO DE CONEXIÓN 18F + TT | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-08-05T00:00 | 2025-08-06T00:00 | 0 | 392FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
394 | 1.2.2.1.15.8 | REMPLAZO DE BRIDAS EN SALIDA DE FONDO + TT | 30.0eh | 30 | 576.0h | 576 | Nativo (factor 19.2x) | 2025-08-06T00:00 | 2025-08-07T06:00 | 0 | 393FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
395 | 1.2.2.1.15.9 | LIMPIEZA FINA | 18.0eh | 18 | 720.0h | 720 | Nativo (factor 40.0x) | 2025-08-07T06:00 | 2025-08-08T00:00 | 0 | 394FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
396 | 1.2.2.1.15.10 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-08-08T00:00 | 2025-08-08T12:00 | 0 | 395FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
397 | 1.2.2.1.15.11 | AJUSTE DE PLATOS Y REPOSICIÓN DE BULONERÍA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-08T12:00 | 2025-08-09T00:00 | 0 | 396FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
398 | 1.2.2.1.15.12 | DESTAPADO Y RECEPCIÓN TOMA DE INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-09T00:00 | 2025-08-09T04:00 | 0 | 397FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
399 | 1.2.2.1.15.13 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-09T04:00 | 2025-08-09T16:00 | 0 | 398FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
400 | 1.2.2.1.15.14 | RECEPCIÓN SALIDA DE FONDO | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-09T16:00 | 2025-08-09T20:00 | 0 | 399FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
401 | 1.2.2.1.15.15 | DESMONTAJE DE ANDAMIO DE FONDO | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-09T20:00 | 2025-08-10T08:00 | 0 | 400FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
402 | 1.2.2.1.15.16 | CIERRE Y TORQUEO DE PH | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-08-10T08:00 | 2025-08-10T16:00 | 0 | 401FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
403 | 1.2.2.1.16 | RETIRO Y NORMALIZADO DE CIEGOS | 30.0eh | 30 | 192.0h | 192 | Nativo (factor 6.4x) | 2025-08-11T12:00 | 2025-08-12T18:00 | 0 | 325FS; 341FS; 355FS; 367FS; 385FS; 401FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
404 | 1.2.2.2 | E602 | 7.9944444444444445d | 191.8667 | 720.0h | 720 | Nativo (factor 3.8x) | 2025-07-17T18:00 | 2025-07-25T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
405 | 1.2.2.2.1 | CEGADO | 12.0eh | 12 | 191.9h | 191.8667 | Nativo (factor 16.0x) | 2025-07-17T18:00 | 2025-07-18T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
406 | 1.2.2.2.2 | APERTURA DE PH | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-18T06:00 | 2025-07-18T12:00 | 0 | 405FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
407 | 1.2.2.2.3 | VENTILACIÓN | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-18T12:00 | 2025-07-19T00:00 | 0 | 406FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
408 | 1.2.2.2.4 | APERTURA DE PASAJES | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-19T00:00 | 2025-07-19T06:00 | 0 | 407FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
409 | 1.2.2.2.5 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-19T06:00 | 2025-07-19T12:00 | 0 | 408FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
410 | 1.2.2.2.6 | LIMPIEZA GRUESA | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-19T12:00 | 2025-07-20T00:00 | 0 | 409FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
411 | 1.2.2.2.7 | CEPILLADO SEGÚN ANEXO I | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-20T00:00 | 2025-07-20T12:00 | 0 | 410FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
412 | 1.2.2.2.8 | INSPECCIÓN Y END | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-20T12:00 | 2025-07-21T00:00 | 0 | 411FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
413 | 1.2.2.2.9 | INSPECCIÓN PROCESOS | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-21T00:00 | 2025-07-21T06:00 | 0 | 412FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
414 | 1.2.2.2.10 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-21T06:00 | 2025-07-23T06:00 | 0 | 413FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
415 | 1.2.2.2.11 | LIMPIEZA FINA | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-07-23T06:00 | 2025-07-23T18:00 | 0 | 414FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
416 | 1.2.2.2.12 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-24T06:00 | 0 | 415FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
417 | 1.2.2.2.13 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-24T06:00 | 2025-07-24T10:00 | 0 | 416FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
418 | 1.2.2.2.14 | CIERRE DE PASAJES | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-24T10:00 | 2025-07-24T16:00 | 0 | 417FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
419 | 1.2.2.2.15 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-07-24T16:00 | 2025-07-24T20:00 | 0 | 418FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
420 | 1.2.2.2.16 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-07-24T20:00 | 2025-07-25T00:00 | 0 | 419FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
421 | 1.2.2.2.17 | CIERRE DE PH | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-25T00:00 | 2025-07-25T06:00 | 0 | 420FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
422 | 1.2.2.2.18 | RETIRO DE CIEGOS | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-25T06:00 | 2025-07-25T18:00 | 0 | 421FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
423 | 1.2.2.3 | E651 | 18.236805555555556d | 437.6833 | 288.0h | 288 | Nativo (factor 0.7x) | 2025-07-17T18:00 | 2025-08-05T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
424 | 1.2.2.3.1 | CEGADO | 24.0eh | 24 | 437.7h | 437.6833 | Nativo (factor 18.2x) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
425 | 1.2.2.3.2 | APERTURA DE PH | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-18T18:00 | 2025-07-19T06:00 | 0 | 424FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
426 | 1.2.2.3.3 | VENTILACIÓN | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-19T06:00 | 2025-07-19T18:00 | 0 | 425FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
427 | 1.2.2.3.4 | SECCIÓN SUPERIOR (PLATOS 52 AL 21) | 7.9944444444444445d | 191.8667 | 288.0h | 288 | Nativo (factor 1.5x) | 2025-07-25T00:00 | 2025-08-02T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
428 | 1.2.2.3.4.1 | APERTURA DE PASAJES | 12.0eh | 12 | 191.9h | 191.8667 | Nativo (factor 16.0x) | 2025-07-25T00:00 | 2025-07-25T12:00 | 0 | 420FS; 426FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
429 | 1.2.2.3.4.2 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-25T12:00 | 2025-07-25T18:00 | 0 | 428FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
430 | 1.2.2.3.4.3 | LIMPIEZA GRUESA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-25T18:00 | 2025-07-26T18:00 | 0 | 429FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
431 | 1.2.2.3.4.4 | CEPILLADO SEGÚN ANEXO I | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-26T18:00 | 2025-07-27T12:00 | 0 | 430FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
432 | 1.2.2.3.4.5 | INSPECCIÓN Y END | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-07-27T12:00 | 2025-07-28T00:00 | 0 | 431FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
433 | 1.2.2.3.4.6 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-28T00:00 | 2025-07-28T12:00 | 0 | 432FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
434 | 1.2.2.3.4.7 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-07-28T12:00 | 2025-07-30T12:00 | 0 | 433FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
435 | 1.2.2.3.4.8 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-30T12:00 | 2025-07-31T12:00 | 0 | 434FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
436 | 1.2.2.3.4.9 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-31T12:00 | 2025-08-01T00:00 | 0 | 435FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
437 | 1.2.2.3.4.10 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-01T00:00 | 2025-08-01T04:00 | 0 | 436FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
438 | 1.2.2.3.4.11 | CIERRE DE PASAJES | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-01T04:00 | 2025-08-01T16:00 | 0 | 437FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
439 | 1.2.2.3.4.12 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-01T16:00 | 2025-08-01T20:00 | 0 | 438FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
440 | 1.2.2.3.4.13 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-08-01T20:00 | 2025-08-02T00:00 | 0 | 439FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
441 | 1.2.2.3.5 | SECCIÓN SUPERIOR (PLATOS 20 AL FONDO) | 7.9944444444444445d | 191.8667 | 96.0h | 96 | Nativo (factor 0.5x) | 2025-07-26T12:00 | 2025-08-03T12:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
442 | 1.2.2.3.5.1 | APERTURA DE PASAJES | 12.0eh | 12 | 191.9h | 191.8667 | Nativo (factor 16.0x) | 2025-07-26T12:00 | 2025-07-27T00:00 | 0 | 426FS; 473FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
443 | 1.2.2.3.5.2 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-27T00:00 | 2025-07-27T06:00 | 0 | 442FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
444 | 1.2.2.3.5.3 | LIMPIEZA GRUESA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-27T06:00 | 2025-07-28T06:00 | 0 | 430FS; 443FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
445 | 1.2.2.3.5.4 | CEPILLADO SEGÚN ANEXO I | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-28T06:00 | 2025-07-29T00:00 | 0 | 444FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
446 | 1.2.2.3.5.5 | INSPECCIÓN Y END | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-07-29T00:00 | 2025-07-29T12:00 | 0 | 432FS; 445FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
447 | 1.2.2.3.5.6 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-29T12:00 | 2025-07-30T00:00 | 0 | 446FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
448 | 1.2.2.3.5.7 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-07-30T00:00 | 2025-08-01T00:00 | 0 | 447FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
449 | 1.2.2.3.5.8 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-08-01T00:00 | 2025-08-02T00:00 | 0 | 448FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
450 | 1.2.2.3.5.9 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-08-02T00:00 | 2025-08-02T12:00 | 0 | 449FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
451 | 1.2.2.3.5.10 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-02T12:00 | 2025-08-02T16:00 | 0 | 450FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
452 | 1.2.2.3.5.11 | CIERRE DE PASAJES | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-02T16:00 | 2025-08-03T04:00 | 0 | 451FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
453 | 1.2.2.3.5.12 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-03T04:00 | 2025-08-03T08:00 | 0 | 452FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
454 | 1.2.2.3.5.13 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-08-03T08:00 | 2025-08-03T12:00 | 0 | 453FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
455 | 1.2.2.3.6 | CIERRE DE PH | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-03T12:00 | 2025-08-04T00:00 | 0 | 440FS; 454FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
456 | 1.2.2.3.7 | RETIRO DE CIEGOS | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-08-04T00:00 | 2025-08-05T00:00 | 0 | 455FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
457 | 1.2.2.4 | E652 | 9.493055555555555d | 227.8333 | 576.0h | 576 | Nativo (factor 2.5x) | 2025-07-17T18:00 | 2025-07-27T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
458 | 1.2.2.4.1 | CEGADO | 12.0eh | 12 | 227.8h | 227.8333 | Nativo (factor 19.0x) | 2025-07-17T18:00 | 2025-07-18T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
459 | 1.2.2.4.2 | APERTURA DE PH | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-18T06:00 | 2025-07-18T12:00 | 0 | 458FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
460 | 1.2.2.4.3 | VENTILACIÓN | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-18T12:00 | 2025-07-19T00:00 | 0 | 459FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
461 | 1.2.2.4.4 | APERTURA DE PASAJES | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-19T00:00 | 2025-07-19T12:00 | 0 | 460FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
462 | 1.2.2.4.5 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-19T12:00 | 2025-07-19T18:00 | 0 | 461FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
463 | 1.2.2.4.6 | LIMPIEZA GRUESA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-19T18:00 | 2025-07-20T18:00 | 0 | 462FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
464 | 1.2.2.4.7 | CEPILLADO SEGÚN ANEXO I | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-20T18:00 | 2025-07-21T06:00 | 0 | 463FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
465 | 1.2.2.4.8 | INSPECCIÓN Y END | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-21T06:00 | 2025-07-21T18:00 | 0 | 412FS; 464FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
466 | 1.2.2.4.9 | INSPECCIÓN PROCESOS | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-21T18:00 | 2025-07-22T00:00 | 0 | 465FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
467 | 1.2.2.4.10 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-22T00:00 | 2025-07-24T00:00 | 0 | 466FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
468 | 1.2.2.4.11 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-24T00:00 | 2025-07-25T00:00 | 0 | 467FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
469 | 1.2.2.4.12 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-25T00:00 | 2025-07-25T12:00 | 0 | 468FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
470 | 1.2.2.4.13 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-25T12:00 | 2025-07-25T16:00 | 0 | 469FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
471 | 1.2.2.4.14 | CIERRE DE PASAJES | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-07-25T16:00 | 2025-07-26T04:00 | 0 | 470FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
472 | 1.2.2.4.15 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-26T04:00 | 2025-07-26T08:00 | 0 | 471FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
473 | 1.2.2.4.16 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-07-26T08:00 | 2025-07-26T12:00 | 0 | 472FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
474 | 1.2.2.4.17 | CIERRE DE PH | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-26T12:00 | 2025-07-26T18:00 | 0 | 473FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
475 | 1.2.2.4.18 | RETIRO DE CIEGOS | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-26T18:00 | 2025-07-27T06:00 | 0 | 474FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
476 | 1.2.2.5 | E653 | 12.490972222222222d | 299.7833 | 12.490972222222222d | 299.7833 | MPXJ (validado) | 2025-07-17T18:00 | 2025-07-30T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
477 | 1.2.2.5.1 | CEGADO | 24.0eh | 24 | 299.8h | 299.7833 | Nativo (factor 12.5x) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
478 | 1.2.2.5.2 | APERTURA DE PH | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-18T18:00 | 2025-07-19T06:00 | 0 | 477FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
479 | 1.2.2.5.3 | VENTILACIÓN | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-19T06:00 | 2025-07-19T18:00 | 0 | 478FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
480 | 1.2.2.5.4 | SECCIÓN SUPERIOR (PLATOS 44 AL 23) | 7.661111111111111d | 183.8667 | 288.0h | 288 | Nativo (factor 1.6x) | 2025-07-19T18:00 | 2025-07-27T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
481 | 1.2.2.5.4.1 | APERTURA DE PASAJES | 12.0eh | 12 | 183.9h | 183.8667 | Nativo (factor 15.3x) | 2025-07-19T18:00 | 2025-07-20T06:00 | 0 | 479FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
482 | 1.2.2.5.4.2 | LIMPIEZA GRUESA | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-20T12:00 | 2025-07-21T12:00 | 0 | 481FS; 492FS; 493FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
483 | 1.2.2.5.4.3 | CEPILLADO SEGÚN ANEXO I | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-21T12:00 | 2025-07-22T06:00 | 0 | 482FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
484 | 1.2.2.5.4.4 | INSPECCIÓN Y END | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 483FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
485 | 1.2.2.5.4.5 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T06:00 | 0 | 484FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
486 | 1.2.2.5.4.6 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-07-23T06:00 | 2025-07-25T06:00 | 0 | 485FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
487 | 1.2.2.5.4.7 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-25T06:00 | 2025-07-26T06:00 | 0 | 486FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
488 | 1.2.2.5.4.8 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-26T06:00 | 2025-07-26T18:00 | 0 | 487FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
489 | 1.2.2.5.4.9 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-26T18:00 | 2025-07-26T22:00 | 0 | 488FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
490 | 1.2.2.5.4.10 | CIERRE DE PASAJES | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-07-26T22:00 | 2025-07-27T10:00 | 0 | 489FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
491 | 1.2.2.5.5 | SECCIÓN INFERIOR (PLATOS 22 AL FONDO) | 8.99375d | 215.85 | 288.0h | 288 | Nativo (factor 1.3x) | 2025-07-19T18:00 | 2025-07-28T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
492 | 1.2.2.5.5.1 | APERTURA DE PASAJES | 12.0eh | 12 | 215.8h | 215.85 | Nativo (factor 18.0x) | 2025-07-19T18:00 | 2025-07-20T06:00 | 0 | 479FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
493 | 1.2.2.5.5.2 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-20T06:00 | 2025-07-20T12:00 | 0 | 492FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
494 | 1.2.2.5.5.3 | LIMPIEZA GRUESA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-21T12:00 | 2025-07-22T12:00 | 0 | 482FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
495 | 1.2.2.5.5.4 | CEPILLADO SEGÚN ANEXO I | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-22T12:00 | 2025-07-23T06:00 | 0 | 494FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
496 | 1.2.2.5.5.5 | INSPECCIÓN Y END | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-07-23T06:00 | 2025-07-23T18:00 | 0 | 484FS; 495FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
497 | 1.2.2.5.5.6 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-24T06:00 | 0 | 496FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
498 | 1.2.2.5.5.7 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-07-24T06:00 | 2025-07-26T06:00 | 0 | 497FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
499 | 1.2.2.5.5.8 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-26T06:00 | 2025-07-27T06:00 | 0 | 498FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
500 | 1.2.2.5.5.9 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-27T06:00 | 2025-07-27T18:00 | 0 | 499FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
501 | 1.2.2.5.5.10 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-27T18:00 | 2025-07-27T22:00 | 0 | 500FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
502 | 1.2.2.5.5.11 | CIERRE DE PASAJES | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-07-27T22:00 | 2025-07-28T10:00 | 0 | 501FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
503 | 1.2.2.5.5.12 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-28T10:00 | 2025-07-28T14:00 | 0 | 502FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
504 | 1.2.2.5.5.13 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-07-28T14:00 | 2025-07-28T18:00 | 0 | 503FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
505 | 1.2.2.5.6 | CIERRE DE PH | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-07-28T18:00 | 2025-07-29T06:00 | 0 | 490FS; 504FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
506 | 1.2.2.5.7 | RETIRO DE CIEGOS | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-29T06:00 | 2025-07-30T06:00 | 0 | 505FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
507 | 1.2.2.6 | E654 | 20.652083333333334d | 495.65 | 20.652083333333334d | 495.65 | MPXJ (validado) | 2025-07-18T18:00 | 2025-08-08T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
508 | 1.2.2.6.1 | CEGADO | 18.0eh | 18 | 495.6h | 495.65 | Nativo (corregido) | 2025-07-18T18:00 | 2025-07-19T12:00 | 0 | 477FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
509 | 1.2.2.6.2 | APERTURA DE PH | 12.0eh | 12 | 432.0h | 432 | Nativo (factor 36.0x) | 2025-07-19T12:00 | 2025-07-20T00:00 | 0 | 508FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
510 | 1.2.2.6.3 | VENTILACIÓN | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-20T00:00 | 2025-07-20T12:00 | 0 | 509FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
511 | 1.2.2.6.4 | APERTURA DE PASAJES | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-27T10:00 | 2025-07-28T10:00 | 0 | 490FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
512 | 1.2.2.6.5 | MONTAJE DE ANDAMIO DE FONDO | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-07-28T10:00 | 2025-07-28T16:00 | 0 | 511FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
513 | 1.2.2.6.6 | LIMPIEZA GRUESA | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-28T16:00 | 2025-07-30T16:00 | 0 | 512FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
514 | 1.2.2.6.7 | CEPILLADO SEGÚN ANEXO I | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-30T16:00 | 2025-07-31T16:00 | 0 | 513FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
515 | 1.2.2.6.8 | INSPECCIÓN Y END | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-31T16:00 | 2025-08-01T16:00 | 0 | 496FS; 514FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
516 | 1.2.2.6.9 | INSPECCIÓN PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-08-01T16:00 | 2025-08-02T04:00 | 0 | 515FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
517 | 1.2.2.6.10 | REPARACIONES METALÚRGICAS Y AJUSTE DE PLATOS | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-08-02T04:00 | 2025-08-04T04:00 | 0 | 516FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
518 | 1.2.2.6.11 | LIMPIEZA FINA | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-08-04T04:00 | 2025-08-05T04:00 | 0 | 517FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
519 | 1.2.2.6.12 | RECEPCIÓN FINAL IEE Y PROCESOS | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-08-05T04:00 | 2025-08-05T16:00 | 0 | 518FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
520 | 1.2.2.6.13 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-08-05T16:00 | 2025-08-05T20:00 | 0 | 519FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
521 | 1.2.2.6.14 | CIERRE DE PASAJES | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-08-05T20:00 | 2025-08-06T20:00 | 0 | 520FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
522 | 1.2.2.6.15 | DESMONTAJE DE ANDAMIO DE FONDO | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-08-06T20:00 | 2025-08-07T00:00 | 0 | 521FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
523 | 1.2.2.6.16 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-08-07T00:00 | 2025-08-07T04:00 | 0 | 522FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
524 | 1.2.2.6.17 | CIERRE DE PH | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-07T04:00 | 2025-08-07T16:00 | 0 | 523FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
525 | 1.2.2.6.18 | RETIRO DE CIEGOS | 18.0eh | 18 | 288.0h | 288 | Nativo (factor 16.0x) | 2025-08-07T16:00 | 2025-08-08T10:00 | 0 | 524FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
526 | 1.2.2.7 | E661 | 23.23402777777778d | 557.6167 | 432.0h | 432 | Nativo (factor 0.8x) | 2025-07-19T06:00 | 2025-08-11T12:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
527 | 1.2.2.7.1 | CEGADO | 12.0eh | 12 | 557.6h | 557.6167 | Nativo (factor 46.5x) | 2025-07-19T06:00 | 2025-07-19T18:00 | 0 | 478FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
528 | 1.2.2.7.2 | APERTURA DE BOCAS DE INSPECCIÓN | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-19T18:00 | 2025-07-20T00:00 | 0 | 527FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
529 | 1.2.2.7.3 | DESMONTAJE Y LIMPIEZA DE DISTRIBUIDORES | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-20T00:00 | 2025-07-20T12:00 | 0 | 528FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
530 | 1.2.2.7.4 | LIMPIEZA INTERIOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-07T04:00 | 2025-08-07T16:00 | 0 | 523FS; 528FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
531 | 1.2.2.7.5 | CEPILLADO SEGÚN ANEXO I | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-07T16:00 | 2025-08-08T04:00 | 0 | 530FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
532 | 1.2.2.7.6 | INSPECCIÓN Y END | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-08T04:00 | 2025-08-08T16:00 | 0 | 531FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
533 | 1.2.2.7.7 | INSPECCIÓN PROCESOS | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-08-08T16:00 | 2025-08-08T22:00 | 0 | 532FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
534 | 1.2.2.7.8 | REPARACIONES METALÚRGICAS | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-08-08T22:00 | 2025-08-09T22:00 | 0 | 533FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
535 | 1.2.2.7.9 | MONTAJE DE DISTRIBUIDORES | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-08-09T22:00 | 2025-08-10T04:00 | 0 | 534FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
536 | 1.2.2.7.10 | RECEPCIÓN FINAL IEE Y PROCESOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-08-10T04:00 | 2025-08-10T10:00 | 0 | 535FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
537 | 1.2.2.7.11 | RECEPCIÓN TOMAS INSTRUMENTOS | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-08-10T10:00 | 2025-08-10T14:00 | 0 | 536FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
538 | 1.2.2.7.12 | LIMPIEZA DE FONDO Y RECEPCÍON SALIDA DE FONDO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-08-10T14:00 | 2025-08-10T18:00 | 0 | 537FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
539 | 1.2.2.7.13 | CIERRE DE BOCAS DE INSPECCIÓN | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-08-10T18:00 | 2025-08-11T00:00 | 0 | 538FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
540 | 1.2.2.7.14 | RETIRO DE CIEGOS | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-08-11T00:00 | 2025-08-11T12:00 | 0 | 539FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
541 | 1.2.2.8 | E662 | 4.246527777777778d | 101.9167 | 288.0h | 288 | Nativo (factor 2.8x) | 2025-07-19T18:00 | 2025-07-24T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
542 | 1.2.2.8.1 | CEGADO | 6.0eh | 6 | 101.9h | 101.9167 | Nativo (factor 17.0x) | 2025-07-19T18:00 | 2025-07-20T00:00 | 0 | 527FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
543 | 1.2.2.8.2 | APERTURA DE TAPA SUPERIOR | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-20T00:00 | 2025-07-20T06:00 | 0 | 542FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
544 | 1.2.2.8.3 | DESMONTAJE Y LIMPIEZA DE DEMISTER | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-20T06:00 | 2025-07-20T18:00 | 0 | 543FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
545 | 1.2.2.8.4 | LIMPIEZA INTERIOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-20T18:00 | 2025-07-21T06:00 | 0 | 544FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
546 | 1.2.2.8.5 | CEPILLADO SEGÚN ANEXO I | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-21T06:00 | 2025-07-21T12:00 | 0 | 545FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
547 | 1.2.2.8.6 | INSPECCIÓN Y END | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-21T12:00 | 2025-07-22T00:00 | 0 | 546FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
548 | 1.2.2.8.7 | REPARACIONES METALÚRGICAS | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-22T00:00 | 2025-07-23T00:00 | 0 | 547FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
549 | 1.2.2.8.8 | MONTAJE DE DEMISTER | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-07-23T00:00 | 2025-07-23T06:00 | 0 | 548FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
550 | 1.2.2.8.9 | RECEPCIÓN FINAL IEE Y PROCESOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-23T06:00 | 2025-07-23T12:00 | 0 | 549FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
551 | 1.2.2.8.10 | CIERRE DE TAPA SUPERIOR | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-23T12:00 | 2025-07-23T18:00 | 0 | 550FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
552 | 1.2.2.8.11 | RETIRO DE CIEGOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-24T00:00 | 0 | 551FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
553 | 1.2.3 | HORNO | 16.65486111111111d | 399.7167 | 144.0h | 144 | Nativo (factor 0.4x) | 2025-07-17T18:00 | 2025-08-03T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
554 | 1.2.3.1 | B-601 | 16.65486111111111d | 399.7167 | 16.65486111111111d | 399.7167 | MPXJ (validado) | 2025-07-17T18:00 | 2025-08-03T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
555 | 1.2.3.1.1 | COLOCAR BC | 18.0eh | 18 | 399.7h | 399.7167 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T12:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
556 | 1.2.3.1.2 | ABRIR PH | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-07-18T12:00 | 2025-07-18T18:00 | 0 | 555FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
557 | 1.2.3.1.3 | CONEXIONES PARA DECOQUIZADO | 18.0eh | 18 | 144.0h | 144 | Nativo (factor 8.0x) | 2025-07-18T18:00 | 2025-07-19T12:00 | 0 | 556FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
558 | 1.2.3.1.4 | ENFRIAMIENTO | 24.0eh | 24 | 432.0h | 432 | Nativo (factor 18.0x) | 2025-07-18T18:00 | 2025-07-19T18:00 | 0 | 556FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
559 | 1.2.3.1.5 | ARMADO DE ANDAMIO EN RADIACION | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-20T18:00 | 0 | 558FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
560 | 1.2.3.1.6 | ARMADO DE ANDAMIO EN CONVECTIVA-CHIMENEA | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-20T18:00 | 2025-07-21T12:00 | 0 | 559FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
561 | 1.2.3.1.7 | INSPECCION | 24.0eh | 24 | 432.0h | 432 | Nativo (factor 18.0x) | 2025-07-21T12:00 | 2025-07-22T12:00 | 0 | 560FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
562 | 1.2.3.1.8 | REALIZAR MEDALLONES | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-21T12:00 | 2025-07-22T12:00 | 0 | 560FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
563 | 1.2.3.1.9 | DESMONTAJE DE QUEMADORES | 24.0h | 0 | 576.0h | 576 | Nativo (MPXJ=0) | 2025-07-18T18:00 | 2025-07-19T18:01 | 0 | 556FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
564 | 1.2.3.1.10 | REPARACION Y CALIBRACION | 100.0eh | 100 | 24.0h | 24 | Nativo (factor 0.2x) | 2025-07-19T18:01 | 2025-07-23T22:01 | 0 | 563FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
565 | 1.2.3.1.11 | INSPECCION TOMA DE ESPESORES | 24.0eh | 24 | 2400.0h | 2400 | Nativo (factor 100.0x) | 2025-07-22T12:00 | 2025-07-23T12:00 | 0 | 562FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
566 | 1.2.3.1.12 | REALIZAR REPARACIONES DE AISLACION | 90.0eh | 90 | 576.0h | 576 | Nativo (factor 6.4x) | 2025-07-23T12:00 | 2025-07-27T06:00 | 0 | 565FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
567 | 1.2.3.1.13 | INSPECCION Y REEMPLAZO DE TERMOCUPLAS | 60.0eh | 60 | 2160.0h | 2160 | Nativo (factor 36.0x) | 2025-07-27T06:00 | 2025-07-29T18:00 | 0 | 566FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
568 | 1.2.3.1.14 | REPARACIONES DE PERCHAS Y SOPORTES DE TUBOS | 70.0eh | 70 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-23T12:00 | 2025-07-26T10:00 | 0 | 565FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
569 | 1.2.3.1.15 | DESMONTAR ANDAMIO RADIACION | 24.0eh | 24 | 1680.0h | 1680 | Nativo (factor 70.0x) | 2025-07-29T18:00 | 2025-07-30T18:00 | 0 | 567FS; 568FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
570 | 1.2.3.1.16 | LIMPIEZA DE PISO | 18.0eh | 18 | 576.0h | 576 | Nativo (factor 32.0x) | 2025-07-30T18:00 | 2025-07-31T12:00 | 0 | 569FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
571 | 1.2.3.1.17 | REPARACION DE CORONAS QUEM. | 16.0eh | 16 | 432.0h | 432 | Nativo (corregido) | 2025-07-31T12:00 | 2025-08-01T04:00 | 0 | 570FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
572 | 1.2.3.1.18 | MONTAJE DE QUEMADORES Y ALINEACION | 40.0eh | 40 | 384.0h | 384 | Nativo (factor 9.6x) | 2025-07-30T18:00 | 2025-08-01T10:00 | 0 | 564FS; 569FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
573 | 1.2.3.1.19 | INSPECCION | 12.0eh | 12 | 960.0h | 960 | Nativo (factor 80.0x) | 2025-08-01T10:00 | 2025-08-01T22:00 | 0 | 572FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
574 | 1.2.3.1.20 | CERRAR PH | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-01T22:00 | 2025-08-02T10:00 | 0 | 573FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
575 | 1.2.3.1.21 | RETIRAR B.C. | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-08-02T10:00 | 2025-08-03T10:00 | 0 | 574FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
576 | 1.2.4 | ACUMULADORES (25) | 18.861805555555556d | 452.6833 | 576.0h | 576 | Nativo (factor 1.3x) | 2025-07-16T18:00 | 2025-08-04T15:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
577 | 1.2.4.1 | F-601 | 11.241666666666667d | 269.8 | 452.7h | 452.6833 | Nativo (factor 1.7x) | 2025-07-17T18:00 | 2025-07-29T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 10000 mm x 3100 mm---H | 4
578 | 1.2.4.1.1 | COLOCAR BC | 10.0eh | 10 | 269.8h | 269.8 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
579 | 1.2.4.1.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T04:00 | 2025-07-18T12:00 | 0 | 578FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
580 | 1.2.4.1.3 | VENTILACION | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-18T12:00 | 2025-07-20T12:00 | 0 | 579FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
581 | 1.2.4.1.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-20T12:00 | 2025-07-20T16:00 | 0 | 580FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
582 | 1.2.4.1.5 | LIMPIEZA INTERIOR | 60.0eh | 60 | 96.0h | 96 | Nativo (factor 1.6x) | 2025-07-20T16:00 | 2025-07-23T04:00 | 0 | 581FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
583 | 1.2.4.1.6 | PREVER REPARACIONES | 72.0eh | 72 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-23T04:00 | 2025-07-26T04:00 | 0 | 582FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
584 | 1.2.4.1.7 | INSPECCION | 10.0eh | 10 | 1728.0h | 1728 | Nativo (factor 172.8x) | 2025-07-26T04:00 | 2025-07-26T14:00 | 0 | 583FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
585 | 1.2.4.1.8 | LIMPIEZA DE TOMAS | 12.0eh | 12 | 240.0h | 240 | Nativo (corregido) | 2025-07-26T14:00 | 2025-07-27T02:00 | 0 | 584FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
586 | 1.2.4.1.9 | RETIRO ACCESO | 10.0eh | 10 | 288.0h | 288 | Nativo (factor 28.8x) | 2025-07-27T02:00 | 2025-07-27T12:00 | 0 | 585FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
587 | 1.2.4.1.10 | TAPAR PH | 16.0eh | 16 | 240.0h | 240 | Nativo (factor 15.0x) | 2025-07-27T12:00 | 2025-07-28T04:00 | 0 | 586FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
588 | 1.2.4.1.11 | RETIRAR BC | 20.0eh | 20 | 384.0h | 384 | Nativo (factor 19.2x) | 2025-07-28T04:00 | 2025-07-29T00:00 | 0 | 587FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
589 | 1.2.4.1.12 | F-602 | 10.57638888888889d | 253.8333 | 480.0h | 480 | Nativo (factor 1.9x) | 2025-07-18T04:00 | 2025-07-28T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
590 | 1.2.4.1.12.1 | COLOCAR BC | 10.0eh | 10 | 253.8h | 253.8333 | Nativo (corregido) | 2025-07-18T04:00 | 2025-07-18T14:00 | 0 | 578FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
591 | 1.2.4.1.12.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T14:00 | 2025-07-18T22:00 | 0 | 590FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
592 | 1.2.4.1.12.3 | VENTILACION | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-18T22:00 | 2025-07-20T22:00 | 0 | 591FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
593 | 1.2.4.1.12.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-20T22:00 | 2025-07-21T02:00 | 0 | 592FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
594 | 1.2.4.1.12.5 | LIMPIEZA INTERIOR | 48.0eh | 48 | 96.0h | 96 | Nativo (factor 2.0x) | 2025-07-21T02:00 | 2025-07-23T02:00 | 0 | 593FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
595 | 1.2.4.1.12.6 | PREVER REPARACIONES | 72.0eh | 72 | 1152.0h | 1152 | Nativo (factor 16.0x) | 2025-07-23T02:00 | 2025-07-26T02:00 | 0 | 594FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
596 | 1.2.4.1.12.7 | INSPECCION | 12.0eh | 12 | 1728.0h | 1728 | Nativo (factor 144.0x) | 2025-07-26T02:00 | 2025-07-26T14:00 | 0 | 595FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
597 | 1.2.4.1.12.8 | LIMPIEZA DE TOMAS | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-26T14:00 | 2025-07-26T22:00 | 0 | 596FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
598 | 1.2.4.1.12.9 | RETIRO ACCESO | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-26T22:00 | 2025-07-27T06:00 | 0 | 597FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
599 | 1.2.4.1.12.10 | TAPAR PH | 12.0eh | 12 | 192.0h | 192 | Nativo (factor 16.0x) | 2025-07-27T06:00 | 2025-07-27T18:00 | 0 | 598FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
600 | 1.2.4.1.12.11 | RETIRAR BC | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-27T18:00 | 2025-07-28T18:00 | 0 | 599FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
601 | 1.2.4.2 | F-604 | 6.7034722222222225d | 160.8833 | 576.0h | 576 | Nativo (factor 3.6x) | 2025-07-18T12:00 | 2025-07-25T05:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 2650 mm 950 mm de Ø vertical | 4
602 | 1.2.4.2.1 | COLOCAR BC | 8.0eh | 8 | 160.9h | 160.8833 | Nativo (corregido) | 2025-07-18T12:00 | 2025-07-18T20:00 | 0 | 579FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
603 | 1.2.4.2.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-18T20:00 | 2025-07-19T02:00 | 0 | 602FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
604 | 1.2.4.2.3 | VENTILACION / LUZ | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-19T02:00 | 2025-07-21T02:00 | 0 | 603FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
605 | 1.2.4.2.4 | MONTAR ANDAMIO INTERIOR | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-21T02:00 | 2025-07-21T06:00 | 0 | 604FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
606 | 1.2.4.2.5 | LIMPIEZA INTERIOR | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-07-23T04:00 | 2025-07-24T04:00 | 0 | 582FS; 605FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
607 | 1.2.4.2.6 | INSPECCION | 3.0eh | 3 | 576.0h | 576 | Nativo (factor 192.0x) | 2025-07-24T04:00 | 2025-07-24T07:00 | 0 | 606FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
608 | 1.2.4.2.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 72.0h | 72 | Nativo (factor 12.0x) | 2025-07-24T07:00 | 2025-07-24T13:00 | 0 | 607FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
609 | 1.2.4.2.8 | TAPAR PH | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-24T13:00 | 2025-07-24T19:00 | 0 | 608FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
610 | 1.2.4.2.9 | RETIRAR BC | 10.0eh | 10 | 144.0h | 144 | Nativo (factor 14.4x) | 2025-07-24T19:00 | 2025-07-25T05:00 | 0 | 609FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
611 | 1.2.4.3 | F-605 | 8.036111111111111d | 192.8667 | 240.0h | 240 | Nativo (factor 1.2x) | 2025-07-19T02:00 | 2025-07-27T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | DIAM.1100 mm x 2450 mm de altura. V | 4
612 | 1.2.4.3.1 | COLOCAR BC | 8.0eh | 8 | 192.9h | 192.8667 | Nativo (corregido) | 2025-07-19T02:00 | 2025-07-19T10:00 | 0 | 603FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
613 | 1.2.4.3.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-19T10:00 | 2025-07-19T16:00 | 0 | 612FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
614 | 1.2.4.3.3 | VENTILACION / LUZ | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-19T16:00 | 2025-07-21T16:00 | 0 | 613FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
615 | 1.2.4.3.4 | MONTAR ANDAMIO INTERIOR | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-21T16:00 | 2025-07-21T20:00 | 0 | 614FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
616 | 1.2.4.3.5 | LIMPIEZA INTERIOR | 36.0eh | 36 | 96.0h | 96 | Nativo (factor 2.7x) | 2025-07-24T04:00 | 2025-07-25T16:00 | 0 | 606FS; 615FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
617 | 1.2.4.3.6 | INSPECCION | 3.0eh | 3 | 864.0h | 864 | Nativo (factor 288.0x) | 2025-07-25T16:00 | 2025-07-25T19:00 | 0 | 616FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
618 | 1.2.4.3.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 72.0h | 72 | Nativo (factor 12.0x) | 2025-07-25T19:00 | 2025-07-26T01:00 | 0 | 617FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
619 | 1.2.4.3.8 | TAPAR PH | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-26T01:00 | 2025-07-26T13:00 | 0 | 618FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
620 | 1.2.4.3.9 | RETIRAR BC | 14.0eh | 14 | 288.0h | 288 | Nativo (corregido) | 2025-07-26T13:00 | 2025-07-27T03:00 | 0 | 619FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
621 | 1.2.4.4 | F-606 | 9.493055555555555d | 227.8333 | 336.0h | 336 | Nativo (factor 1.5x) | 2025-07-19T16:00 | 2025-07-29T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | DIAM.1100 mm x 2450 mm de altura. V | 4
622 | 1.2.4.4.1 | COLOCAR BC | 12.0eh | 12 | 227.8h | 227.8333 | Nativo (factor 19.0x) | 2025-07-19T16:00 | 2025-07-20T04:00 | 0 | 613FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
623 | 1.2.4.4.2 | DESTAPAR PH | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-20T04:00 | 2025-07-20T10:00 | 0 | 622FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
624 | 1.2.4.4.3 | VENTILACION / LUZ | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-20T10:00 | 2025-07-22T10:00 | 0 | 623FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
625 | 1.2.4.4.4 | MONTAR ANDAMIO INTERIOR | 10.0eh | 10 | 1152.0h | 1152 | Nativo (factor 115.2x) | 2025-07-22T10:00 | 2025-07-22T20:00 | 0 | 624FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
626 | 1.2.4.4.5 | LIMPIEZA INTERIOR | 36.0eh | 36 | 240.0h | 240 | Nativo (factor 6.7x) | 2025-07-25T16:00 | 2025-07-27T04:00 | 0 | 616FS; 625FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
627 | 1.2.4.4.6 | INSPECCION | 18.0eh | 18 | 864.0h | 864 | Nativo (factor 48.0x) | 2025-07-27T04:00 | 2025-07-27T22:00 | 0 | 626FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
628 | 1.2.4.4.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-07-27T22:00 | 2025-07-28T04:00 | 0 | 627FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
629 | 1.2.4.4.8 | TAPAR PH | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-28T04:00 | 2025-07-28T16:00 | 0 | 628FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
630 | 1.2.4.4.9 | RETIRAR BC | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-28T16:00 | 2025-07-29T04:00 | 0 | 629FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
631 | 1.2.4.5 | F-651 | 10.284027777777778d | 246.8167 | 10.284027777777778d | 246.8167 | MPXJ (validado) | 2025-07-17T18:00 | 2025-07-28T01:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | DIAMETRO 3505 MM X 6000 LARGO --H | 4
632 | 1.2.4.5.1 | COLOCAR BC | 10.0eh | 10 | 246.8h | 246.8167 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
633 | 1.2.4.5.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T04:00 | 2025-07-18T12:00 | 0 | 632FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
634 | 1.2.4.5.3 | VENTILACION /LUZ | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-18T12:00 | 2025-07-20T12:00 | 0 | 633FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
635 | 1.2.4.5.4 | MONTAR ANDAMIO INTERIOR | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-07-20T12:00 | 2025-07-21T00:00 | 0 | 634FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
636 | 1.2.4.5.5 | DESMONTAR MALLA | 13.0eh | 13 | 288.0h | 288 | Nativo (corregido) | 2025-07-21T00:00 | 2025-07-21T13:00 | 0 | 635FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
637 | 1.2.4.5.6 | LIMPIAR MALLA | 36.0eh | 36 | 312.0h | 312 | Nativo (factor 8.7x) | 2025-07-21T13:00 | 2025-07-23T01:00 | 0 | 636FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
638 | 1.2.4.5.7 | REACONDICIONAR MALLA | 60.0eh | 60 | 864.0h | 864 | Nativo (factor 14.4x) | 2025-07-23T01:00 | 2025-07-25T13:00 | 0 | 637FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
639 | 1.2.4.5.8 | LIMPIEZA INTERIOR | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-21T13:00 | 2025-07-24T01:00 | 0 | 636FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
640 | 1.2.4.5.9 | INSPECCION | 10.0eh | 10 | 1440.0h | 1440 | Nativo (factor 144.0x) | 2025-07-24T01:00 | 2025-07-24T11:00 | 0 | 639FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
641 | 1.2.4.5.10 | MONTAR MALLA | 20.0eh | 20 | 240.0h | 240 | Nativo (factor 12.0x) | 2025-07-25T13:00 | 2025-07-26T09:00 | 0 | 638FS; 640FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
642 | 1.2.4.5.11 | DESMONTAR ANDAMIO | 10.0eh | 10 | 480.0h | 480 | Nativo (factor 48.0x) | 2025-07-26T09:00 | 2025-07-26T19:00 | 0 | 641FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
643 | 1.2.4.5.12 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 240.0h | 240 | Nativo (factor 40.0x) | 2025-07-26T19:00 | 2025-07-27T01:00 | 0 | 642FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
644 | 1.2.4.5.13 | TAPAR PH | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-27T01:00 | 2025-07-27T13:00 | 0 | 643FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
645 | 1.2.4.5.14 | RETIRAR BC | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-27T13:00 | 2025-07-28T01:00 | 0 | 644FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
646 | 1.2.4.6 | F-652 | 9.868055555555555d | 236.8333 | 288.0h | 288 | Nativo (factor 1.2x) | 2025-07-18T12:00 | 2025-07-28T09:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | LARGO 5000mm x 1725 mm de diametro---H | 4
647 | 1.2.4.6.1 | COLOCAR BC | 11.0eh | 11 | 236.8h | 236.8333 | Nativo (corregido) | 2025-07-18T12:00 | 2025-07-18T23:00 | 0 | 633FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
648 | 1.2.4.6.2 | DESTAPAR PH | 10.0eh | 10 | 264.0h | 264 | Nativo (corregido) | 2025-07-18T23:00 | 2025-07-19T09:00 | 0 | 647FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
649 | 1.2.4.6.3 | VENTILACION | 36.0eh | 36 | 240.0h | 240 | Nativo (factor 6.7x) | 2025-07-19T09:00 | 2025-07-20T21:00 | 0 | 648FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
650 | 1.2.4.6.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 864.0h | 864 | Nativo (factor 216.0x) | 2025-07-20T21:00 | 2025-07-21T01:00 | 0 | 649FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
651 | 1.2.4.6.5 | LIMPIEZA INTERIOR | 72.0eh | 72 | 96.0h | 96 | Nativo (factor 1.3x) | 2025-07-24T01:00 | 2025-07-27T01:00 | 0 | 639FS; 650FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
652 | 1.2.4.6.6 | INSPECCION | 2.0eh | 2 | 1728.0h | 1728 | Nativo (factor 864.0x) | 2025-07-27T01:00 | 2025-07-27T03:00 | 0 | 651FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
653 | 1.2.4.6.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 48.0h | 48 | Nativo (factor 8.0x) | 2025-07-27T03:00 | 2025-07-27T09:00 | 0 | 652FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
654 | 1.2.4.6.8 | RETIRO ACCESO | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-07-27T09:00 | 2025-07-27T13:00 | 0 | 653FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
655 | 1.2.4.6.9 | TAPAR PH | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-07-27T13:00 | 2025-07-28T01:00 | 0 | 654FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
656 | 1.2.4.6.10 | RETIRAR BC | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-28T01:00 | 2025-07-28T09:00 | 0 | 655FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
657 | 1.2.4.7 | F-653 | 10.74236111111111d | 257.8167 | 192.0h | 192 | Nativo (factor 0.7x) | 2025-07-19T09:00 | 2025-07-30T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | LARGO 12000 X 2800 DE DIAMETRO--- H | 4
658 | 1.2.4.7.1 | COLOCAR BC | 10.0eh | 10 | 257.8h | 257.8167 | Nativo (corregido) | 2025-07-19T09:00 | 2025-07-19T19:00 | 0 | 648FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
659 | 1.2.4.7.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-19T19:00 | 2025-07-20T03:00 | 0 | 658FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
660 | 1.2.4.7.3 | VENTILACION | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-20T03:00 | 2025-07-22T03:00 | 0 | 659FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
661 | 1.2.4.7.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-22T03:00 | 2025-07-22T07:00 | 0 | 660FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
662 | 1.2.4.7.5 | LIMPIEZA INTERIOR | 48.0eh | 48 | 96.0h | 96 | Nativo (factor 2.0x) | 2025-07-27T01:00 | 2025-07-29T01:00 | 0 | 651FS; 661FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
663 | 1.2.4.7.6 | INSPECCION | 2.0eh | 2 | 1152.0h | 1152 | Nativo (factor 576.0x) | 2025-07-29T01:00 | 2025-07-29T03:00 | 0 | 662FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
664 | 1.2.4.7.7 | LIMPIEZA DE TOMAS | 4.0eh | 4 | 48.0h | 48 | Nativo (factor 12.0x) | 2025-07-29T03:00 | 2025-07-29T07:00 | 0 | 663FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
665 | 1.2.4.7.8 | RETIRO ACCESO | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-29T07:00 | 2025-07-29T13:00 | 0 | 664FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
666 | 1.2.4.7.9 | TAPAR PH | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-29T13:00 | 2025-07-29T19:00 | 0 | 665FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
667 | 1.2.4.7.10 | RETIRAR BC | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-07-29T19:00 | 2025-07-30T03:00 | 0 | 666FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
668 | 1.2.4.8 | F-654 | 1.582638888888889d | 37.9833 | 192.0h | 192 | Nativo (factor 5.1x) | 2025-07-20T03:00 | 2025-07-21T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | CARRETEL DE 8" | 4
669 | 1.2.4.8.1 | DESBRIDAR Y DESMONTAR | 12.0eh | 12 | 38.0h | 37.9833 | Nativo (factor 3.2x) | 2025-07-20T03:00 | 2025-07-20T15:00 | 0 | 659FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
670 | 1.2.4.8.2 | LIMPIEZA INTERIOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-20T15:00 | 2025-07-21T03:00 | 0 | 669FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
671 | 1.2.4.8.3 | INSPECCION | 2.0eh | 2 | 288.0h | 288 | Nativo (factor 144.0x) | 2025-07-21T03:00 | 2025-07-21T05:00 | 0 | 670FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
672 | 1.2.4.8.4 | MONTAR Y BRIDAR | 12.0eh | 12 | 48.0h | 48 | Nativo (factor 4.0x) | 2025-07-21T05:00 | 2025-07-21T17:00 | 0 | 671FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
673 | 1.2.4.9 | F-655 | 11.700694444444444d | 280.8167 | 11.700694444444444d | 280.8167 | MPXJ (validado) | 2025-07-20T03:00 | 2025-07-31T20:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | LTURA 3600mm diam. 1250 mmm V | 4
674 | 1.2.4.9.1 | COLOCAR BC | 8.0eh | 8 | 280.8h | 280.8167 | Nativo (factor 35.1x) | 2025-07-20T03:00 | 2025-07-20T11:00 | 0 | 659FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
675 | 1.2.4.9.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-20T11:00 | 2025-07-20T17:00 | 0 | 674FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
676 | 1.2.4.9.3 | VENTILACION /LUZ | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-20T17:00 | 2025-07-22T17:00 | 0 | 675FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
677 | 1.2.4.9.4 | MONTAR ANDAMIO INTERIOR | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-22T17:00 | 2025-07-22T21:00 | 0 | 676FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
678 | 1.2.4.9.5 | LIMPIEZA INTERIOR | 36.0eh | 36 | 96.0h | 96 | Nativo (factor 2.7x) | 2025-07-29T01:00 | 2025-07-30T13:00 | 0 | 662FS; 677FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
679 | 1.2.4.9.6 | INSPECCION | 3.0eh | 3 | 864.0h | 864 | Nativo (factor 288.0x) | 2025-07-30T13:00 | 2025-07-30T16:00 | 0 | 678FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
680 | 1.2.4.9.7 | DESMONTAR ANDAMIO | 6.0eh | 6 | 72.0h | 72 | Nativo (factor 12.0x) | 2025-07-30T16:00 | 2025-07-30T22:00 | 0 | 679FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
681 | 1.2.4.9.8 | LIMPIEZA DE TOMAS | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-07-30T22:00 | 2025-07-31T02:00 | 0 | 680FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
682 | 1.2.4.9.9 | TAPAR PH | 8.0eh | 8 | 96.0h | 96 | Nativo (factor 12.0x) | 2025-07-31T02:00 | 2025-07-31T10:00 | 0 | 681FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
683 | 1.2.4.9.10 | RETIRAR BC | 10.0eh | 10 | 192.0h | 192 | Nativo (factor 19.2x) | 2025-07-31T10:00 | 2025-07-31T20:00 | 0 | 682FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
684 | 1.2.4.10 | F-656 | 12.407638888888888d | 297.7833 | 12.407638888888888d | 297.7833 | MPXJ (validado) | 2025-07-20T17:00 | 2025-08-02T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | LARGO 8100mm diam.2000mm---- H | 4
685 | 1.2.4.10.1 | COLOCAR BC | 8.0eh | 8 | 297.8h | 297.7833 | Nativo (factor 37.2x) | 2025-07-20T17:00 | 2025-07-21T01:00 | 0 | 633FS; 675FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
686 | 1.2.4.10.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-21T01:00 | 2025-07-21T07:00 | 0 | 685FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
687 | 1.2.4.10.3 | VENTILACION | 36.0eh | 36 | 144.0h | 144 | Nativo (factor 4.0x) | 2025-07-21T07:00 | 2025-07-22T19:00 | 0 | 686FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
688 | 1.2.4.10.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 864.0h | 864 | Nativo (factor 216.0x) | 2025-07-22T19:00 | 2025-07-22T23:00 | 0 | 687FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
689 | 1.2.4.10.5 | LIMPIEZA INTERIOR | 36.0eh | 36 | 96.0h | 96 | Nativo (factor 2.7x) | 2025-07-30T13:00 | 2025-08-01T01:00 | 0 | 678FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
690 | 1.2.4.10.6 | INSPECCION | 2.0eh | 2 | 864.0h | 864 | Nativo (factor 432.0x) | 2025-08-01T01:00 | 2025-08-01T03:00 | 0 | 689FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
691 | 1.2.4.10.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 48.0h | 48 | Nativo (factor 8.0x) | 2025-08-01T03:00 | 2025-08-01T09:00 | 0 | 690FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
692 | 1.2.4.10.8 | RETIRO ACCESO | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-08-01T09:00 | 2025-08-01T13:00 | 0 | 691FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
693 | 1.2.4.10.9 | TAPAR PH | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-08-01T13:00 | 2025-08-01T19:00 | 0 | 692FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
694 | 1.2.4.10.10 | RETIRAR BC | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-08-01T19:00 | 2025-08-02T03:00 | 0 | 693FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
695 | 1.2.4.11 | F-658 | 3.6638888888888888d | 87.9333 | 192.0h | 192 | Nativo (factor 2.2x) | 2025-07-17T18:00 | 2025-07-21T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
696 | 1.2.4.11.1 | DESTAPAR SEPARADOR | 12.0eh | 12 | 87.9h | 87.9333 | Nativo (factor 7.3x) | 2025-07-17T18:00 | 2025-07-18T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
697 | 1.2.4.11.2 | LIMPIEZA INTERNA DESDE EL EXTERIOR | 48.0eh | 48 | 288.0h | 288 | Nativo (factor 6.0x) | 2025-07-18T06:00 | 2025-07-20T06:00 | 0 | 696FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
698 | 1.2.4.11.3 | REALIZAR END EXTERNOS | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-07-20T06:00 | 2025-07-20T18:00 | 0 | 697FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
699 | 1.2.4.11.4 | TAPAR SEPARADOR 8"-600 | 16.0eh | 16 | 288.0h | 288 | Nativo (factor 18.0x) | 2025-07-20T18:00 | 2025-07-21T10:00 | 0 | 698FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
700 | 1.2.4.12 | F-602 | 10.409027777777778d | 249.8167 | 384.0h | 384 | Nativo (factor 1.5x) | 2025-07-17T18:00 | 2025-07-28T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
701 | 1.2.4.12.1 | COLOCAR BC | 10.0eh | 10 | 249.8h | 249.8167 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
702 | 1.2.4.12.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T04:00 | 2025-07-18T12:00 | 0 | 701FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
703 | 1.2.4.12.3 | VENTILACION | 52.0eh | 52 | 192.0h | 192 | Nativo (factor 3.7x) | 2025-07-18T12:00 | 2025-07-20T16:00 | 0 | 702FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
704 | 1.2.4.12.4 | COLOCAR ACCESO/ LUZ | 6.0eh | 6 | 1248.0h | 1248 | Nativo (factor 208.0x) | 2025-07-20T16:00 | 2025-07-20T22:00 | 0 | 703FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
705 | 1.2.4.12.5 | LIMPIEZA INTERIOR | 60.0eh | 60 | 144.0h | 144 | Nativo (factor 2.4x) | 2025-07-20T22:00 | 2025-07-23T10:00 | 0 | 704FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
706 | 1.2.4.12.6 | INSPECCION | 72.0eh | 72 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-23T10:00 | 2025-07-26T10:00 | 0 | 705FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
707 | 1.2.4.12.7 | LIMPIEZA DE TOMAS | 8.0eh | 8 | 1728.0h | 1728 | Nativo (factor 216.0x) | 2025-07-26T10:00 | 2025-07-26T18:00 | 0 | 706FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
708 | 1.2.4.12.8 | RETIRO ACCESO | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-26T18:00 | 2025-07-27T02:00 | 0 | 707FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
709 | 1.2.4.12.9 | TAPAR PH | 12.0eh | 12 | 192.0h | 192 | Nativo (factor 16.0x) | 2025-07-27T02:00 | 2025-07-27T14:00 | 0 | 708FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
710 | 1.2.4.12.10 | RETIRAR BC | 14.0eh | 14 | 288.0h | 288 | Nativo (corregido) | 2025-07-27T14:00 | 2025-07-28T04:00 | 0 | 709FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
711 | 1.2.4.13 | F-607 | 5.6625d | 135.9 | 336.0h | 336 | Nativo (factor 2.5x) | 2025-07-17T18:00 | 2025-07-23T10:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
712 | 1.2.4.13.1 | COLOCAR BC | 8.0eh | 8 | 135.9h | 135.9 | Nativo (factor 17.0x) | 2025-07-17T18:00 | 2025-07-18T02:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
713 | 1.2.4.13.2 | DESTAPAR PH | 4.0eh | 4 | 192.0h | 192 | Nativo (factor 48.0x) | 2025-07-18T02:00 | 2025-07-18T06:00 | 0 | 712FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
714 | 1.2.4.13.3 | VENTILACION | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-07-18T06:00 | 2025-07-19T06:00 | 0 | 713FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
715 | 1.2.4.13.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-07-19T06:00 | 2025-07-19T10:00 | 0 | 714FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
716 | 1.2.4.13.5 | LIMPIEZA INTERIOR | 40.0eh | 40 | 96.0h | 96 | Nativo (factor 2.4x) | 2025-07-19T10:00 | 2025-07-21T02:00 | 0 | 715FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
717 | 1.2.4.13.6 | INSPECCION | 16.0eh | 16 | 960.0h | 960 | Nativo (factor 60.0x) | 2025-07-21T02:00 | 2025-07-21T18:00 | 0 | 716FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
718 | 1.2.4.13.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 384.0h | 384 | Nativo (factor 64.0x) | 2025-07-21T18:00 | 2025-07-22T00:00 | 0 | 717FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
719 | 1.2.4.13.8 | RETIRO ACCESO | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-22T00:00 | 2025-07-22T06:00 | 0 | 718FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
720 | 1.2.4.13.9 | TAPAR PH | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 719FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
721 | 1.2.4.13.10 | RETIRAR BC | 16.0eh | 16 | 288.0h | 288 | Nativo (factor 18.0x) | 2025-07-22T18:00 | 2025-07-23T10:00 | 0 | 720FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
722 | 1.2.4.14 | F-657 | 6.8284722222222225d | 163.8833 | 384.0h | 384 | Nativo (factor 2.3x) | 2025-07-17T18:00 | 2025-07-24T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
723 | 1.2.4.14.1 | COLOCAR BC | 8.0eh | 8 | 163.9h | 163.8833 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T02:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
724 | 1.2.4.14.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-18T02:00 | 2025-07-18T08:00 | 0 | 723FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
725 | 1.2.4.14.3 | VENTILACION | 36.0eh | 36 | 144.0h | 144 | Nativo (factor 4.0x) | 2025-07-18T08:00 | 2025-07-19T20:00 | 0 | 724FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
726 | 1.2.4.14.4 | COLOCAR ACCESO/ LUZ | 6.0eh | 6 | 864.0h | 864 | Nativo (factor 144.0x) | 2025-07-19T20:00 | 2025-07-20T02:00 | 0 | 725FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
727 | 1.2.4.14.5 | LIMPIEZA INTERIOR | 50.0eh | 50 | 144.0h | 144 | Nativo (factor 2.9x) | 2025-07-20T02:00 | 2025-07-22T04:00 | 0 | 726FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
728 | 1.2.4.14.6 | INSPECCION | 20.0eh | 20 | 1200.0h | 1200 | Nativo (factor 60.0x) | 2025-07-22T04:00 | 2025-07-23T00:00 | 0 | 727FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
729 | 1.2.4.14.7 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 480.0h | 480 | Nativo (factor 80.0x) | 2025-07-23T00:00 | 2025-07-23T06:00 | 0 | 728FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
730 | 1.2.4.14.8 | RETIRO ACCESO | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-23T06:00 | 2025-07-23T12:00 | 0 | 729FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
731 | 1.2.4.14.9 | TAPAR PH | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-23T12:00 | 2025-07-24T00:00 | 0 | 730FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
732 | 1.2.4.14.10 | RETIRAR BC | 14.0eh | 14 | 288.0h | 288 | Nativo (corregido) | 2025-07-24T00:00 | 2025-07-24T14:00 | 0 | 731FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
733 | 1.2.4.15 | F-660 | 9.243055555555555d | 221.8333 | 336.0h | 336 | Nativo (factor 1.5x) | 2025-07-17T18:00 | 2025-07-27T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
734 | 1.2.4.15.1 | COLOCAR BC | 10.0eh | 10 | 221.8h | 221.8333 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
735 | 1.2.4.15.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T04:00 | 2025-07-18T12:00 | 0 | 734FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
736 | 1.2.4.15.3 | VENTILACION | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-18T12:00 | 2025-07-20T12:00 | 0 | 735FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
737 | 1.2.4.15.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-20T12:00 | 2025-07-20T16:00 | 0 | 736FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
738 | 1.2.4.15.5 | LIMPIEZA INTERIOR | 90.0eh | 90 | 90.0eh | 90 | MPXJ (validado) | 2025-07-20T16:00 | 2025-07-24T10:00 | 0 | 737FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
739 | 1.2.4.15.6 | INSPECCION | 24.0eh | 24 | 2160.0h | 2160 | Nativo (factor 90.0x) | 2025-07-24T10:00 | 2025-07-25T10:00 | 0 | 738FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
740 | 1.2.4.15.7 | LIMPIEZA DE TOMAS | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-07-25T10:00 | 2025-07-25T14:00 | 0 | 739FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
741 | 1.2.4.15.8 | RETIRO ACCESO | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-25T14:00 | 2025-07-25T20:00 | 0 | 740FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
742 | 1.2.4.15.9 | TAPAR PH | 16.0eh | 16 | 144.0h | 144 | Nativo (factor 9.0x) | 2025-07-25T20:00 | 2025-07-26T12:00 | 0 | 741FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
743 | 1.2.4.15.10 | RETIRAR BC | 12.0eh | 12 | 384.0h | 384 | Nativo (factor 32.0x) | 2025-07-26T12:00 | 2025-07-27T00:00 | 0 | 742FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
744 | 1.2.4.16 | F-661 | 12.532638888888888d | 300.7833 | 12.532638888888888d | 300.7833 | MPXJ (validado) | 2025-07-17T18:00 | 2025-07-30T07:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
745 | 1.2.4.16.1 | INSTALAR DISCOS CIEGOS | 10.0eh | 10 | 300.8h | 300.7833 | Nativo (factor 30.1x) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
746 | 1.2.4.16.2 | DESTAPAR PH | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-18T04:00 | 2025-07-18T12:00 | 0 | 745FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
747 | 1.2.4.16.3 | VENTILACION | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-18T12:00 | 2025-07-20T00:00 | 0 | 746FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
748 | 1.2.4.16.4 | DESBRIDAR Y DESM.CASQUETE 36" | 8.0eh | 8 | 864.0h | 864 | Nativo (factor 108.0x) | 2025-07-20T00:00 | 2025-07-20T08:00 | 0 | 747FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
749 | 1.2.4.16.5 | LIMPIEZA DE CONTACTOR | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-20T08:00 | 2025-07-21T20:00 | 0 | 748FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
750 | 1.2.4.16.6 | MONTAJE DE ANDAMIO INTERNO | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-21T20:00 | 2025-07-22T08:00 | 0 | 749FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
751 | 1.2.4.16.7 | LIMPIEZA INTERNA TOTAL | 74.0eh | 74 | 288.0h | 288 | Nativo (factor 3.9x) | 2025-07-22T08:00 | 2025-07-25T10:00 | 0 | 750FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
752 | 1.2.4.16.8 | INSPECCION | 8.0eh | 8 | 1776.0h | 1776 | Nativo (factor 222.0x) | 2025-07-25T10:00 | 2025-07-25T18:00 | 0 | 751FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
753 | 1.2.4.16.9 | REPARACION DE INTERNOS | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-25T18:00 | 2025-07-27T06:00 | 0 | 752FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
754 | 1.2.4.16.10 | DESMONTAR ANDAMIO INTERNO | 25.0eh | 25 | 864.0h | 864 | Nativo (factor 34.6x) | 2025-07-27T06:00 | 2025-07-28T07:00 | 0 | 753FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
755 | 1.2.4.16.11 | LIMPIEZA FINA | 6.0eh | 6 | 600.0h | 600 | Nativo (factor 100.0x) | 2025-07-28T07:00 | 2025-07-28T13:00 | 0 | 754FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
756 | 1.2.4.16.12 | MONTAR Y BRIDAR CASQUETE CONTACTOR | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-28T13:00 | 2025-07-29T01:00 | 0 | 755FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
757 | 1.2.4.16.13 | INSPECCION Y LIMPIEZA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-29T01:00 | 2025-07-29T13:00 | 0 | 756FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
758 | 1.2.4.16.14 | TAPAR PH | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-29T13:00 | 2025-07-29T21:00 | 0 | 757FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
759 | 1.2.4.16.15 | RETIRAR DISCOS CIEGOS | 10.0eh | 10 | 192.0h | 192 | Nativo (factor 19.2x) | 2025-07-29T21:00 | 2025-07-30T07:00 | 0 | 758FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
760 | 1.2.4.17 | F-662 | 13.157638888888888d | 315.7833 | 240.0h | 240 | Nativo (factor 0.8x) | 2025-07-17T18:00 | 2025-07-30T22:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
761 | 1.2.4.17.1 | INSTALAR DISCOS CIEGOS | 10.0eh | 10 | 315.8h | 315.7833 | Nativo (factor 31.6x) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
762 | 1.2.4.17.2 | DESTAPAR PH | 12.0eh | 12 | 240.0h | 240 | Nativo (corregido) | 2025-07-18T04:00 | 2025-07-18T16:00 | 0 | 761FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
763 | 1.2.4.17.3 | VENTILACION | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-18T16:00 | 2025-07-20T04:00 | 0 | 762FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
764 | 1.2.4.17.4 | DESBRIDAR Y DESM.CASQUETE | 8.0eh | 8 | 864.0h | 864 | Nativo (factor 108.0x) | 2025-07-20T04:00 | 2025-07-20T12:00 | 0 | 763FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
765 | 1.2.4.17.5 | LIMPIEZA DE CONTACTOR | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-20T12:00 | 2025-07-22T00:00 | 0 | 764FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
766 | 1.2.4.17.6 | MONTAJE DE ANDAMIO INTERNO | 8.0eh | 8 | 864.0h | 864 | Nativo (factor 108.0x) | 2025-07-22T00:00 | 2025-07-22T08:00 | 0 | 765FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
767 | 1.2.4.17.7 | LIMPIEZA INTERNA TOTAL | 72.0eh | 72 | 192.0h | 192 | Nativo (factor 2.7x) | 2025-07-22T08:00 | 2025-07-25T08:00 | 0 | 766FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
768 | 1.2.4.17.8 | INSPECCION | 24.0eh | 24 | 1728.0h | 1728 | Nativo (factor 72.0x) | 2025-07-25T08:00 | 2025-07-26T08:00 | 0 | 767FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
769 | 1.2.4.17.9 | REPARACION DE INTERNOS | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-26T08:00 | 2025-07-27T20:00 | 0 | 768FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
770 | 1.2.4.17.10 | DESMONTAR ANDAMIO INTERNO | 20.0eh | 20 | 864.0h | 864 | Nativo (factor 43.2x) | 2025-07-27T20:00 | 2025-07-28T16:00 | 0 | 769FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
771 | 1.2.4.17.11 | LIMPIEZA FINA | 24.0eh | 24 | 480.0h | 480 | Nativo (corregido) | 2025-07-28T16:00 | 2025-07-29T16:00 | 0 | 770FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
772 | 1.2.4.17.12 | MONTAR Y BRIDAR CASQUETE CONTACTOR | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-29T16:00 | 2025-07-30T00:00 | 0 | 771FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
773 | 1.2.4.17.13 | DESMONTAR ILUMINACION | 4.0eh | 4 | 192.0h | 192 | Nativo (factor 48.0x) | 2025-07-30T00:00 | 2025-07-30T04:00 | 0 | 772FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
774 | 1.2.4.17.14 | TAPAR PH | 8.0eh | 8 | 96.0h | 96 | Nativo (factor 12.0x) | 2025-07-30T04:00 | 2025-07-30T12:00 | 0 | 773FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
775 | 1.2.4.17.15 | RETIRAR DISCOS CIEGOS | 10.0eh | 10 | 192.0h | 192 | Nativo (factor 19.2x) | 2025-07-30T12:00 | 2025-07-30T22:00 | 0 | 774FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
776 | 1.2.4.18 | F-675 | 14.573611111111111d | 349.7667 | 240.0h | 240 | Nativo (factor 0.7x) | 2025-07-21T01:00 | 2025-08-04T15:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | ACUMULADOR GRANDE DE VAPOR GRANDE CON 3 MALLAS | 4
777 | 1.2.4.18.1 | COLOCAR BC | 8.0eh | 8 | 349.8h | 349.7667 | Nativo (factor 43.7x) | 2025-07-21T01:00 | 2025-07-21T09:00 | 0 | 685FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
778 | 1.2.4.18.2 | DESTAPAR PH 24"-600# | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-21T09:00 | 2025-07-21T15:00 | 0 | 777FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
779 | 1.2.4.18.3 | VENTILACION | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-21T15:00 | 2025-07-22T03:00 | 0 | 778FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
780 | 1.2.4.18.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-22T03:00 | 2025-07-22T07:00 | 0 | 779FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
781 | 1.2.4.18.5 | DESMONTAR 3 MALLAS | 30.0eh | 30 | 96.0h | 96 | Nativo (factor 3.2x) | 2025-07-22T07:00 | 2025-07-23T13:00 | 0 | 780FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
782 | 1.2.4.18.6 | LIMPIEZA INTERIOR | 24.0eh | 24 | 720.0h | 720 | Nativo (factor 30.0x) | 2025-08-01T01:00 | 2025-08-02T01:00 | 0 | 689FS; 781FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
783 | 1.2.4.18.7 | LIMPIEZA MALLAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-23T13:00 | 2025-07-24T13:00 | 0 | 781FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
784 | 1.2.4.18.8 | INSPECCION MALLAS | 2.0eh | 2 | 576.0h | 576 | Nativo (factor 288.0x) | 2025-07-24T13:00 | 2025-07-24T15:00 | 0 | 783FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
785 | 1.2.4.18.9 | REPARAR MALLAS | 36.0eh | 36 | 48.0h | 48 | Nativo (factor 1.3x) | 2025-07-24T15:00 | 2025-07-26T03:00 | 0 | 784FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
786 | 1.2.4.18.10 | MONTAR MALLAS | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-08-02T01:00 | 2025-08-03T13:00 | 0 | 782FS; 785FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
787 | 1.2.4.18.11 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 864.0h | 864 | Nativo (factor 144.0x) | 2025-08-03T13:00 | 2025-08-03T19:00 | 0 | 786FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
788 | 1.2.4.18.12 | INSPECCION ENVOLVENTE | 2.0eh | 2 | 144.0h | 144 | Nativo (factor 72.0x) | 2025-08-03T19:00 | 2025-08-03T21:00 | 0 | 787FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
789 | 1.2.4.18.13 | RETIRO DE ACCESO | 4.0eh | 4 | 48.0h | 48 | Nativo (factor 12.0x) | 2025-08-03T21:00 | 2025-08-04T01:00 | 0 | 788FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
790 | 1.2.4.18.14 | TAPAR PH- 24"- 600# | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-08-04T01:00 | 2025-08-04T07:00 | 0 | 789FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
791 | 1.2.4.18.15 | RETIRAR BC | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-08-04T07:00 | 2025-08-04T15:00 | 0 | 790FS; 801FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
792 | 1.2.4.19 | F-676 | 12.657638888888888d | 303.7833 | 192.0h | 192 | Nativo (factor 0.6x) | 2025-07-21T15:00 | 2025-08-03T07:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | ACUMULADOR MEDIANO DE VAPOR GRANDE CON 3 MALLAS | 4
793 | 1.2.4.19.1 | COLOCAR CIEGOS | 18.0eh | 18 | 303.8h | 303.7833 | Nativo (factor 16.9x) | 2025-07-21T15:00 | 2025-07-22T09:00 | 0 | 778FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
794 | 1.2.4.19.2 | DESTAPAR PH | 6.0eh | 6 | 432.0h | 432 | Nativo (factor 72.0x) | 2025-07-22T09:00 | 2025-07-22T15:00 | 0 | 793FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
795 | 1.2.4.19.3 | VENTILACION | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-22T15:00 | 2025-07-23T03:00 | 0 | 794FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
796 | 1.2.4.19.4 | COLOCAR ACCESO/ LUZ | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-23T03:00 | 2025-07-23T07:00 | 0 | 795FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
797 | 1.2.4.19.5 | LIMPIEZA INTERIOR | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-08-01T01:00 | 2025-08-02T01:00 | 0 | 689FS; 796FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
798 | 1.2.4.19.6 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 576.0h | 576 | Nativo (factor 96.0x) | 2025-08-02T01:00 | 2025-08-02T07:00 | 0 | 797FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
799 | 1.2.4.19.7 | INSPECCION ENVOLVENTE | 2.0eh | 2 | 144.0h | 144 | Nativo (factor 72.0x) | 2025-08-02T07:00 | 2025-08-02T09:00 | 0 | 798FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
800 | 1.2.4.19.8 | RETIRO DE ACCESO | 4.0eh | 4 | 48.0h | 48 | Nativo (factor 12.0x) | 2025-08-02T09:00 | 2025-08-02T13:00 | 0 | 799FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
801 | 1.2.4.19.9 | TAPAR PH | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-08-02T13:00 | 2025-08-02T19:00 | 0 | 800FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
802 | 1.2.4.19.10 | RETIRAR CIEGOS | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-08-02T19:00 | 2025-08-03T07:00 | 0 | 801FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
803 | 1.2.4.20 | F-672 (TOLVA DE CAT) | 8.36875d | 200.85 | 288.0h | 288 | Nativo (factor 1.4x) | 2025-07-16T18:00 | 2025-07-25T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 150000 50000 | 4
804 | 1.2.4.20.1 | ARMAR ANDAMIO EXTERIOR | 36.0eh | 36 | 200.8h | 200.85 | Nativo (factor 5.6x) | 2025-07-16T18:00 | 2025-07-18T06:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
805 | 1.2.4.20.2 | REALIZAR DESCARGA DE CAT. | 94.0eh | 94 | 864.0h | 864 | Nativo (factor 9.2x) | 2025-07-16T18:00 | 2025-07-20T16:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
806 | 1.2.4.20.3 | ABRIR PH | 12.0eh | 12 | 2256.0h | 2256 | Nativo (factor 188.0x) | 2025-07-20T16:00 | 2025-07-21T04:00 | 0 | 805FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | ESTA ESTIMACION ESTA HECHA CON POCO VOLUMEN DE CATALIZADOR | 5
807 | 1.2.4.20.4 | INSPECCION | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-21T04:00 | 2025-07-21T16:00 | 0 | 806FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
808 | 1.2.4.20.5 | TAPAR PH | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-21T16:00 | 2025-07-22T04:00 | 0 | 807FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
809 | 1.2.4.20.6 | CARGAR CATALIZADOR | 45.0eh | 45 | 288.0h | 288 | Nativo (factor 6.4x) | 2025-07-23T06:00 | 2025-07-25T03:00 | 0 | 808FS; 813FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
810 | 1.2.4.20.7 | LPZA CORDONES DE SOLDADURA EXTERIOR | 36.0eh | 36 | 1080.0h | 1080 | Nativo (factor 30.0x) | 2025-07-18T06:00 | 2025-07-19T18:00 | 0 | 804FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
811 | 1.2.4.20.8 | INSPECCION EXTERIOR | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-19T18:00 | 2025-07-20T18:00 | 0 | 810FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
812 | 1.2.4.20.9 | DESARMAR ANDAMIO | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-20T18:00 | 2025-07-22T06:00 | 0 | 811FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
813 | 1.2.4.20.10 | RETIRO DE BC | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-22T06:00 | 2025-07-23T06:00 | 0 | 812FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
814 | 1.2.4.21 | F-674 (TOLVA DE CAT.) | 10.49236111111111d | 251.8167 | 576.0h | 576 | Nativo (factor 2.3x) | 2025-07-20T16:00 | 2025-07-31T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 10000 mm 2896 mm tiene un ciclon en parte superior | 4
815 | 1.2.4.21.1 | COLOCAR CIEGOS | 12.0eh | 12 | 251.8h | 251.8167 | Nativo (corregido) | 2025-07-20T16:00 | 2025-07-21T04:00 | 0 | 805FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
816 | 1.2.4.21.2 | DESCARGA DE REMANENTE | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-21T04:00 | 2025-07-22T16:00 | 0 | 815FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | ESTA ESTIMACION ESTA HECHA CON POCO VOLUMEN DE CATALIZADOR | 5
817 | 1.2.4.21.3 | DESTAPAR PH | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-22T16:00 | 2025-07-23T04:00 | 0 | 816FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
818 | 1.2.4.21.4 | ILUMINACION INTERNA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-23T04:00 | 2025-07-23T16:00 | 0 | 817FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
819 | 1.2.4.21.5 | MONTAR ANDAMIO INTERNO | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-23T16:00 | 2025-07-24T16:00 | 0 | 818FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
820 | 1.2.4.21.6 | LIMPIEZA DEL EQUIPO | 60.0eh | 60 | 576.0h | 576 | Nativo (factor 9.6x) | 2025-07-24T16:00 | 2025-07-27T04:00 | 0 | 819FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
821 | 1.2.4.21.7 | LIMPIEZA DE CORDONES DE SOLDADURA | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-27T04:00 | 2025-07-28T16:00 | 0 | 820FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
822 | 1.2.4.21.8 | INSPECCION | 4.0eh | 4 | 864.0h | 864 | Nativo (factor 216.0x) | 2025-07-28T16:00 | 2025-07-28T20:00 | 0 | 820FS; 821FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
823 | 1.2.4.21.9 | REPARACION DE INTERNOS | 24.0eh | 24 | 96.0h | 96 | Nativo (factor 4.0x) | 2025-07-28T20:00 | 2025-07-29T20:00 | 0 | 822FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
824 | 1.2.4.21.10 | DESARMAR ANDAMIO | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-29T20:00 | 2025-07-30T08:00 | 0 | 823FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
825 | 1.2.4.21.11 | RETIRAR ILUMINACION | 4.0eh | 4 | 288.0h | 288 | Nativo (factor 72.0x) | 2025-07-30T08:00 | 2025-07-30T12:00 | 0 | 824FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
826 | 1.2.4.21.12 | TAPAR PASAHOMBRES | 8.0eh | 8 | 96.0h | 96 | Nativo (factor 12.0x) | 2025-07-30T12:00 | 2025-07-30T20:00 | 0 | 825FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
827 | 1.2.4.21.13 | RETIRAR DISCOS CIEGOS | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-30T20:00 | 2025-07-31T04:00 | 0 | 826FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
828 | 1.2.4.22 | F-677 | 7.745138888888889d | 185.8833 | 7.745138888888889d | 185.8833 | MPXJ (validado) | 2025-07-23T04:00 | 2025-07-30T22:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 3000 1400 Ø DOSIFICADOR DE CATALIZADOR CHICO CON 1 MALLA | 4
829 | 1.2.4.22.1 | COLOCAR BC | 8.0eh | 8 | 185.9h | 185.8833 | Nativo (corregido) | 2025-07-23T04:00 | 2025-07-23T12:00 | 0 | 815FS; 817FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
830 | 1.2.4.22.2 | DESTAPAR PH | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-23T12:00 | 2025-07-23T18:00 | 0 | 829FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
831 | 1.2.4.22.3 | DESMONTAR MALLA | 30.0eh | 30 | 144.0h | 144 | Nativo (factor 4.8x) | 2025-07-23T18:00 | 2025-07-25T00:00 | 0 | 830FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
832 | 1.2.4.22.4 | LIMPIEZA INTERIOR | 24.0eh | 24 | 720.0h | 720 | Nativo (factor 30.0x) | 2025-07-25T00:00 | 2025-07-26T00:00 | 0 | 831FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
833 | 1.2.4.22.5 | LIMPIEZA MALLA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-26T00:00 | 2025-07-27T00:00 | 0 | 832FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
834 | 1.2.4.22.6 | INSPECCION | 2.0eh | 2 | 576.0h | 576 | Nativo (factor 288.0x) | 2025-07-27T00:00 | 2025-07-27T02:00 | 0 | 833FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
835 | 1.2.4.22.7 | REPARAR MALLA | 36.0eh | 36 | 48.0h | 48 | Nativo (factor 1.3x) | 2025-07-27T02:00 | 2025-07-28T14:00 | 0 | 834FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
836 | 1.2.4.22.8 | MONTAR MALLA | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-28T14:00 | 2025-07-30T02:00 | 0 | 835FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
837 | 1.2.4.22.9 | LIMPIEZA DE TOMAS | 6.0eh | 6 | 864.0h | 864 | Nativo (factor 144.0x) | 2025-07-30T02:00 | 2025-07-30T08:00 | 0 | 836FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
838 | 1.2.4.22.10 | TAPAR PH- | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-30T08:00 | 2025-07-30T14:00 | 0 | 837FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
839 | 1.2.4.22.11 | RETIRAR BC | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-07-30T14:00 | 2025-07-30T22:00 | 0 | 838FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
840 | 1.2.4.23 | G-602 (SEPARADORES) | 2.747916666666667d | 65.95 | 192.0h | 192 | Nativo (factor 2.9x) | 2025-07-21T17:00 | 2025-07-24T11:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
841 | 1.2.4.23.1 | DESTAPAR SEPARADOR 8"-600 | 6.0eh | 6 | 66.0h | 65.95 | Nativo (factor 11.0x) | 2025-07-21T17:00 | 2025-07-21T23:00 | 0 | 672FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
842 | 1.2.4.23.2 | LIMPIEZA INTERNA DESDE EL EXTERIOR | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-21T23:00 | 2025-07-22T23:00 | 0 | 841FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
843 | 1.2.4.23.3 | REALIZAR END EXTERNOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T23:00 | 2025-07-23T23:00 | 0 | 842FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
844 | 1.2.4.23.4 | TAPAR SEPARADOR 8"-600 | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-23T23:00 | 2025-07-24T11:00 | 0 | 843FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
845 | 1.2.4.24 | G-603 (SEPARADORES) | 2.747916666666667d | 65.95 | 288.0h | 288 | Nativo (factor 4.4x) | 2025-07-24T11:00 | 2025-07-27T05:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
846 | 1.2.4.24.1 | DESTAPAR SEPARADOR 8"-600 | 6.0eh | 6 | 66.0h | 65.95 | Nativo (factor 11.0x) | 2025-07-24T11:00 | 2025-07-24T17:00 | 0 | 844FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
847 | 1.2.4.24.2 | LIMPIEZA INTERNA DESDE EL EXTERIOR | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-24T17:00 | 2025-07-25T17:00 | 0 | 846FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
848 | 1.2.4.24.3 | REALIZAR END EXTERNOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-25T17:00 | 2025-07-26T17:00 | 0 | 847FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
849 | 1.2.4.24.4 | TAPAR SEPARADOR 8"-600 | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-26T17:00 | 2025-07-27T05:00 | 0 | 848FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
850 | 1.2.4.25 | G-605 (SEPARADORES) | 2.9145833333333333d | 69.95 | 288.0h | 288 | Nativo (factor 4.1x) | 2025-07-27T05:00 | 2025-07-30T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
851 | 1.2.4.25.1 | DESTAPAR SEPARADOR 8"-600 | 10.0eh | 10 | 70.0h | 69.95 | Nativo (factor 7.0x) | 2025-07-27T05:00 | 2025-07-27T15:00 | 0 | 849FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
852 | 1.2.4.25.2 | LIMPIEZA INTERNA DESDE EL EXTERIOR | 24.0eh | 24 | 240.0h | 240 | Nativo (factor 10.0x) | 2025-07-27T15:00 | 2025-07-28T15:00 | 0 | 851FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
853 | 1.2.4.25.3 | REALIZAR END EXTERNOS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-28T15:00 | 2025-07-29T15:00 | 0 | 852FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
854 | 1.2.4.25.4 | TAPAR SEPARADOR 8"-600 | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-29T15:00 | 2025-07-30T03:00 | 0 | 853FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
855 | 1.2.5 | INTERCAMBIADORES - 55 - | 18.986805555555556d | 455.6833 | 288.0h | 288 | Nativo (factor 0.6x) | 2025-07-17T18:00 | 2025-08-05T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
856 | 1.2.5.1 | CEGADO Y DESARME | 7.9944444444444445d | 191.8667 | 455.7h | 455.6833 | Nativo (factor 2.4x) | 2025-07-17T18:00 | 2025-07-25T18:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
857 | 1.2.5.1.1 | C-602 ABCD (1010 3/4") | 60.0eh | 60 | 191.9h | 191.8667 | Nativo (factor 3.2x) | 2025-07-17T18:00 | 2025-07-20T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
858 | 1.2.5.1.2 | C-603 (62T 3/4") | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-17T18:00 | 2025-07-18T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
859 | 1.2.5.1.3 | C-605 (1610-3/4") | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-20T06:00 | 2025-07-22T06:00 | 0 | 6FS; 886FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
860 | 1.2.5.1.4 | C-611 A (870 3/4") C | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
861 | 1.2.5.1.5 | C-611 B (870 3/4") C | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-21T18:00 | 0 | 860FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
862 | 1.2.5.1.6 | C-614- ( 1414 / 3/4") C | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
863 | 1.2.5.1.7 | C-616 (380 3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
864 | 1.2.5.1.8 | C-617 A/ B (158-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
865 | 1.2.5.1.9 | C-619 A-B(116 /3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
866 | 1.2.5.1.10 | C-655 (459-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
867 | 1.2.5.1.11 | C-J675 (2244--3/4")CONDENSADOR | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
868 | 1.2.5.1.12 | C-J671 (3001 -3/4) CONDENSADOR | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
869 | 1.2.5.1.13 | C-J675-5A/B (80--3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
870 | 1.2.5.1.14 | C-J671-5A/B (80 -3/4) | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-21T18:00 | 0 | 869FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
871 | 1.2.5.1.15 | C-607 A/B/C (676 3/4") | 72.0eh | 72 | 1152.0h | 1152 | Nativo (factor 16.0x) | 2025-07-17T18:00 | 2025-07-20T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
872 | 1.2.5.1.16 | C-607 D/E/F (676 3/4") | 72.0eh | 72 | 1728.0h | 1728 | Nativo (corregido) | 2025-07-20T18:00 | 2025-07-23T18:00 | 0 | 871FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
873 | 1.2.5.1.17 | C-604 A/B (197-3/4") | 48.0eh | 48 | 1728.0h | 1728 | Nativo (factor 36.0x) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
874 | 1.2.5.1.18 | C-612 A/B (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
875 | 1.2.5.1.19 | C-612 C/ D (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-21T18:00 | 0 | 874FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
876 | 1.2.5.1.20 | C-658 (510 T 3/4) | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
877 | 1.2.5.1.21 | C-656 A/B/C/D/E/F (880 T 3/4) | 144.0eh | 144 | 1152.0h | 1152 | Nativo (factor 8.0x) | 2025-07-19T18:00 | 2025-07-25T18:00 | 0 | 866FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
878 | 1.2.5.1.22 | C-653 | 48.0eh | 48 | 3456.0h | 3456 | Nativo (factor 72.0x) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
879 | 1.2.5.1.23 | C-659 (118-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
880 | 1.2.5.1.24 | C-660 ABC (1020-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
881 | 1.2.5.1.25 | C-662 (325 3/4") adecuacion cunas | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
882 | 1.2.5.1.26 | C-663 (62 U-3/4") adecuacion cunas | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
883 | 1.2.5.1.27 | C-665 A/B (128-3/4") | 53.0eh | 53 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T23:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
884 | 1.2.5.1.28 | C-668 (712-3/4") | 48.0eh | 48 | 1272.0h | 1272 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
885 | 1.2.5.1.29 | C-615 (3P)CAJA ENFRIADORAS | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
886 | 1.2.5.1.30 | C-666 ABCD (912 T ) | 60.0eh | 60 | 1152.0h | 1152 | Nativo (factor 19.2x) | 2025-07-17T18:00 | 2025-07-20T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
887 | 1.2.5.1.31 | C-661 (20 T3/4") | 48.0eh | 48 | 1440.0h | 1440 | Nativo (factor 30.0x) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
888 | 1.2.5.2 | LAVADO | 10.49236111111111d | 251.8167 | 1152.0h | 1152 | Nativo (factor 4.6x) | 2025-07-18T18:00 | 2025-07-29T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
889 | 1.2.5.2.1 | C-602 ABCD (1010 3/4") | 72.0eh | 72 | 251.8h | 251.8167 | Nativo (factor 3.5x) | 2025-07-20T06:00 | 2025-07-23T06:00 | 0 | 857FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
890 | 1.2.5.2.2 | C-603 (62T 3/4") | 60.0eh | 60 | 1728.0h | 1728 | Nativo (factor 28.8x) | 2025-07-18T18:00 | 2025-07-21T06:00 | 0 | 858FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
891 | 1.2.5.2.3 | C-605 (1610-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-24T18:00 | 0 | 859FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
892 | 1.2.5.2.4 | C-611 A (870 3/4") C | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 860FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
893 | 1.2.5.2.5 | C-611 B (870 3/4") C | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-21T18:00 | 2025-07-24T06:00 | 0 | 861FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
894 | 1.2.5.2.6 | C-614- ( 1414 / 3/4") C | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 862FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
895 | 1.2.5.2.7 | C-616 (380 3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 863FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
896 | 1.2.5.2.8 | C-617 A/ B (158-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 864FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
897 | 1.2.5.2.9 | C-619 A-B(116 /3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 865FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
898 | 1.2.5.2.10 | C-655 (459-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 866FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
899 | 1.2.5.2.11 | C-J675 (2244--3/4")CONDENSADOR | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 867FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
900 | 1.2.5.2.12 | C-J671 (3001 -3/4) CONDENSADOR | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 868FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
901 | 1.2.5.2.13 | C-J675-5A/B (80--3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 869FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
902 | 1.2.5.2.14 | C-J671-5A/B (80 -3/4) | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-21T18:00 | 2025-07-24T06:00 | 0 | 870FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
903 | 1.2.5.2.15 | C-607 A/B/C (676 3/4") | 72.0eh | 72 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-20T18:00 | 2025-07-23T18:00 | 0 | 871FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
904 | 1.2.5.2.16 | C-607 D/E/F (676 3/4") | 72.0eh | 72 | 1728.0h | 1728 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-26T18:00 | 0 | 872FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
905 | 1.2.5.2.17 | C-604 A/B (197-3/4") | 60.0eh | 60 | 1728.0h | 1728 | Nativo (factor 28.8x) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 873FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
906 | 1.2.5.2.18 | C-612 A/B (56-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 874FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
907 | 1.2.5.2.19 | C-612 C/ D (56-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-21T18:00 | 2025-07-24T06:00 | 0 | 875FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
908 | 1.2.5.2.20 | C-658 (510 T 3/4) | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 876FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
909 | 1.2.5.2.21 | C-656 A/B/C/D (880 T 3/4) | 72.0eh | 72 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-25T18:00 | 2025-07-28T18:00 | 0 | 877FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
910 | 1.2.5.2.22 | C-653 | 60.0eh | 60 | 1728.0h | 1728 | Nativo (factor 28.8x) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 878FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
911 | 1.2.5.2.23 | C-659 (118-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 879FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
912 | 1.2.5.2.24 | C-660 ABC (1020-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 880FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
913 | 1.2.5.2.25 | C-662 (325 3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 881FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
914 | 1.2.5.2.26 | C-663 (62 U-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 882FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
915 | 1.2.5.2.27 | C-665 A/B (128-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T23:00 | 2025-07-22T11:00 | 0 | 883FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
916 | 1.2.5.2.28 | C-668 (712-3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 884FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
917 | 1.2.5.2.29 | C-615 (3P)CAJA ENFRIADORAS | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 885FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
918 | 1.2.5.2.30 | C-666 ABCD (912 T ) | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-20T06:00 | 2025-07-22T18:00 | 0 | 886FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
919 | 1.2.5.2.31 | C-661 (20 T3/4") | 60.0eh | 60 | 1440.0h | 1440 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-22T06:00 | 0 | 887FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
920 | 1.2.5.2.32 | INSPECCION | 7.9944444444444445d | 191.8667 | 1440.0h | 1440 | Nativo (factor 7.5x) | 2025-07-21T06:00 | 2025-07-29T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
921 | 1.2.5.2.32.1 | C-602 ABCD (1010 3/4") | 12.0eh | 12 | 191.9h | 191.8667 | Nativo (factor 16.0x) | 2025-07-23T06:00 | 2025-07-23T18:00 | 0 | 889FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
922 | 1.2.5.2.32.2 | C-603 (62T 3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-21T06:00 | 2025-07-21T18:00 | 0 | 890FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
923 | 1.2.5.2.32.3 | C-605 (1610-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-24T18:00 | 2025-07-25T06:00 | 0 | 891FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
924 | 1.2.5.2.32.4 | C-611 A (870 3/4") C | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 892FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
925 | 1.2.5.2.32.5 | C-611 B (870 3/4") C | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-24T06:00 | 2025-07-24T18:00 | 0 | 893FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
926 | 1.2.5.2.32.6 | C-614- ( 1414 / 3/4") C | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 894FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
927 | 1.2.5.2.32.7 | C-616 (380 3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 895FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
928 | 1.2.5.2.32.8 | C-617 A/ B (158-3/4") | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-22T06:00 | 2025-07-23T06:00 | 0 | 896FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
929 | 1.2.5.2.32.9 | C-619 A-B(116 /3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-23T06:00 | 0 | 897FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
930 | 1.2.5.2.32.10 | C-655 (459-3/4") | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 898FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
931 | 1.2.5.2.32.11 | C-J675 (2244--3/4")CONDENSADOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 899FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
932 | 1.2.5.2.32.12 | C-J671 (3001 -3/4) CONDENSADOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 900FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
933 | 1.2.5.2.32.13 | C-J675-5A/B (80--3/4") | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-22T06:00 | 2025-07-23T06:00 | 0 | 901FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
934 | 1.2.5.2.32.14 | C-J671-5A/B (80 -3/4) | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-24T06:00 | 2025-07-25T06:00 | 0 | 902FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
935 | 1.2.5.2.32.15 | C-607 A/B/C (676 3/4") | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 903FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
936 | 1.2.5.2.32.16 | C-607 D/E/F (676 3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-26T18:00 | 2025-07-28T06:00 | 0 | 904FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
937 | 1.2.5.2.32.17 | C-604 A/B (197-3/4") | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 905FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
938 | 1.2.5.2.32.18 | C-612 A/B (56-3/4") | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-22T06:00 | 2025-07-23T06:00 | 0 | 906FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
939 | 1.2.5.2.32.19 | C-612 C/ D (56-3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-24T06:00 | 2025-07-25T06:00 | 0 | 907FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
940 | 1.2.5.2.32.20 | C-658 (510 T 3/4) | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 908FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
941 | 1.2.5.2.32.21 | C-656 A/B/C/D (880 T 3/4) | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-28T18:00 | 2025-07-29T06:00 | 0 | 909FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
942 | 1.2.5.2.32.22 | C-653 | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 910FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
943 | 1.2.5.2.32.23 | C-659 (118-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 911FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
944 | 1.2.5.2.32.24 | C-660 ABC (1020-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 912FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
945 | 1.2.5.2.32.25 | C-662 (325 3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 913FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
946 | 1.2.5.2.32.26 | C-663 (62 U-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 914FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
947 | 1.2.5.2.32.27 | C-665 A/B (128-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T11:00 | 2025-07-22T23:00 | 0 | 915FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
948 | 1.2.5.2.32.28 | C-668 (712-3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 916FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
949 | 1.2.5.2.32.29 | C-615 (3P)CAJA ENFRIADORAS | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 917FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
950 | 1.2.5.2.32.30 | C-666 ABCD (912 T ) | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T06:00 | 0 | 918FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
951 | 1.2.5.2.32.31 | C-661 (20 T3/4") | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-22T06:00 | 2025-07-22T18:00 | 0 | 919FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
952 | 1.2.5.3 | ARMADO Y PRUEBA | 11.491666666666667d | 275.8 | 11.491666666666667d | 275.8 | MPXJ (validado) | 2025-07-21T18:00 | 2025-08-02T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
953 | 1.2.5.3.1 | C-602 ABCD (1010 3/4") | 60.0eh | 60 | 275.8h | 275.8 | Nativo (factor 4.6x) | 2025-07-23T18:00 | 2025-07-26T06:00 | 0 | 921FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
954 | 1.2.5.3.2 | C-603 (62T 3/4") | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-21T18:00 | 2025-07-22T18:00 | 0 | 922FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
955 | 1.2.5.3.3 | C-605 (1610-3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-25T06:00 | 2025-07-26T06:00 | 0 | 923FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
956 | 1.2.5.3.4 | C-611 A (870 3/4") C | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 924FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
957 | 1.2.5.3.5 | C-611 B (870 3/4") C | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-24T18:00 | 2025-07-25T18:00 | 0 | 925FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
958 | 1.2.5.3.6 | C-614- ( 1414 / 3/4") C | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 926FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
959 | 1.2.5.3.7 | C-616 (380 3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 927FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
960 | 1.2.5.3.8 | C-617 A/ B (158-3/4") | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-23T06:00 | 2025-07-25T06:00 | 0 | 928FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
961 | 1.2.5.3.9 | C-619 A-B(116 /3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-23T06:00 | 2025-07-25T06:00 | 0 | 929FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
962 | 1.2.5.3.10 | C-655 (459-3/4") | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 930FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
963 | 1.2.5.3.11 | C-J675 (2244--3/4")CONDENSADOR | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 931FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
964 | 1.2.5.3.12 | C-J671 (3001 -3/4) CONDENSADOR | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 932FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
965 | 1.2.5.3.13 | C-J675-5A/B (80--3/4") | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-23T06:00 | 2025-07-25T06:00 | 0 | 933FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
966 | 1.2.5.3.14 | C-J671-5A/B (80 -3/4) | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 934FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
967 | 1.2.5.3.15 | C-607 A/B/C (676 3/4") | 36.0eh | 36 | 1152.0h | 1152 | Nativo (factor 32.0x) | 2025-07-25T06:00 | 2025-07-26T18:00 | 0 | 935FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
968 | 1.2.5.3.16 | C-607 D/E/F (676 3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-28T06:00 | 2025-07-29T18:00 | 0 | 936FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
969 | 1.2.5.3.17 | C-604 A/B (197-3/4") | 48.0eh | 48 | 864.0h | 864 | Nativo (factor 18.0x) | 2025-07-22T18:00 | 2025-07-24T18:00 | 0 | 937FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
970 | 1.2.5.3.18 | C-612 A/B (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-23T06:00 | 2025-07-25T06:00 | 0 | 938FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
971 | 1.2.5.3.19 | C-612 C/ D (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 939FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
972 | 1.2.5.3.20 | C-658 (510 T 3/4) | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 940FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
973 | 1.2.5.3.21 | C-656 A/B/C/D (880 T 3/4) | 96.0eh | 96 | 576.0h | 576 | Nativo (factor 6.0x) | 2025-07-29T06:00 | 2025-08-02T06:00 | 0 | 941FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
974 | 1.2.5.3.22 | C-653 | 24.0eh | 24 | 2304.0h | 2304 | Nativo (factor 96.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 942FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
975 | 1.2.5.3.23 | C-659 (118-3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 943FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
976 | 1.2.5.3.24 | C-660 ABC (1020-3/4") | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-22T18:00 | 2025-07-24T06:00 | 0 | 944FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
977 | 1.2.5.3.25 | C-662 (325 3/4") | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 945FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
978 | 1.2.5.3.26 | C-663 (62 U-3/4") | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 946FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
979 | 1.2.5.3.27 | C-665 A/B (128-3/4") | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-22T23:00 | 2025-07-24T23:00 | 0 | 947FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
980 | 1.2.5.3.28 | C-668 (712-3/4") | 24.0eh | 24 | 1152.0h | 1152 | Nativo (factor 48.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 948FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
981 | 1.2.5.3.29 | C-615 (3P)CAJA ENFRIADORAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 949FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
982 | 1.2.5.3.30 | C-666 ABCD (912 T ) | 96.0eh | 96 | 576.0h | 576 | Nativo (factor 6.0x) | 2025-07-23T06:00 | 2025-07-27T06:00 | 0 | 950FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
983 | 1.2.5.3.31 | C-661 (20 T3/4") | 24.0eh | 24 | 2304.0h | 2304 | Nativo (factor 96.0x) | 2025-07-22T18:00 | 2025-07-23T18:00 | 0 | 951FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
984 | 1.2.5.4 | NORMALIZADO DE BRIDAS | 13.490277777777777d | 323.7667 | 576.0h | 576 | Nativo (factor 1.8x) | 2025-07-22T18:00 | 2025-08-05T06:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
985 | 1.2.5.4.1 | C-602 ABCD (1010 3/4") | 60.0eh | 60 | 323.8h | 323.7667 | Nativo (factor 5.4x) | 2025-07-26T06:00 | 2025-07-28T18:00 | 0 | 953FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
986 | 1.2.5.4.2 | C-603 (62T 3/4") | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-22T18:00 | 2025-07-24T06:00 | 0 | 954FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
987 | 1.2.5.4.3 | C-605 (1610-3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-26T06:00 | 2025-07-27T18:00 | 0 | 955FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
988 | 1.2.5.4.4 | C-611 A (870 3/4") C | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 956FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
989 | 1.2.5.4.5 | C-611 B (870 3/4") C | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-25T18:00 | 2025-07-27T06:00 | 0 | 957FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
990 | 1.2.5.4.6 | C-614- ( 1414 / 3/4") C | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 958FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
991 | 1.2.5.4.7 | C-616 (380 3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 959FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
992 | 1.2.5.4.8 | C-617 A/ B (158-3/4") | 48.0eh | 48 | 864.0h | 864 | Nativo (factor 18.0x) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 960FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
993 | 1.2.5.4.9 | C-619 A-B(116 /3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 961FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
994 | 1.2.5.4.10 | C-655 (459-3/4") | 36.0eh | 36 | 1152.0h | 1152 | Nativo (factor 32.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 962FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
995 | 1.2.5.4.11 | C-J675 (2244--3/4")CONDENSADOR | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 963FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
996 | 1.2.5.4.12 | C-J671 (3001 -3/4) CONDENSADOR | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 964FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
997 | 1.2.5.4.13 | C-J675-5A/B (80--3/4") | 48.0eh | 48 | 864.0h | 864 | Nativo (factor 18.0x) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 965FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
998 | 1.2.5.4.14 | C-J671-5A/B (80 -3/4) | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-27T06:00 | 2025-07-29T06:00 | 0 | 966FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
999 | 1.2.5.4.15 | C-607 A/B/C (676 3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-26T18:00 | 2025-07-28T18:00 | 0 | 967FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1000 | 1.2.5.4.16 | C-607 D/E/F (676 3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-29T18:00 | 2025-07-31T18:00 | 0 | 968FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1001 | 1.2.5.4.17 | C-604 A/B (197-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-24T18:00 | 2025-07-26T18:00 | 0 | 969FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1002 | 1.2.5.4.18 | C-612 A/B (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T06:00 | 2025-07-27T06:00 | 0 | 970FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1003 | 1.2.5.4.19 | C-612 C/ D (56-3/4") | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-27T06:00 | 2025-07-29T06:00 | 0 | 971FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1004 | 1.2.5.4.20 | C-658 (510 T 3/4) | 36.0eh | 36 | 1152.0h | 1152 | Nativo (factor 32.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 972FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1005 | 1.2.5.4.21 | C-656 A/B/C/D (880 T 3/4) | 72.0eh | 72 | 864.0h | 864 | Nativo (factor 12.0x) | 2025-08-02T06:00 | 2025-08-05T06:00 | 0 | 973FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1006 | 1.2.5.4.22 | C-653 | 36.0eh | 36 | 1728.0h | 1728 | Nativo (factor 48.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 974FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1007 | 1.2.5.4.23 | C-659 (118-3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 975FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1008 | 1.2.5.4.24 | C-660 ABC (1020-3/4") | 60.0eh | 60 | 864.0h | 864 | Nativo (factor 14.4x) | 2025-07-24T06:00 | 2025-07-26T18:00 | 0 | 976FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1009 | 1.2.5.4.25 | C-662 (325 3/4") | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 977FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1010 | 1.2.5.4.26 | C-663 (62 U-3/4") | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 978FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1011 | 1.2.5.4.27 | C-665 A/B (128-3/4") | 60.0eh | 60 | 864.0h | 864 | Nativo (factor 14.4x) | 2025-07-24T23:00 | 2025-07-27T11:00 | 0 | 979FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1012 | 1.2.5.4.28 | C-668 (712-3/4") | 36.0eh | 36 | 1440.0h | 1440 | Nativo (factor 40.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 980FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1013 | 1.2.5.4.29 | C-615 (3P)CAJA ENFRIADORAS | 36.0eh | 36 | 864.0h | 864 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 981FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1014 | 1.2.5.4.30 | C-666 ABCD (912 T ) | 72.0eh | 72 | 864.0h | 864 | Nativo (factor 12.0x) | 2025-07-27T06:00 | 2025-07-30T06:00 | 0 | 982FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1015 | 1.2.5.4.31 | C-661 (20 T3/4") | 36.0eh | 36 | 1728.0h | 1728 | Nativo (factor 48.0x) | 2025-07-23T18:00 | 2025-07-25T06:00 | 0 | 983FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1016 | 1.2.5.5 | ENTREGA MECÁNICA DE EQUIPOS | 12.0eh | 12 | 864.0h | 864 | Nativo (factor 72.0x) | 2025-08-05T06:00 | 2025-08-05T18:00 | 0 | 984FS; 985FS; 986FS; 987FS; 988FS; 989FS; 990FS; 991FS; 992FS; 993FS; 994FS; 995FS; 996FS; 997FS; 998FS; 999FS; 1000FS; 1001FS; 1002FS; 1003FS; 1004FS; 1005FS; 1006FS; 1007FS; 1008FS; 1009FS; 1010FS; 1011FS; 1012FS; 1013FS; 1014FS; 1015FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1017 | 1.2.6 | AEROENFRIADORES | 15.947222222222223d | 382.7333 | 288.0h | 288 | Nativo (factor 0.8x) | 2025-07-17T18:00 | 2025-08-02T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1018 | 1.2.6.1 | C-601 ABCDEFGH (204-1") | 14.822916666666666d | 355.75 | 14.822916666666666d | 355.75 | MPXJ (validado) | 2025-07-17T18:00 | 2025-08-01T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | SON 8 PANELES | 4
1019 | 1.2.6.1.1 | COLOCAR B.C. | 48.0eh | 48 | 355.8h | 355.75 | Nativo (factor 7.4x) | 2025-07-17T18:00 | 2025-07-19T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1020 | 1.2.6.1.2 | RETIRAR TAPONES | 96.0eh | 96 | 1152.0h | 1152 | Nativo (factor 12.0x) | 2025-07-18T18:00 | 2025-07-22T18:00 | 0 | 1019FS-24eh |  | 0 | 0.0h | FALSE | FALSE | FALSE | 12 HS X CADA PANEL | 5
1021 | 1.2.6.1.3 | REALIZAR LIMPIEZA | 96.0eh | 96 | 2304.0h | 2304 | Nativo (corregido) | 2025-07-21T06:00 | 2025-07-25T06:00 | 0 | 1020FS-36eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1022 | 1.2.6.1.4 | REPASO DE ROSCAS | 96.0eh | 96 | 2304.0h | 2304 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-27T18:00 | 0 | 1021FS-36eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1023 | 1.2.6.1.5 | MONTAR TAPONES | 80.0eh | 80 | 2304.0h | 2304 | Nativo (factor 28.8x) | 2025-07-26T06:00 | 2025-07-29T14:00 | 0 | 1022FS-36eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1024 | 1.2.6.1.6 | PROBAR | 48.0eh | 48 | 1920.0h | 1920 | Nativo (factor 40.0x) | 2025-07-28T14:00 | 2025-07-30T14:00 | 0 | 1023FS-24eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1025 | 1.2.6.1.7 | RETIRAR B.C. | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-30T14:00 | 2025-08-01T14:00 | 0 | 1024FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1026 | 1.2.6.2 | C-608 A1/2 (120-1") | 4.913194444444445d | 117.9167 | 1152.0h | 1152 | Nativo (factor 9.8x) | 2025-07-17T18:00 | 2025-07-22T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1027 | 1.2.6.2.1 | COLOCAR B.C. | 10.0eh | 10 | 117.9h | 117.9167 | Nativo (factor 11.8x) | 2025-07-17T18:00 | 2025-07-18T04:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1028 | 1.2.6.2.2 | RETIRAR TAPONES | 24.0eh | 24 | 240.0h | 240 | Nativo (factor 10.0x) | 2025-07-18T04:00 | 2025-07-19T04:00 | 0 | 1027FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1029 | 1.2.6.2.3 | REALIZAR LIMPIEZA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-19T04:00 | 2025-07-20T04:00 | 0 | 1028FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1030 | 1.2.6.2.4 | REPASO DE ROSCAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-20T04:00 | 2025-07-21T04:00 | 0 | 1029FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1031 | 1.2.6.2.5 | MONTAR TAPONES | 20.0eh | 20 | 576.0h | 576 | Nativo (factor 28.8x) | 2025-07-21T04:00 | 2025-07-22T00:00 | 0 | 1030FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1032 | 1.2.6.2.6 | PROBAR | 8.0eh | 8 | 480.0h | 480 | Nativo (factor 60.0x) | 2025-07-22T00:00 | 2025-07-22T08:00 | 0 | 1031FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1033 | 1.2.6.2.7 | RETIRAR B.C. | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-22T08:00 | 2025-07-22T16:00 | 0 | 1032FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1034 | 1.2.6.3 | C-610 (120-1") | 5.496527777777778d | 131.9167 | 192.0h | 192 | Nativo (factor 1.5x) | 2025-07-18T04:00 | 2025-07-23T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1035 | 1.2.6.3.1 | COLOCAR B.C. | 10.0eh | 10 | 131.9h | 131.9167 | Nativo (factor 13.2x) | 2025-07-18T04:00 | 2025-07-18T14:00 | 0 | 1027FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1036 | 1.2.6.3.2 | RETIRAR TAPONES | 24.0eh | 24 | 240.0h | 240 | Nativo (factor 10.0x) | 2025-07-19T04:00 | 2025-07-20T04:00 | 0 | 1028FS; 1035FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1037 | 1.2.6.3.3 | REALIZAR LIMPIEZA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-20T04:00 | 2025-07-21T04:00 | 0 | 1029FS; 1036FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1038 | 1.2.6.3.4 | REPASO DE ROSCAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-21T04:00 | 2025-07-22T04:00 | 0 | 1030FS; 1037FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1039 | 1.2.6.3.5 | MONTAR TAPONES | 20.0eh | 20 | 576.0h | 576 | Nativo (factor 28.8x) | 2025-07-22T04:00 | 2025-07-23T00:00 | 0 | 1031FS; 1038FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1040 | 1.2.6.3.6 | PROBAR | 8.0eh | 8 | 480.0h | 480 | Nativo (factor 60.0x) | 2025-07-23T00:00 | 2025-07-23T08:00 | 0 | 1032FS; 1039FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1041 | 1.2.6.3.7 | RETIRAR B.C. | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-23T08:00 | 2025-07-23T16:00 | 0 | 1033FS; 1040FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1042 | 1.2.6.4 | C-618 (120-1") | 5.4125d | 129.9 | 192.0h | 192 | Nativo (factor 1.5x) | 2025-07-18T14:00 | 2025-07-24T00:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1043 | 1.2.6.4.1 | COLOCAR B.C. | 6.0eh | 6 | 129.9h | 129.9 | Nativo (corregido) | 2025-07-18T14:00 | 2025-07-18T20:00 | 0 | 1035FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1044 | 1.2.6.4.2 | RETIRAR TAPONES | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-20T04:00 | 2025-07-20T16:00 | 0 | 1036FS; 1043FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1045 | 1.2.6.4.3 | REALIZAR LIMPIEZA | 16.0eh | 16 | 288.0h | 288 | Nativo (factor 18.0x) | 2025-07-21T04:00 | 2025-07-21T20:00 | 0 | 1037FS; 1044FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1046 | 1.2.6.4.4 | REPASO DE ROSCAS | 12.0eh | 12 | 384.0h | 384 | Nativo (factor 32.0x) | 2025-07-22T04:00 | 2025-07-22T16:00 | 0 | 1038FS; 1045FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1047 | 1.2.6.4.5 | MONTAR TAPONES | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-23T00:00 | 2025-07-23T12:00 | 0 | 1039FS; 1046FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1048 | 1.2.6.4.6 | PROBAR | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-23T12:00 | 2025-07-23T18:00 | 0 | 1040FS; 1047FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1049 | 1.2.6.4.7 | RETIRAR B.C. | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-23T18:00 | 2025-07-24T00:00 | 0 | 1041FS; 1048FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1050 | 1.2.6.5 | C-620 (114-1") | 6.495138888888889d | 155.8833 | 6.495138888888889d | 155.8833 | MPXJ (validado) | 2025-07-18T20:00 | 2025-07-25T08:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1051 | 1.2.6.5.1 | COLOCAR B.C. | 10.0eh | 10 | 155.9h | 155.8833 | Nativo (factor 15.6x) | 2025-07-18T20:00 | 2025-07-19T06:00 | 0 | 1043FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1052 | 1.2.6.5.2 | RETIRAR TAPONES | 24.0eh | 24 | 240.0h | 240 | Nativo (factor 10.0x) | 2025-07-20T16:00 | 2025-07-21T16:00 | 0 | 1044FS; 1051FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1053 | 1.2.6.5.3 | REALIZAR LIMPIEZA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-21T20:00 | 2025-07-22T20:00 | 0 | 1045FS; 1052FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1054 | 1.2.6.5.4 | REPASO DE ROSCAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-22T20:00 | 2025-07-23T20:00 | 0 | 1046FS; 1053FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1055 | 1.2.6.5.5 | MONTAR TAPONES | 20.0eh | 20 | 576.0h | 576 | Nativo (factor 28.8x) | 2025-07-23T20:00 | 2025-07-24T16:00 | 0 | 1047FS; 1054FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1056 | 1.2.6.5.6 | PROBAR | 8.0eh | 8 | 480.0h | 480 | Nativo (factor 60.0x) | 2025-07-24T16:00 | 2025-07-25T00:00 | 0 | 1055FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1057 | 1.2.6.5.7 | RETIRAR B.C. | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-25T00:00 | 2025-07-25T08:00 | 0 | 1049FS; 1056FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1058 | 1.2.6.6 | C-651 A/B(145-1") | 12.075d | 289.8 | 192.0h | 192 | Nativo (factor 0.7x) | 2025-07-19T06:00 | 2025-07-31T08:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1059 | 1.2.6.6.1 | COLOCAR B.C. | 24.0eh | 24 | 289.8h | 289.8 | Nativo (factor 12.1x) | 2025-07-19T06:00 | 2025-07-20T06:00 | 0 | 1027FS; 1051FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1060 | 1.2.6.6.2 | RETIRAR TAPONES | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-21T16:00 | 2025-07-23T16:00 | 0 | 1028FS; 1052FS; 1059FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1061 | 1.2.6.6.3 | REALIZAR LIMPIEZA | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-23T16:00 | 2025-07-25T16:00 | 0 | 1029FS; 1053FS; 1060FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1062 | 1.2.6.6.4 | REPASO DE ROSCAS | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T16:00 | 2025-07-27T16:00 | 0 | 1030FS; 1054FS; 1061FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1063 | 1.2.6.6.5 | MONTAR TAPONES | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-27T16:00 | 2025-07-29T16:00 | 0 | 1031FS; 1055FS; 1062FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1064 | 1.2.6.6.6 | PROBAR | 16.0eh | 16 | 1152.0h | 1152 | Nativo (factor 72.0x) | 2025-07-29T16:00 | 2025-07-30T08:00 | 0 | 1063FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1065 | 1.2.6.6.7 | RETIRAR B.C. | 24.0eh | 24 | 384.0h | 384 | Nativo (factor 16.0x) | 2025-07-30T08:00 | 2025-07-31T08:00 | 0 | 1057FS; 1064FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1066 | 1.2.6.7 | C-652 A/B (145-1") | 13.074305555555556d | 313.7833 | 576.0h | 576 | Nativo (factor 1.8x) | 2025-07-20T06:00 | 2025-08-02T08:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1067 | 1.2.6.7.1 | COLOCAR B.C. | 24.0eh | 24 | 313.8h | 313.7833 | Nativo (factor 13.1x) | 2025-07-20T06:00 | 2025-07-21T06:00 | 0 | 1059FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1068 | 1.2.6.7.2 | RETIRAR TAPONES | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-23T16:00 | 2025-07-25T16:00 | 0 | 1060FS; 1067FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1069 | 1.2.6.7.3 | REALIZAR LIMPIEZA | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-25T16:00 | 2025-07-27T16:00 | 0 | 1061FS; 1068FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1070 | 1.2.6.7.4 | REPASO DE ROSCAS | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-27T16:00 | 2025-07-29T16:00 | 0 | 1062FS; 1069FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1071 | 1.2.6.7.5 | MONTAR TAPONES | 48.0eh | 48 | 1152.0h | 1152 | Nativo (corregido) | 2025-07-29T16:00 | 2025-07-31T16:00 | 0 | 1063FS; 1070FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1072 | 1.2.6.7.6 | PROBAR | 16.0eh | 16 | 1152.0h | 1152 | Nativo (factor 72.0x) | 2025-07-31T16:00 | 2025-08-01T08:00 | 0 | 1071FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1073 | 1.2.6.7.7 | RETIRAR B.C. | 24.0eh | 24 | 384.0h | 384 | Nativo (factor 16.0x) | 2025-08-01T08:00 | 2025-08-02T08:00 | 0 | 1072FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1074 | 1.2.6.8 | C-654 A/B (174-1") | 12.408333333333333d | 297.8 | 576.0h | 576 | Nativo (factor 1.9x) | 2025-07-21T06:00 | 2025-08-02T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1075 | 1.2.6.8.1 | COLOCAR B.C. | 10.0eh | 10 | 297.8h | 297.8 | Nativo (factor 29.8x) | 2025-07-21T06:00 | 2025-07-21T16:00 | 0 | 1067FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1076 | 1.2.6.8.2 | RETIRAR TAPONES | 30.0eh | 30 | 240.0h | 240 | Nativo (factor 8.0x) | 2025-07-25T16:00 | 2025-07-26T22:00 | 0 | 1068FS; 1075FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1077 | 1.2.6.8.3 | REALIZAR LIMPIEZA | 30.0eh | 30 | 720.0h | 720 | Nativo (corregido) | 2025-07-27T16:00 | 2025-07-28T22:00 | 0 | 1069FS; 1076FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1078 | 1.2.6.8.4 | REPASO DE ROSCAS | 24.0eh | 24 | 720.0h | 720 | Nativo (factor 30.0x) | 2025-07-29T16:00 | 2025-07-30T16:00 | 0 | 1070FS; 1077FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1079 | 1.2.6.8.5 | MONTAR TAPONES | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-31T16:00 | 2025-08-01T16:00 | 0 | 1071FS; 1078FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1080 | 1.2.6.8.6 | PROBAR | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-08-01T16:00 | 2025-08-02T00:00 | 0 | 1079FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1081 | 1.2.6.8.7 | RETIRAR B.C. | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-08-02T08:00 | 2025-08-02T16:00 | 0 | 1073FS; 1080FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1082 | 1.2.6.9 | ENTREGA DE EQUIPOS | 1.0eh | 1 | 192.0h | 192 | Nativo (factor 192.0x) | 2025-08-02T16:00 | 2025-08-02T17:00 | 0 | 1025FS; 1033FS; 1041FS; 1049FS; 1057FS; 1065FS; 1073FS; 1081FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1083 | 1.2.7 | FILTROS | 4.413194444444445d | 105.9167 | 24.0h | 24 | Nativo (factor 0.2x) | 2025-07-17T18:00 | 2025-07-22T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1084 | 1.2.7.1 | F-691 | 1.9152777777777779d | 45.9667 | 105.9h | 105.9167 | Nativo (factor 2.3x) | 2025-07-17T18:00 | 2025-07-19T16:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 1000 DE ALT. 0.4 DE Ø PASAMANO 8" | 4
1085 | 1.2.7.1.1 | DESBRIDAR | 6.0eh | 6 | 46.0h | 45.9667 | Nativo (factor 7.7x) | 2025-07-17T18:00 | 2025-07-18T00:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1086 | 1.2.7.1.2 | LIMPIEZA INTERIOR Y REPARACION DE FILTRO | 30.0eh | 30 | 144.0h | 144 | Nativo (factor 4.8x) | 2025-07-18T00:00 | 2025-07-19T06:00 | 0 | 1085FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1087 | 1.2.7.1.3 | INSPECCION | 2.0eh | 2 | 720.0h | 720 | Nativo (factor 360.0x) | 2025-07-19T06:00 | 2025-07-19T08:00 | 0 | 1086FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1088 | 1.2.7.1.4 | BRIDAR | 8.0eh | 8 | 48.0h | 48 | Nativo (factor 6.0x) | 2025-07-19T08:00 | 2025-07-19T16:00 | 0 | 1087FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1089 | 1.2.7.2 | F-695 | 1.1659722222222222d | 27.9833 | 192.0h | 192 | Nativo (factor 6.9x) | 2025-07-19T16:00 | 2025-07-20T20:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 1000 DE ALT. 0.4 DE Ø PASAMANO 8" | 4
1090 | 1.2.7.2.1 | DESBRIDAR | 6.0eh | 6 | 28.0h | 27.9833 | Nativo (factor 4.7x) | 2025-07-19T16:00 | 2025-07-19T22:00 | 0 | 1088FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1091 | 1.2.7.2.2 | LIMPIEZA INTERIOR | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-19T22:00 | 2025-07-20T10:00 | 0 | 1090FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1092 | 1.2.7.2.3 | INSPECCION | 2.0eh | 2 | 288.0h | 288 | Nativo (factor 144.0x) | 2025-07-20T10:00 | 2025-07-20T12:00 | 0 | 1091FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1093 | 1.2.7.2.4 | BRIDAR | 8.0eh | 8 | 48.0h | 48 | Nativo (factor 6.0x) | 2025-07-20T12:00 | 2025-07-20T20:00 | 0 | 1092FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1094 | 1.2.7.3 | F-696 | 1.3319444444444444d | 31.9667 | 192.0h | 192 | Nativo (factor 6.0x) | 2025-07-20T20:00 | 2025-07-22T04:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 1000 DE ALT. 0.4 DE Ø PASAMANO 8" | 4
1095 | 1.2.7.3.1 | COLOCAR BC | 6.0eh | 6 | 32.0h | 31.9667 | Nativo (factor 5.3x) | 2025-07-20T20:00 | 2025-07-21T02:00 | 0 | 1093FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1096 | 1.2.7.3.2 | DESTAPAR PM | 12.0eh | 12 | 144.0h | 144 | Nativo (factor 12.0x) | 2025-07-21T02:00 | 2025-07-21T14:00 | 0 | 1095FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1097 | 1.2.7.3.3 | LIMPIEZA INTERIOR | 2.0eh | 2 | 288.0h | 288 | Nativo (factor 144.0x) | 2025-07-21T14:00 | 2025-07-21T16:00 | 0 | 1096FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1098 | 1.2.7.3.4 | INSPECCION | 8.0eh | 8 | 48.0h | 48 | Nativo (factor 6.0x) | 2025-07-21T16:00 | 2025-07-22T00:00 | 0 | 1097FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1099 | 1.2.7.3.5 | BRIDAR | 4.0eh | 4 | 192.0h | 192 | Nativo (factor 48.0x) | 2025-07-22T00:00 | 2025-07-22T04:00 | 0 | 1098FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1100 | 1.2.8 | VALVULAS DE SEGURIDAD | 22.35902777777778d | 536.6167 | 96.0h | 96 | Nativo (factor 0.2x) | 2025-07-17T18:00 | 2025-08-09T03:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 107 VALVULAS | 3
1101 | 1.2.8.1 | DESMONTAR VALVULAS | 120.0eh | 120 | 536.6h | 536.6167 | Nativo (factor 4.5x) | 2025-07-17T18:00 | 2025-07-22T18:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | 10 VALVULAS POR TURNO | 4
1102 | 1.2.8.2 | PRE-TEST | 144.0eh | 144 | 2880.0h | 2880 | Nativo (corregido) | 2025-07-19T18:00 | 2025-07-25T18:00 | 0 | 1101FS-72eh |  | 0 | 0.0h | FALSE | FALSE | FALSE | 7 VALVULA X TURNO | 4
1103 | 1.2.8.3 | REPARACIONES Y CALIBRADO | 15.0ed | 360 | 3456.0h | 3456 | Nativo (factor 9.6x) | 2025-07-21T18:00 | 2025-08-05T18:00 | 0 | 1102FS-96eh |  | 0 | 0.0h | FALSE | FALSE | FALSE | 15DT7 VALVULAS X DIA | 4
1104 | 1.2.8.4 | CALIBRACION EN BANCO | 144.0eh | 144 | 360.0h | 360 | Nativo (factor 2.5x) | 2025-07-31T23:00 | 2025-08-06T23:00 | 0 | 1103FS-115eh |  | 0 | 0.0h | FALSE | FALSE | FALSE | SE ESTIMA EL 75% 80 VALV7 VALV X TURNO | 4
1105 | 1.2.8.5 | MONTAR | 112.0eh | 112 | 3456.0h | 3456 | Nativo (factor 30.9x) | 2025-08-04T11:00 | 2025-08-09T03:00 | 0 | 1104FS-60eh |  | 0 | 0.0h | FALSE | FALSE | FALSE | 10 VALVULAS POR TURNO | 4
1106 | 1.2.9 | VARIOS DE CAÑERIAS | 24.0d | 576 | 2688.0h | 2688 | Nativo (factor 4.7x) | 2025-07-17T18:00 | 2025-08-10T18:24 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1107 | 1.2.9.1 | CAMBIO VALVULAS SOLDADAS | 24.0d | 576 | 24.0d | 576 | MPXJ (validado) | 2025-07-17T18:00 | 2025-08-10T18:24 | 0 | 5FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1108 | 1.2.9.2 | CAMBIO VALVULAS BRIDADAS | 24.0d | 576 | 24.0d | 576 | MPXJ (validado) | 2025-07-17T18:00 | 2025-08-10T18:24 | 0 | 5FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1109 | 1.2.10 | INSTRUMENTOS | 24.0d | 576 | 24.0d | 576 | MPXJ (validado) | 2025-07-17T17:00 | 2025-08-10T17:24 | 0 | 5FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 3
1110 | 1.2.11 | OBRAS | 24.0d | 576 | 24.0d | 576 | MPXJ (validado) | 2025-07-17T17:00 | 2025-08-10T17:24 | 0 | 5FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 3
1111 | 1.2.12 | EQUIPOS ROTANTES | 26.315277777777776d | 631.5667 | 26.315277777777776d | 631.5667 | MPXJ (validado) | 2025-07-15T06:00 | 2025-08-10T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1112 | 1.2.12.1 | J-675 | 21.69375d | 520.65 | 631.6h | 631.5667 | Nativo (factor 1.2x) | 2025-07-15T06:00 | 2025-08-05T23:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1113 | 1.2.12.1.1 | ENTREGA | 1.0eh | 1 | 520.6h | 520.65 | Nativo (factor 520.6x) | 2025-07-15T06:00 | 2025-07-15T07:00 | 0 | 4FS+24eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1114 | 1.2.12.1.2 | MANTENIMIENTO | 21.652083333333334d | 519.65 | 24.0h | 24 | Nativo (factor 0.0x) | 2025-07-15T07:00 | 2025-08-05T23:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | DESMONTAJ3E MANTENIMIENTO MONTAJE PRUEBA Y PEM | 5
1115 | 1.2.12.1.2.1 | DESMONTAJE Y TRASLADO | 30.0eh | 30 | 519.6h | 519.65 | Nativo (factor 17.3x) | 2025-07-15T07:00 | 2025-07-16T13:00 | 0 | 1113FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1116 | 1.2.12.1.2.2 | MTO. MECANICO | 460.0eh | 460 | 720.0h | 720 | Nativo (factor 1.6x) | 2025-07-16T13:00 | 2025-08-04T17:00 | 0 | 1115FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1117 | 1.2.12.1.2.3 | PRUEBA | 30.0eh | 30 | 11040.0h | 11040 | Nativo (factor 368.0x) | 2025-08-04T17:00 | 2025-08-05T23:00 | 0 | 1116FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1118 | 1.2.12.2 | J-671 | 25.31597222222222d | 607.5833 | 25.31597222222222d | 607.5833 | MPXJ (validado) | 2025-07-16T06:00 | 2025-08-10T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1119 | 1.2.12.2.1 | ENTREGA | 1.0eh | 1 | 607.6h | 607.5833 | Nativo (factor 607.6x) | 2025-07-16T06:00 | 2025-07-16T07:00 | 0 | 4FS+48eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1120 | 1.2.12.2.2 | MANTENIMIENTO | 25.274305555555557d | 606.5833 | 24.0h | 24 | Nativo (factor 0.0x) | 2025-07-16T07:00 | 2025-08-10T14:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | DESMONTAJ3E MANTENIMIENTO MONTAJE PRUEBA Y PEM | 5
1121 | 1.2.12.2.2.1 | DESMONTAJE Y TRASLADO | 30.0eh | 30 | 606.6h | 606.5833 | Nativo (corregido) | 2025-07-16T07:00 | 2025-07-17T13:00 | 0 | 1119FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1122 | 1.2.12.2.2.2 | MTO. MECANICO | 520.0eh | 520 | 720.0h | 720 | Nativo (factor 1.4x) | 2025-07-17T13:00 | 2025-08-08T05:00 | 0 | 1121FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1123 | 1.2.12.2.2.3 | PRUEBA | 57.0eh | 57 | 12480.0h | 12480 | Nativo (factor 218.9x) | 2025-08-08T05:00 | 2025-08-10T14:00 | 0 | 1122FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1124 | 1.2.12.3 | RESTO DE EQ. ROTANTES | 60.0eh | 60 | 1368.0h | 1368 | Nativo (corregido) | 2025-07-17T18:00 | 2025-07-20T06:00 | 0 | 6FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1125 | 1.3 | PEM | 3.9972222222222222d | 95.9333 | 1440.0h | 1440 | Nativo (factor 15.0x) | 2025-08-12T23:02 | 2025-08-16T23:02 | 0 |  |  | 0 | 0.0h | TRUE | FALSE | TRUE |  | 2
1126 | 1.3.1 | RETIRO DE BC L.B. | 72.0eh | 72 | 95.9h | 95.9333 | Nativo (factor 1.3x) | 2025-08-12T23:02 | 2025-08-15T23:02 | 0 | 313FS; 1117FS; 1123FS; 1109FS; 1110FS; 1105FS; 1107FS; 1108FS; 1082FS; 1016FS; 403FS; 422FS; 456FS; 475FS; 506FS; 525FS; 540FS; 552FS; 575FS; 588FS; 600FS; 610FS; 620FS; 630FS; 645FS; 656FS; 667FS; 672FS; 683FS; 694FS; 699FS; 710FS; 721FS; 732FS; 743FS; 759FS; 775FS; 791FS; 802FS; 813FS; 827FS; 839FS; 844FS; 849FS; 854FS; 1088FS; 1093FS; 1099FS |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 3
1127 | 1.3.2 | PUESTA EN MARCHA | 72.0eh | 72 | 1728.0h | 1728 | Nativo (corregido) | 2025-08-13T23:02 | 2025-08-16T23:02 | 0 | 1126SS+24eh |  | 0 | 0.0h | TRUE | FALSE | FALSE |  | 3
1128 | 1.4 | MEROX | 17.02986111111111d | 408.7167 | 1728.0h | 1728 | Nativo (factor 4.2x) | 2025-07-16T18:00 | 2025-08-02T19:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 2
1129 | 1.4.1 | PARO UNIDAD | 3.2888888888888888d | 78.9333 | 408.7h | 408.7167 | Nativo (factor 5.2x) | 2025-07-16T18:00 | 2025-07-20T01:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1130 | 1.4.1.1 | LAVADO Y PURGA | 55.0eh | 55 | 78.9h | 78.9333 | Nativo (factor 1.4x) | 2025-07-16T18:00 | 2025-07-19T01:00 | 0 | 10FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1131 | 1.4.1.2 | COLOCACION B.C. | 24.0eh | 24 | 1320.0h | 1320 | Nativo (factor 55.0x) | 2025-07-19T01:00 | 2025-07-20T01:00 | 0 | 1130FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 4
1132 | 1.4.2 | MANTENIMIENTO | 13.740972222222222d | 329.7833 | 576.0h | 576 | Nativo (factor 1.7x) | 2025-07-20T01:00 | 2025-08-02T19:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 3
1133 | 1.4.2.1 | TORRES | 11.575694444444444d | 277.8167 | 11.575694444444444d | 277.8167 | MPXJ (validado) | 2025-07-22T01:00 | 2025-08-02T15:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1134 | 1.4.2.1.1 | E-801 | 11.575694444444444d | 277.8167 | 11.575694444444444d | 277.8167 | MPXJ (validado) | 2025-07-22T01:00 | 2025-08-02T15:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
1135 | 1.4.2.1.1.1 | COLOCACION B.C. | 12.0eh | 12 | 277.8h | 277.8167 | Nativo (corregido) | 2025-07-22T01:00 | 2025-07-22T13:00 | 0 | 1131FS+48eh |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1136 | 1.4.2.1.1.2 | DESTAPAR P.H.18"-300# - 2 - | 10.0eh | 10 | 288.0h | 288 | Nativo (factor 28.8x) | 2025-07-22T13:00 | 2025-07-22T23:00 | 0 | 1135FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1137 | 1.4.2.1.1.3 | VENTILACION | 36.0eh | 36 | 240.0h | 240 | Nativo (factor 6.7x) | 2025-07-22T23:00 | 2025-07-24T11:00 | 0 | 1136FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1138 | 1.4.2.1.1.4 | AUTORIZACION INGRESO CONF. | 2.0eh | 2 | 864.0h | 864 | Nativo (factor 432.0x) | 2025-07-24T11:00 | 2025-07-24T13:00 | 0 | 1137FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1139 | 1.4.2.1.1.5 | MONTAR ILUMINACION | 2.0eh | 2 | 48.0h | 48 | Nativo (corregido) | 2025-07-24T13:00 | 2025-07-24T15:00 | 0 | 1138FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1140 | 1.4.2.1.1.6 | DESMONTAR COLECTORES ( 3 ) | 24.0eh | 24 | 48.0h | 48 | Nativo (factor 2.0x) | 2025-07-24T15:00 | 2025-07-25T15:00 | 0 | 1139FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1141 | 1.4.2.1.1.7 | LIMPIEZA Y REPARACION | 48.0eh | 48 | 576.0h | 576 | Nativo (factor 12.0x) | 2025-07-25T15:00 | 2025-07-27T15:00 | 0 | 1140FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1142 | 1.4.2.1.1.8 | INSTALAR ANDAMIO INT. | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-07-25T15:00 | 2025-07-26T03:00 | 0 | 1140FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1143 | 1.4.2.1.1.9 | DESMONTAR MALLA COALESCEDORA EN AISI 304 | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-26T03:00 | 2025-07-26T15:00 | 0 | 1142FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1144 | 1.4.2.1.1.10 | LAVAR Y REPARAR MALLA | 72.0eh | 72 | 288.0h | 288 | Nativo (factor 4.0x) | 2025-07-26T15:00 | 2025-07-29T15:00 | 0 | 1143FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1145 | 1.4.2.1.1.11 | LAVAR EQUIPO COMPLETO Y TOMAS | 24.0eh | 24 | 1728.0h | 1728 | Nativo (factor 72.0x) | 2025-07-26T15:00 | 2025-07-27T15:00 | 0 | 1143FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1146 | 1.4.2.1.1.12 | INSPECCION | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-07-27T15:00 | 2025-07-27T19:00 | 0 | 1145FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1147 | 1.4.2.1.1.13 | MONTAR MALLA COALESCEDORA | 28.0eh | 28 | 96.0h | 96 | Nativo (factor 3.4x) | 2025-07-29T15:00 | 2025-07-30T19:00 | 0 | 1144FS; 1146FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1148 | 1.4.2.1.1.14 | DESMONTAR ANDAMIO | 8.0eh | 8 | 672.0h | 672 | Nativo (factor 84.0x) | 2025-07-30T19:00 | 2025-07-31T03:00 | 0 | 1147FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1149 | 1.4.2.1.1.15 | MONTAR COLECTORES ( 3 ) | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-31T03:00 | 2025-08-01T15:00 | 0 | 1141FS; 1148FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1150 | 1.4.2.1.1.16 | INSPECCION | 2.0eh | 2 | 864.0h | 864 | Nativo (factor 432.0x) | 2025-08-01T15:00 | 2025-08-01T17:00 | 0 | 1149FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1151 | 1.4.2.1.1.17 | TAPAR P.H.18"-300# - 2 - | 10.0eh | 10 | 48.0h | 48 | Nativo (factor 4.8x) | 2025-08-01T17:00 | 2025-08-02T03:00 | 0 | 1150FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1152 | 1.4.2.1.1.18 | RETIRAR DISCOS CIEGOS | 12.0eh | 12 | 240.0h | 240 | Nativo (corregido) | 2025-08-02T03:00 | 2025-08-02T15:00 | 0 | 1151FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1153 | 1.4.2.1.2 | E-802 | 9.993055555555555d | 239.8333 | 288.0h | 288 | Nativo (factor 1.2x) | 2025-07-22T23:00 | 2025-08-01T23:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 21550 DE H; 1830 DE DIAM. 10 PLATOS | 5
1154 | 1.4.2.1.2.1 | COLOCAR BC. | 10.0eh | 10 | 239.8h | 239.8333 | Nativo (corregido) | 2025-07-22T23:00 | 2025-07-23T09:00 | 0 | 1136FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1155 | 1.4.2.1.2.2 | DESTAPAR P.H. (2) | 10.0eh | 10 | 240.0h | 240 | Nativo (corregido) | 2025-07-23T09:00 | 2025-07-23T19:00 | 0 | 1136FS; 1154FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1156 | 1.4.2.1.2.3 | VENTILACION | 48.0eh | 48 | 240.0h | 240 | Nativo (factor 5.0x) | 2025-07-23T19:00 | 2025-07-25T19:00 | 0 | 1155FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1157 | 1.4.2.1.2.4 | MONTAR AND.FONDO | 8.0eh | 8 | 1152.0h | 1152 | Nativo (factor 144.0x) | 2025-07-25T19:00 | 2025-07-26T03:00 | 0 | 1156FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1158 | 1.4.2.1.2.5 | ABRIR PASAJES | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-25T19:00 | 2025-07-26T01:00 | 0 | 1156FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1159 | 1.4.2.1.2.6 | LIMPIEZA DE PLATOS | 72.0eh | 72 | 144.0h | 144 | Nativo (factor 2.0x) | 2025-07-26T01:00 | 2025-07-29T01:00 | 0 | 1158FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1160 | 1.4.2.1.2.7 | INSPECCION | 3.0eh | 3 | 1728.0h | 1728 | Nativo (factor 576.0x) | 2025-07-29T01:00 | 2025-07-29T04:00 | 0 | 1159FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1161 | 1.4.2.1.2.8 | REPARACIONES MENORES | 43.0eh | 43 | 72.0h | 72 | Nativo (factor 1.7x) | 2025-07-29T04:00 | 2025-07-30T23:00 | 0 | 1160FS |  | 0 | 0.0h | FALSE | FALSE | FALSE | EN PARO ANTERIOR SE REPARARON PASAJES DEFORMADOS | 6
1162 | 1.4.2.1.2.9 | LIMPIEZA FINAL | 12.0eh | 12 | 1032.0h | 1032 | Nativo (factor 86.0x) | 2025-07-30T23:00 | 2025-07-31T11:00 | 0 | 1161FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1163 | 1.4.2.1.2.10 | CERRAR PASAJES | 8.0eh | 8 | 288.0h | 288 | Nativo (factor 36.0x) | 2025-07-31T11:00 | 2025-07-31T19:00 | 0 | 1162FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1164 | 1.4.2.1.2.11 | DESMONTAR ANDAMIO FONDO | 4.0h | 0 | 192.0h | 192 | Nativo (MPXJ=0) | 2025-07-31T19:00 | 2025-07-31T23:00 | 0 | 1163FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1165 | 1.4.2.1.2.12 | LIMPIEZA DE FONDO | 6.0eh | 6 | 4.0h | 4 | Nativo (factor 0.7x) | 2025-07-31T23:00 | 2025-08-01T05:00 | 0 | 1164FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1166 | 1.4.2.1.2.13 | TAPAR P.H. | 10.0eh | 10 | 144.0h | 144 | Nativo (factor 14.4x) | 2025-08-01T05:00 | 2025-08-01T15:00 | 0 | 1165FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1167 | 1.4.2.1.2.14 | RETIRAR B.C. | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-08-01T15:00 | 2025-08-01T23:00 | 0 | 1166FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1168 | 1.4.2.1.3 | E-803 | 8.702777777777778d | 208.8667 | 8.702777777777778d | 208.8667 | MPXJ (validado) | 2025-07-23T19:00 | 2025-08-01T12:01 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 7000 mm x 600mm 1.5 m3 de anillos de carbon | 5
1169 | 1.4.2.1.3.1 | COLOCAR BC | 8.0eh | 8 | 208.9h | 208.8667 | Nativo (corregido) | 2025-07-23T19:00 | 2025-07-24T03:00 | 0 | 1155FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1170 | 1.4.2.1.3.2 | DESTAPAR PH Y DESCARGA | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-24T03:00 | 2025-07-24T11:00 | 0 | 1155FS; 1169FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1171 | 1.4.2.1.3.3 | VENTILACION | 36.0eh | 36 | 192.0h | 192 | Nativo (factor 5.3x) | 2025-07-24T11:00 | 2025-07-25T23:00 | 0 | 1170FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1172 | 1.4.2.1.3.4 | DESCARGAR ANILLOS | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-25T23:00 | 2025-07-26T23:00 | 0 | 1171FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1173 | 1.4.2.1.3.5 | RETIRAR DISTRIBUIDOR | 6.0h | 0 | 576.0h | 576 | Nativo (MPXJ=0) | 2025-07-26T23:00 | 2025-07-27T05:01 | 0 | 1172FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1174 | 1.4.2.1.3.6 | LIMPIEZA DISTRIBUIDOR | 12.0eh | 12 | 6.0h | 6 | Nativo (factor 0.5x) | 2025-07-27T05:01 | 2025-07-27T17:01 | 0 | 1173FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1175 | 1.4.2.1.3.7 | MONTAR MASTIL | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-27T17:01 | 2025-07-27T23:01 | 0 | 1174FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1176 | 1.4.2.1.3.8 | LIMPIEZA ENVOLVENTE | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-27T23:01 | 2025-07-28T23:01 | 0 | 1175FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1177 | 1.4.2.1.3.9 | INSPECCION | 4.0eh | 4 | 576.0h | 576 | Nativo (factor 144.0x) | 2025-07-28T23:01 | 2025-07-29T03:01 | 0 | 1176FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1178 | 1.4.2.1.3.10 | REPARAC. DISTRIBUIDOR | 19.0eh | 19 | 96.0h | 96 | Nativo (factor 5.1x) | 2025-07-29T03:01 | 2025-07-29T22:01 | 0 | 1177FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1179 | 1.4.2.1.3.11 | DESMONTAJE MASTIL | 6.0eh | 6 | 456.0h | 456 | Nativo (factor 76.0x) | 2025-07-29T22:01 | 2025-07-30T04:01 | 0 | 1178FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1180 | 1.4.2.1.3.12 | LIMPIEZA DE FONDO | 8.0eh | 8 | 144.0h | 144 | Nativo (factor 18.0x) | 2025-07-30T04:01 | 2025-07-30T12:01 | 0 | 1179FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1181 | 1.4.2.1.3.13 | MONTAJE DISTRIBUIDOR | 10.0eh | 10 | 192.0h | 192 | Nativo (factor 19.2x) | 2025-07-30T12:01 | 2025-07-30T22:01 | 0 | 1180FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1182 | 1.4.2.1.3.14 | TAPAR DESCARGA | 6.0eh | 6 | 240.0h | 240 | Nativo (factor 40.0x) | 2025-07-30T22:01 | 2025-07-31T04:01 | 0 | 1181FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1183 | 1.4.2.1.3.15 | CARGAR ANILLOS | 16.0eh | 16 | 144.0h | 144 | Nativo (factor 9.0x) | 2025-07-31T04:01 | 2025-07-31T20:01 | 0 | 1182FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1184 | 1.4.2.1.3.16 | TAPAR PH | 8.0eh | 8 | 384.0h | 384 | Nativo (factor 48.0x) | 2025-07-31T20:01 | 2025-08-01T04:01 | 0 | 1183FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1185 | 1.4.2.1.3.17 | RETIRAR BC | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-08-01T04:01 | 2025-08-01T12:01 | 0 | 1184FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1186 | 1.4.2.2 | ACUMULADORES | 13.740972222222222d | 329.7833 | 192.0h | 192 | Nativo (factor 0.6x) | 2025-07-20T01:00 | 2025-08-02T19:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1187 | 1.4.2.2.1 | F-804 | 10.243055555555555d | 245.8333 | 329.8h | 329.7833 | Nativo (factor 1.3x) | 2025-07-20T01:00 | 2025-07-30T07:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | ACUMULADOR CON TORRETA 16" ACUMULADOR PH 18" DIA. 1.050 LARGO 4400 LECHO DE ANTRACITA 1 M3 2 mallas de 0.8 m2 c/una | 5
1188 | 1.4.2.2.1.1 | COLOCAR BC | 10.0eh | 10 | 245.8h | 245.8333 | Nativo (corregido) | 2025-07-20T01:00 | 2025-07-20T11:00 | 0 | 1131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1189 | 1.4.2.2.1.2 | DESTAPAR PH (2) | 8.0eh | 8 | 240.0h | 240 | Nativo (factor 30.0x) | 2025-07-20T11:00 | 2025-07-20T19:00 | 0 | 1188FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1190 | 1.4.2.2.1.3 | VENTILACION | 24.0eh | 24 | 192.0h | 192 | Nativo (factor 8.0x) | 2025-07-20T19:00 | 2025-07-21T19:00 | 0 | 1189FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1191 | 1.4.2.2.1.4 | DESMONTAR TORRETA | 36.0eh | 36 | 576.0h | 576 | Nativo (factor 16.0x) | 2025-07-21T19:00 | 2025-07-23T07:00 | 0 | 1190FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1192 | 1.4.2.2.1.5 | DESCARGAR RELLENO | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-23T07:00 | 2025-07-24T07:00 | 0 | 1191FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1193 | 1.4.2.2.1.6 | LIMPIEZA RELLENO | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-24T07:00 | 2025-07-25T07:00 | 0 | 1192FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1194 | 1.4.2.2.1.7 | CAMBIO DE EQUIPO | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-25T07:00 | 2025-07-26T07:00 | 0 | 1193FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1195 | 1.4.2.2.1.8 | CARGAR TORRETA | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-26T07:00 | 2025-07-27T07:00 | 0 | 1194FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1196 | 1.4.2.2.1.9 | DESARME DE PLATAFORMAS Y LINEAS | 24.0eh | 24 | 576.0h | 576 | Nativo (corregido) | 2025-07-23T07:00 | 2025-07-24T07:00 | 0 | 1191FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1197 | 1.4.2.2.1.10 | REEMPLAZO DE EQUIPO | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-24T07:00 | 2025-07-24T15:00 | 0 | 1196FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1198 | 1.4.2.2.1.11 | MONTAJE DE LINEAS Y PLATAFORMAS | 48.0eh | 48 | 192.0h | 192 | Nativo (factor 4.0x) | 2025-07-24T15:00 | 2025-07-26T15:00 | 0 | 1197FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1199 | 1.4.2.2.1.12 | MONTAR TORRETA | 12.0eh | 12 | 1152.0h | 1152 | Nativo (factor 96.0x) | 2025-07-27T07:00 | 2025-07-27T19:00 | 0 | 1195FS; 1198FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1200 | 1.4.2.2.1.13 | CONECTAR INSTRUMENTAL | 36.0eh | 36 | 288.0h | 288 | Nativo (factor 8.0x) | 2025-07-27T19:00 | 2025-07-29T07:00 | 0 | 1199FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1201 | 1.4.2.2.1.14 | RETIRO DE BC | 24.0eh | 24 | 864.0h | 864 | Nativo (factor 36.0x) | 2025-07-29T07:00 | 2025-07-30T07:00 | 0 | 1200FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1202 | 1.4.2.2.2 | F-803 | 4.996527777777778d | 119.9167 | 576.0h | 576 | Nativo (factor 4.8x) | 2025-07-24T07:00 | 2025-07-29T07:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 8" p.mano 1500 X 0.6 DE DIAMETRO | 5
1203 | 1.4.2.2.2.1 | CLOCAR BC | 12.0eh | 12 | 119.9h | 119.9167 | Nativo (factor 10.0x) | 2025-07-24T07:00 | 2025-07-24T19:00 | 0 | 1192FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1204 | 1.4.2.2.2.2 | DESBRIDAR BOCA DE LIMPIEZA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-24T19:00 | 2025-07-25T07:00 | 0 | 1203FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1205 | 1.4.2.2.2.3 | REALIZAR LIMPIEZA | 60.0eh | 60 | 288.0h | 288 | Nativo (factor 4.8x) | 2025-07-25T07:00 | 2025-07-27T19:00 | 0 | 1203FS; 1204FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1206 | 1.4.2.2.2.4 | INSPECCION | 12.0eh | 12 | 1440.0h | 1440 | Nativo (factor 120.0x) | 2025-07-27T19:00 | 2025-07-28T07:00 | 0 | 1205FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1207 | 1.4.2.2.2.5 | BRIDAR Y RETIRAR BC | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-28T07:00 | 2025-07-29T07:00 | 0 | 1206FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1208 | 1.4.2.2.3 | F-802 | 12.158333333333333d | 291.8 | 576.0h | 576 | Nativo (factor 2.0x) | 2025-07-20T01:00 | 2025-08-01T05:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 2280 de Ø h 5700 distribuidores 1 lecho 8 m3 | 5
1209 | 1.4.2.2.3.1 | INSTALAR DISCOS CIEGOS | 24.0eh | 24 | 291.8h | 291.8 | Nativo (factor 12.2x) | 2025-07-20T01:00 | 2025-07-21T01:00 | 0 | 1131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1210 | 1.4.2.2.3.2 | DESTAPAR P.H. 18"-300# - 20" 300#(2) | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-21T01:00 | 2025-07-21T13:00 | 0 | 1209FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1211 | 1.4.2.2.3.3 | DESCARGAR ARENA (45 TAMB.) | 60.0eh | 60 | 288.0h | 288 | Nativo (factor 4.8x) | 2025-07-21T13:00 | 2025-07-24T01:00 | 0 | 1210FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1212 | 1.4.2.2.3.4 | VENTILACION | 24.0eh | 24 | 1440.0h | 1440 | Nativo (factor 60.0x) | 2025-07-24T01:00 | 2025-07-25T01:00 | 0 | 1211FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1213 | 1.4.2.2.3.5 | MONTAR ACCESO | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-25T01:00 | 2025-07-25T13:00 | 0 | 1212FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1214 | 1.4.2.2.3.6 | DESMONTAR DISTRIBUIDOR | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-25T13:00 | 2025-07-26T01:00 | 0 | 1213FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1215 | 1.4.2.2.3.7 | DESMONTAR GRILLA | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-07-26T01:00 | 2025-07-26T13:00 | 0 | 1214FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1216 | 1.4.2.2.3.8 | LAVAR EQUIPO COMPLETO | 24.0eh | 24 | 288.0h | 288 | Nativo (factor 12.0x) | 2025-07-26T13:00 | 2025-07-27T13:00 | 0 | 1215FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1217 | 1.4.2.2.3.9 | LIMPIEZA DE GRILLA | 12.0eh | 12 | 576.0h | 576 | Nativo (factor 48.0x) | 2025-07-27T13:00 | 2025-07-28T01:00 | 0 | 1216FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1218 | 1.4.2.2.3.10 | INSPECCION DE GRILLA | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-28T01:00 | 2025-07-28T07:00 | 0 | 1217FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1219 | 1.4.2.2.3.11 | REPARACION DE GRILLA | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-28T07:00 | 2025-07-29T07:00 | 0 | 1218FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1220 | 1.4.2.2.3.12 | MONTAR GRILLA | 20.0eh | 20 | 576.0h | 576 | Nativo (factor 28.8x) | 2025-07-29T07:00 | 2025-07-30T03:00 | 0 | 1219FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1221 | 1.4.2.2.3.13 | CARGAR LECHO DE ARENA | 26.0eh | 26 | 480.0h | 480 | Nativo (factor 18.5x) | 2025-07-30T03:00 | 2025-07-31T05:00 | 0 | 1220FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1222 | 1.4.2.2.3.14 | MONTAR DISTRIBUIDOR | 8.0eh | 8 | 624.0h | 624 | Nativo (factor 78.0x) | 2025-07-31T05:00 | 2025-07-31T13:00 | 0 | 1221FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1223 | 1.4.2.2.3.15 | RETIRAR ILUMINACION Y TAPAR P.H. | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-31T13:00 | 2025-07-31T21:00 | 0 | 1222FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1224 | 1.4.2.2.3.16 | RETIRAR DISCOS CIEGOS | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-31T21:00 | 2025-08-01T05:00 | 0 | 1223FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1225 | 1.4.2.2.4 | F-801 | 5.288194444444445d | 126.9167 | 192.0h | 192 | Nativo (factor 1.5x) | 2025-07-24T01:00 | 2025-07-29T08:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE | 8000X 2000 H vacio horizontal | 5
1226 | 1.4.2.2.4.1 | INSTALAR DISCOS CIEGOS | 12.0eh | 12 | 126.9h | 126.9167 | Nativo (factor 10.6x) | 2025-07-24T01:00 | 2025-07-24T13:00 | 0 | 1211FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1227 | 1.4.2.2.4.2 | DESTAPAR P-H. 18"-150# | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-24T13:00 | 2025-07-24T19:00 | 0 | 1226FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1228 | 1.4.2.2.4.3 | VENTILACION | 36.0eh | 36 | 144.0h | 144 | Nativo (factor 4.0x) | 2025-07-24T19:00 | 2025-07-26T07:00 | 0 | 1227FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1229 | 1.4.2.2.4.4 | MONTAR ACCESO | 6.0eh | 6 | 864.0h | 864 | Nativo (factor 144.0x) | 2025-07-26T07:00 | 2025-07-26T13:00 | 0 | 1228FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1230 | 1.4.2.2.4.5 | LIMPIEZA INTERNA COMPLETA | 48.0eh | 48 | 144.0h | 144 | Nativo (factor 3.0x) | 2025-07-26T13:00 | 2025-07-28T13:00 | 0 | 1229FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1231 | 1.4.2.2.4.6 | INSPECCION FINAL | 4.0eh | 4 | 1152.0h | 1152 | Nativo (factor 288.0x) | 2025-07-28T13:00 | 2025-07-28T17:00 | 0 | 1230FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1232 | 1.4.2.2.4.7 | DESMONTAR ACCESO | 3.0eh | 3 | 96.0h | 96 | Nativo (factor 32.0x) | 2025-07-28T17:00 | 2025-07-28T20:00 | 0 | 1231FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1233 | 1.4.2.2.4.8 | TAPAR PASAHOMBRE 30" | 6.0eh | 6 | 72.0h | 72 | Nativo (factor 12.0x) | 2025-07-28T20:00 | 2025-07-29T02:00 | 0 | 1232FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1234 | 1.4.2.2.4.9 | RETIRAR CIEGOS | 6.0eh | 6 | 144.0h | 144 | Nativo (corregido) | 2025-07-29T02:00 | 2025-07-29T08:00 | 0 | 1233FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1235 | 1.4.2.2.5 | F806 | 5.995833333333334d | 143.9 | 5.995833333333334d | 143.9 | MPXJ (validado) | 2025-07-27T19:00 | 2025-08-02T19:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
1236 | 1.4.2.2.5.1 | COLOCAR BC | 12.0eh | 12 | 143.9h | 143.9 | Nativo (factor 12.0x) | 2025-07-27T19:00 | 2025-07-28T07:00 | 0 | 1205FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1237 | 1.4.2.2.5.2 | ABRIR PH | 6.0eh | 6 | 288.0h | 288 | Nativo (factor 48.0x) | 2025-07-28T07:00 | 2025-07-28T13:00 | 0 | 1236FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1238 | 1.4.2.2.5.3 | VENTILACION | 24.0eh | 24 | 144.0h | 144 | Nativo (factor 6.0x) | 2025-07-28T13:00 | 2025-07-29T13:00 | 0 | 1237FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1239 | 1.4.2.2.5.4 | DESARME DE INTERNOS | 16.0eh | 16 | 576.0h | 576 | Nativo (factor 36.0x) | 2025-07-29T13:00 | 2025-07-30T05:00 | 0 | 1238FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1240 | 1.4.2.2.5.5 | MONTAR ACCESO | 8.0eh | 8 | 384.0h | 384 | Nativo (factor 48.0x) | 2025-07-30T05:00 | 2025-07-30T13:00 | 0 | 1239FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1241 | 1.4.2.2.5.6 | LIMPIEZA | 24.0eh | 24 | 192.0h | 192 | Nativo (factor 8.0x) | 2025-07-30T13:00 | 2025-07-31T13:00 | 0 | 1240FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1242 | 1.4.2.2.5.7 | INSPECCION | 8.0eh | 8 | 576.0h | 576 | Nativo (factor 72.0x) | 2025-07-31T13:00 | 2025-07-31T21:00 | 0 | 1241FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1243 | 1.4.2.2.5.8 | RETIRO DE ACCESO | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-31T21:00 | 2025-08-01T03:00 | 0 | 1242FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1244 | 1.4.2.2.5.9 | DESTAPAR TOMAS | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-08-01T03:00 | 2025-08-01T07:00 | 0 | 1243FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1245 | 1.4.2.2.5.10 | ARMAR INTERNOS | 12.0eh | 12 | 96.0h | 96 | Nativo (factor 8.0x) | 2025-08-01T07:00 | 2025-08-01T19:00 | 0 | 1244FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1246 | 1.4.2.2.5.11 | TAPAR PH | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-01T19:00 | 2025-08-02T07:00 | 0 | 1245FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1247 | 1.4.2.2.5.12 | RETIRO DE BC | 12.0eh | 12 | 288.0h | 288 | Nativo (corregido) | 2025-08-02T07:00 | 2025-08-02T19:00 | 0 | 1246FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1248 | 1.4.2.3 | INTERCAMBIADORES | 3.6645833333333333d | 87.95 | 288.0h | 288 | Nativo (factor 3.3x) | 2025-07-20T01:00 | 2025-07-23T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1249 | 1.4.2.3.1 | C-801 ( 1 -U -3/4)-BFT | 3.6645833333333333d | 87.95 | 3.6645833333333333d | 87.95 | MPXJ (validado) | 2025-07-20T01:00 | 2025-07-23T17:00 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 5
1250 | 1.4.2.3.1.1 | COLOCAR DISCOS CIEGOS | 8.0eh | 8 | 88.0h | 87.95 | Nativo (factor 11.0x) | 2025-07-20T01:00 | 2025-07-20T09:00 | 0 | 1131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1251 | 1.4.2.3.1.2 | DESMONTAR TAPA Y CAB.FIJO | 8.0eh | 8 | 192.0h | 192 | Nativo (corregido) | 2025-07-20T09:00 | 2025-07-20T17:00 | 0 | 1250FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1252 | 1.4.2.3.1.3 | DESMONTAR HAZ EN U | 6.0eh | 6 | 192.0h | 192 | Nativo (factor 32.0x) | 2025-07-20T17:00 | 2025-07-20T23:00 | 0 | 1251FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1253 | 1.4.2.3.1.4 | LIMPIEZA DE ENV. Y CAB. | 4.0eh | 4 | 144.0h | 144 | Nativo (factor 36.0x) | 2025-07-20T23:00 | 2025-07-21T03:00 | 0 | 1252FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1254 | 1.4.2.3.1.5 | LIMPIEZA DE HAZ | 8.0eh | 8 | 96.0h | 96 | Nativo (factor 12.0x) | 2025-07-21T03:00 | 2025-07-21T11:00 | 0 | 1253FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1255 | 1.4.2.3.1.6 | INSPECCION | 2.0eh | 2 | 192.0h | 192 | Nativo (factor 96.0x) | 2025-07-21T11:00 | 2025-07-21T13:00 | 0 | 1254FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1256 | 1.4.2.3.1.7 | REPARACIÓN DE CABEZALES | 26.0eh | 26 | 48.0h | 48 | Nativo (factor 1.8x) | 2025-07-21T13:00 | 2025-07-22T15:00 | 0 | 1255FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1257 | 1.4.2.3.1.8 | MONTAR HAZ | 8.0eh | 8 | 624.0h | 624 | Nativo (factor 78.0x) | 2025-07-22T15:00 | 2025-07-22T23:00 | 0 | 1254FS; 1256FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1258 | 1.4.2.3.1.9 | MONTAR CABEZAL FIJO Y TAPA | 4.0eh | 4 | 192.0h | 192 | Nativo (factor 48.0x) | 2025-07-22T23:00 | 2025-07-23T03:00 | 0 | 1257FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1259 | 1.4.2.3.1.10 | PROBAR POR ENVOLV. | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-07-23T03:00 | 2025-07-23T07:00 | 0 | 1258FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1260 | 1.4.2.3.1.11 | TAPAR CAB.FIJO | 4.0eh | 4 | 96.0h | 96 | Nativo (corregido) | 2025-07-23T07:00 | 2025-07-23T11:00 | 0 | 1259FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1261 | 1.4.2.3.1.12 | BRIDAR Y RET.B.C. | 6.0eh | 6 | 96.0h | 96 | Nativo (factor 16.0x) | 2025-07-23T11:00 | 2025-07-23T17:00 | 0 | 1260FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 6
1262 | 1.4.2.4 | VARIOS DE CAÑERIAS | 8.0d | 192 | 144.0h | 144 | Nativo (factor 0.8x) | 2025-07-20T01:00 | 2025-07-28T01:08 | 0 |  |  | 0 | 0.0h | FALSE | FALSE | TRUE |  | 4
1263 | 1.4.2.4.1 | CAMBIO VALVULAS SOLDADAS | 8.0d | 192 | 8.0d | 192 | MPXJ (validado) | 2025-07-20T01:00 | 2025-07-28T01:08 | 0 | 1131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1264 | 1.4.2.4.2 | VALVULAS DE SEGURIDAD | 8.0d | 192 | 8.0d | 192 | MPXJ (validado) | 2025-07-20T01:00 | 2025-07-28T01:08 | 0 | 1131FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 5
1265 | 1.5 | PEM | 38.0eh | 38 | 192.0h | 192 | Nativo (factor 5.1x) | 2025-08-02T19:00 | 2025-08-04T09:00 | 0 | 1152FS; 1167FS; 1185FS; 1201FS; 1207FS; 1224FS; 1234FS; 1247FS; 1261FS |  | 0 | 0.0h | FALSE | FALSE | FALSE |  | 2

## Correction_Summary
Metric | Count | Percentage
Tasks from Nativo (corregido) | 283 | 22.4%
Tasks from Nativo (factor 12.0x) | 81 | 6.4%
Tasks from Nativo (factor 48.0x) | 74 | 5.8%
Tasks from Nativo (factor 36.0x) | 51 | 4.0%
Tasks from Nativo (factor 72.0x) | 48 | 3.8%
Tasks from Nativo (factor 16.0x) | 46 | 3.6%
Tasks from Nativo (factor 8.0x) | 33 | 2.6%
Tasks from MPXJ (validado) | 31 | 2.4%
Tasks from Nativo (factor 6.0x) | 30 | 2.4%
Tasks from Nativo (factor 32.0x) | 29 | 2.3%
Tasks from Nativo (factor 4.0x) | 23 | 1.8%
Tasks from Nativo (factor 144.0x) | 21 | 1.7%
Tasks from Nativo (factor 18.0x) | 19 | 1.5%
Tasks from Nativo (factor 96.0x) | 17 | 1.3%
Tasks from Nativo (factor 30.0x) | 17 | 1.3%
Tasks from Nativo (factor 60.0x) | 15 | 1.2%
Tasks from Nativo (factor 28.8x) | 14 | 1.1%
Tasks from Nativo (factor 288.0x) | 13 | 1.0%
Tasks from Nativo (factor 5.3x) | 13 | 1.0%
Tasks from Nativo (factor 3.0x) | 12 | 0.9%
Tasks from Nativo (factor 40.0x) | 12 | 0.9%
Tasks from Nativo (factor 4.8x) | 11 | 0.9%
Tasks from Nativo (factor 1.5x) | 10 | 0.8%
Tasks from Nativo (factor 1.3x) | 10 | 0.8%
Tasks from Nativo (factor 9.6x) | 9 | 0.7%
Tasks from Nativo (factor 108.0x) | 9 | 0.7%
Tasks from Nativo (factor 14.4x) | 9 | 0.7%
Tasks from Nativo (factor 19.2x) | 9 | 0.7%
Tasks from Nativo (factor 2.0x) | 8 | 0.6%
Tasks from Nativo (factor 0.7x) | 7 | 0.6%
Tasks from Nativo (factor 2.7x) | 6 | 0.5%
Tasks from Nativo (factor 0.8x) | 6 | 0.5%
Tasks from Nativo (factor 90.0x) | 6 | 0.5%
Tasks from Nativo (factor 0.6x) | 6 | 0.5%
Tasks from Nativo (MPXJ=0) | 5 | 0.4%
Tasks from Nativo (factor 9.0x) | 5 | 0.4%
Tasks from Nativo (factor 0.5x) | 5 | 0.4%
Tasks from Nativo (factor 3.2x) | 5 | 0.4%
Tasks from Nativo (factor 2.4x) | 5 | 0.4%
Tasks from Nativo (factor 1.2x) | 5 | 0.4%
Tasks from Nativo (factor 6.4x) | 5 | 0.4%
Tasks from Nativo (factor 216.0x) | 5 | 0.4%
Tasks from Nativo (factor 10.0x) | 5 | 0.4%
Tasks from Nativo (factor 192.0x) | 4 | 0.3%
Tasks from Nativo (factor 10.7x) | 4 | 0.3%
Tasks from Nativo (factor 0.4x) | 4 | 0.3%
Tasks from Nativo (factor 6.7x) | 4 | 0.3%
Tasks from Nativo (factor 1.4x) | 4 | 0.3%
Tasks from Nativo (factor 2.3x) | 4 | 0.3%
Tasks from Nativo (factor 1.8x) | 4 | 0.3%
Tasks from Nativo (factor 80.0x) | 3 | 0.2%
Tasks from Nativo (factor 5.8x) | 3 | 0.2%
Tasks from Nativo (factor 5.1x) | 3 | 0.2%
Tasks from Nativo (factor 2.9x) | 3 | 0.2%
Tasks from Nativo (factor 2.5x) | 3 | 0.2%
Tasks from Nativo (factor 1.6x) | 3 | 0.2%
Tasks from Nativo (factor 11.0x) | 3 | 0.2%
Tasks from Nativo (factor 432.0x) | 3 | 0.2%
Tasks from Nativo (factor 360.0x) | 3 | 0.2%
Tasks from Nativo (factor 18.5x) | 3 | 0.2%
Tasks from Nativo (factor 1.7x) | 3 | 0.2%
Tasks from Nativo (factor 1.9x) | 3 | 0.2%
Tasks from Nativo (factor 43.2x) | 3 | 0.2%
Tasks from Nativo (factor 7.2x) | 3 | 0.2%
Tasks from Nativo (factor 0.2x) | 3 | 0.2%
Tasks from Nativo (factor 11.7x) | 3 | 0.2%
Tasks from Nativo (factor 57.6x) | 3 | 0.2%
Tasks from Nativo (factor 4.5x) | 3 | 0.2%
Tasks from Nativo (factor 120.0x) | 3 | 0.2%
Tasks from Nativo (factor 0.0x) | 3 | 0.2%
Tasks from Nativo (factor 30.9x) | 2 | 0.2%
Tasks from Nativo (factor 7.5x) | 2 | 0.2%
Tasks from Nativo (factor 4.2x) | 2 | 0.2%
Tasks from Nativo (factor 2.2x) | 2 | 0.2%
Tasks from Nativo (factor 576.0x) | 2 | 0.2%
Tasks from Nativo (factor 5.6x) | 2 | 0.2%
Tasks from Nativo (factor 70.0x) | 2 | 0.2%
Tasks from Nativo (factor 9.2x) | 2 | 0.2%
Tasks from Nativo (factor 6.9x) | 2 | 0.2%
Tasks from Nativo (factor 4.7x) | 2 | 0.2%
Tasks from Nativo (factor 4.6x) | 2 | 0.2%
Tasks from Nativo (factor 17.3x) | 2 | 0.2%
Tasks from Nativo (factor 13.2x) | 2 | 0.2%
Tasks from Nativo (factor 19.0x) | 2 | 0.2%
Tasks from Nativo (factor 9.3x) | 2 | 0.2%
Tasks from Nativo (factor 13.1x) | 2 | 0.2%
Tasks from Nativo (factor 78.0x) | 2 | 0.2%
Tasks from Nativo (factor 15.0x) | 2 | 0.2%
Tasks from Nativo (factor 17.0x) | 2 | 0.2%
Tasks from Nativo (factor 100.0x) | 2 | 0.2%
Tasks from Nativo (factor 12.8x) | 2 | 0.2%
Tasks from Nativo (factor 0.3x) | 2 | 0.2%
Tasks from Nativo (factor 64.0x) | 1 | 0.1%
Tasks from Nativo (factor 208.0x) | 1 | 0.1%
Tasks from Nativo (factor 3.7x) | 1 | 0.1%
Tasks from Nativo (factor 864.0x) | 1 | 0.1%
Tasks from Nativo (factor 7.3x) | 1 | 0.1%
Tasks from Nativo (factor 86.0x) | 1 | 0.1%
Tasks from Nativo (factor 76.0x) | 1 | 0.1%
Tasks from Nativo (factor 37.2x) | 1 | 0.1%
Tasks from Nativo (factor 35.1x) | 1 | 0.1%
Tasks from Nativo (factor 12.2x) | 1 | 0.1%
Tasks from Nativo (factor 8.7x) | 1 | 0.1%
Tasks from Nativo (factor 115.2x) | 1 | 0.1%
Tasks from Nativo (factor 3.6x) | 1 | 0.1%
Tasks from Nativo (factor 172.8x) | 1 | 0.1%
Tasks from Nativo (factor 10.6x) | 1 | 0.1%
Tasks from Nativo (factor 30.1x) | 1 | 0.1%
Tasks from Nativo (factor 34.6x) | 1 | 0.1%
Tasks from Nativo (factor 3.9x) | 1 | 0.1%
Tasks from Nativo (factor 222.0x) | 1 | 0.1%
Tasks from Nativo (factor 9.8x) | 1 | 0.1%
Tasks from Nativo (factor 15.6x) | 1 | 0.1%
Tasks from Nativo (factor 12.1x) | 1 | 0.1%
Tasks from Nativo (factor 7.4x) | 1 | 0.1%
Tasks from Nativo (factor 29.8x) | 1 | 0.1%
Tasks from Nativo (factor 5.4x) | 1 | 0.1%
Tasks from Nativo (factor 3.5x) | 1 | 0.1%
Tasks from Nativo (factor 7.7x) | 1 | 0.1%
Tasks from Nativo (factor 520.6x) | 1 | 0.1%
Tasks from Nativo (factor 7.0x) | 1 | 0.1%
Tasks from Nativo (factor 4.1x) | 1 | 0.1%
Tasks from Nativo (factor 4.4x) | 1 | 0.1%
Tasks from Nativo (factor 368.0x) | 1 | 0.1%
Tasks from Nativo (factor 607.6x) | 1 | 0.1%
Tasks from Nativo (factor 218.9x) | 1 | 0.1%
Tasks from Nativo (factor 5.2x) | 1 | 0.1%
Tasks from Nativo (factor 188.0x) | 1 | 0.1%
Tasks from Nativo (factor 16.9x) | 1 | 0.1%
Tasks from Nativo (factor 55.0x) | 1 | 0.1%
Tasks from Nativo (factor 3.4x) | 1 | 0.1%
Tasks from Nativo (factor 43.7x) | 1 | 0.1%
Tasks from Nativo (factor 31.6x) | 1 | 0.1%
Tasks from Nativo (factor 11.8x) | 1 | 0.1%
Tasks from Nativo (factor 84.0x) | 1 | 0.1%
Tasks from Nativo (factor 5.0x) | 1 | 0.1%
Tasks from MPXJ | 1 | 0.1%
Tasks from Nativo (factor 30.7x) | 1 | 0.1%
Tasks from Nativo (factor 2.8x) | 1 | 0.1%
Tasks from Nativo (factor 16.5x) | 1 | 0.1%
Tasks from Nativo (factor 154.3x) | 1 | 0.1%
Tasks from Nativo (factor 106.7x) | 1 | 0.1%
Tasks from Nativo (factor 42.2x) | 1 | 0.1%
Tasks from Nativo (factor 101.1x) | 1 | 0.1%
Tasks from Nativo (factor 240.0x) | 1 | 0.1%
Tasks from Nativo (factor 34.0x) | 1 | 0.1%
Tasks from Nativo (factor 42.4x) | 1 | 0.1%
Tasks from Nativo (factor 50.6x) | 1 | 0.1%
Tasks from Nativo (factor 107.1x) | 1 | 0.1%
Tasks from Nativo (factor 16.8x) | 1 | 0.1%
Tasks from Nativo (factor 384.0x) | 1 | 0.1%
Tasks from Nativo (factor 35.0x) | 1 | 0.1%
Tasks from Nativo (factor 86.4x) | 1 | 0.1%
Tasks from Nativo (factor 12.3x) | 1 | 0.1%
Tasks from Nativo (factor 30.4x) | 1 | 0.1%
Tasks from Nativo (factor 15.2x) | 1 | 0.1%
Tasks from Nativo (factor 16.1x) | 1 | 0.1%
Tasks from Nativo (factor 156.0x) | 1 | 0.1%
Tasks from Nativo (factor 46.0x) | 1 | 0.1%
Tasks from Nativo (factor 117.9x) | 1 | 0.1%
Tasks from Nativo (factor 97.9x) | 1 | 0.1%
Tasks from Nativo (factor 57.4x) | 1 | 0.1%
Tasks from Nativo (factor 2136.0x) | 1 | 0.1%
Tasks from Nativo (factor 9.1x) | 1 | 0.1%
Tasks from Nativo (factor 54.2x) | 1 | 0.1%
Tasks from Nativo (factor 400.0x) | 1 | 0.1%
Tasks from Nativo (factor 46.5x) | 1 | 0.1%
Tasks from Nativo (factor 10.8x) | 1 | 0.1%
Tasks from Nativo (factor 15.3x) | 1 | 0.1%
Tasks from Nativo (factor 12.5x) | 1 | 0.1%
Tasks from Nativo (factor 18.2x) | 1 | 0.1%
Tasks from Nativo (factor 3.8x) | 1 | 0.1%
Tasks from Nativo (factor 43.1x) | 1 | 0.1%
Tasks from Nativo (factor 9.7x) | 1 | 0.1%
Tasks from Nativo (factor 440.0x) | 1 | 0.1%
Tasks from Nativo (factor 17.4x) | 1 | 0.1%
Tasks from Nativo (factor 63.0x) | 1 | 0.1%
Tasks from Nativo (factor 180.0x) | 1 | 0.1%
Tasks from Nativo (factor 106.4x) | 1 | 0.1%
Tasks from Nativo (factor 13.3x) | 1 | 0.1%
Tasks from Nativo (factor 8.3x) | 1 | 0.1%
Tasks from Nativo (factor 8.2x) | 1 | 0.1%
Tasks from Nativo (factor 11.9x) | 1 | 0.1%
Tasks from Nativo (factor 8.5x) | 1 | 0.1%
Tasks from Nativo (factor 8.8x) | 1 | 0.1%
Tasks from Nativo (factor 32.1x) | 1 | 0.1%
Tasks from Nativo (factor 11.3x) | 1 | 0.1%
Tasks from Nativo (factor 33.9x) | 1 | 0.1%
Tasks from Nativo (factor 98.2x) | 1 | 0.1%
Tasks from Nativo (factor 29.3x) | 1 | 0.1%
Tasks from Nativo (factor 49.5x) | 1 | 0.1%
Tasks from Nativo (factor 200.0x) | 1 | 0.1%
Tasks from Nativo (factor 3.3x) | 1 | 0.1%
Total tasks | 1266 | 100%
Original MPXJ hours | 71190
Corrected hours | 741903
Correction factor | 10.4x